## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Sub-Surface water based Churulia PWSS. | SM/11205 | Augmentation | Acceptance cum work order for Distribution Network including providing FHTC Work under Augmentation of Churulia and its adjoining mouzas (Zone-II) PWSS Block- Jamuira, Dist- Paschim Bardhaman under RCFA Div-I Phe,Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000103/2022-2023 | 1276/RCD-I | 02/06/2022 | 31/08/2022 | MD AAMIR KHAN | 70.29 | 48.29 | 68.71 | 100
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Sub-Surface water based Churulia PWSS. | SM/11205 | Augmentation | Formal Work Order for Augmentation of Churulia and its adjoining mouzas (Zone-I) PWSS by construction of OHR of capacity 100 cum with 20 mtr staging height LDS with necessary interconnection & FHTC work Block-Jamuria, Dist-Paschim Bardhaman under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000118/2022-2023 | 1372/RCD-I | 16/06/2022 | 31/08/2025 | ASHA CONSTRUCTION | 306.57 | 156.81 | 51.15 | 100
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Sub-Surface water based Churulia PWSS. | SM/11205 | Augmentation | Acceptance cum work order for Sinking of 2 (Two) no. 200 mm dia river bed tube well in the river Ajoy of Augmentation of Churulia and its Adjoining Mouzas PWSS under RCFA Division-I PHE Dte.(SL NO 09) | Assistant Engineer 2 | Junior Engineer | ORD/000114/2022-2023 | 1283/RCD I | 02/06/2022 | 02/07/2022 | R B ENTERPRISE | 13 | 8.2 | 63.07 | 80
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Sub-Surface water based Churulia PWSS. | SM/11205 | Augmentation | Acceptance cum work order for laying of 150 mm and 200 mm dia rising main for the proposed augmentation work of Churulia and its adjoining mouzas piped water supply scheme under RCFA Div-I, PHE Dte | Assistant Engineer 2 | Junior Engineer | ORD/000613/2022-2023 | 3273/RCD I | 20/12/2022 | 01/09/2024 | T.R. ENTERPRISE | 21.17 | 10.65 | 50.3 | 70
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Sub-Surface water based Churulia PWSS. | SM/11205 | Augmentation | Acceptance cum work order for construction of 200 cum capacity 20 mtr staging height RCC over Head Reservoir, pipe connection and cost of pipes specials of Churulia piped Water Supply Scheme under RCFA Div-I PHE Dte in the District of Paschim Bardhaman. Ref PC-I/OHR/09/2021 | Assistant Engineer 2 | Junior Engineer | ORD/000543/2022-2023 | 3245/RCD I | 20/12/2022 | 20/09/2023 | ASHA CONSTRUCTION | 71.55 | 71.55 | 100 | 100
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Sub-Surface water based Churulia PWSS. | SM/11205 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000024/2022-2023 | 3127 | 09/12/2022 | 09/12/2022 | Resource Division | 178.46 | 0 | 0 | 0
7 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Sub-Surface water based Churulia PWSS. | SM/11205 | Augmentation | Acceptance cum work Order for Repairing, Renovation, renewing & oversauling & obsolete i) for 2 nos. Iron Removal Plant (Pressure type) each capacity 45 cum/Hr at Churulia Head Work Site for Augmentation of Churulia W/S Scheme under RCFA Division-I PHE Dte. (Part-A) ii) for 3 nos. Iron Removal Plant (Pressure type of capacity 50 cum/hr 1no. & 75 cum/hr-2nos) at Madantore Head Works site for Madantore W/S Scheme under RCFA Division-I PHE Dte (Part-B) iii) for 4 nos. iron removal Plant (Pressure type) each capacity 20 cum /hr at Pandabeswar Head Works Site for Pandabeswar W/S Scheme under RCFA Division-I PHE Dte. (Part-C) iv) for 2 nos. iron Removal Plant (Pressure type) each capacity 50 cum/hr at Madanpur Head Work Site under RCFA Division-I PHE Dte. (Part-D). | Assistant Engineer 2 | Junior Engineer | ORD/000009/2023-2024 | 1391/RCD I | 11/04/2023 | 01/04/2024 | TARAPRASAD SARKAR | 97.93 | 45.74 | 46.71 | 100
8 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Sub-Surface water based Churulia PWSS. | SM/11205 | Augmentation | Acceptance cum work order Construction of Concrete retaining wall with land development Churulia Ajoy River Bed Site under Augmentation of Churulia W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000852/2022-2023 | 1088/RCD-I | 23/03/2023 | 21/06/2023 | S. CHAKRABORTY & CO. | 44.66 | 40.55 | 90.8 | 100
9 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Sub-Surface water based Churulia PWSS. | SM/11205 | Augmentation | Acceptance cum work order for Sinking of 6 (Six) nos 200 mm dia river bed tube well in river Ajoy of Augmentation of Churulia PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000761/2022-2023 | 388/RCDI | 30/01/2023 | 16/03/2023 | ASHA CONSTRUCTION | 41.46 | 40.95 | 98.77 | 100
10 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Sub-Surface water based Churulia PWSS. | SM/11205 | Augmentation | Acceptance come work order for Balance work for distribution network of Churulia Madhudanga and its adjoining mouzas (Zone-II) under Augmentation of Churulia W/S Scheme under RCFA Division-I PHE Dte. (Sl No. 20) | Assistant Engineer 2 | Junior Engineer | ORD/000854/2022-2023 | 1087/RCD-I | 23/03/2023 | 21/06/2023 | MD AAMIR KHAN | 16.38 | 16.32 | 99.66 | 100
11 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation of Sub-Surface water based Churulia PWSS. | SM/11205 | Augmentation | Supply,delivery & installation of Electro-Mechanical equipment and other allied works at Ajoyghat Head Works Site in the basis of "Augmentation of Churulia & Its Adjoining Mouzas"Piped Water Supply Scheme under Asansol Mechanical Division,P.H.E Dte. Block-Jamuria, District-Paschim Bardhaman. | Assistant Engineer-I | Junior Engineer-5 | ORD/000538/2022-2023 | 747/AMD | 16/03/2023 | 21/11/2026 | BENGAL CONSTRUCTION | 116.52 | 60.15 | 51.62 | 100
12 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Sub-Surface water based Churulia PWSS. | SM/11205 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000031/2022-2023 | 106/RCD-I | 20/01/2023 | 20/01/2023 | Resource Division | 159.09 | 0 | 0 | 0
13 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Sub-Surface water based Churulia PWSS. | SM/11205 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000004/2023-2024 | 1639/RCD-I | 27/04/2023 | 27/04/2023 | Resource Division | 45.72 | 0 | 0 | 0
14 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation of Sub-Surface water based Churulia PWSS. | SM/11205 | Augmentation | Quotation for New Connection at Churulia. |  |  | BILL/00022/2023-2024 | BP-2023-24-6 | 19/05/2023 | 19/05/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.94 | 0 | 0 | 0
15 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation of Sub-Surface water based Churulia PWSS. | SM/11205 | Augmentation | Installation of yard lighting arrangement, electrical wiring of pump house and other allied works at Churulia Pump House under Augmentation of Churulia Piped Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-5 | ORD/000036/2025-2026 | 955/AMD | 16/05/2025 | 03/01/2026 | CIEMENICS | 3.67 | 0 | 0 | 100
Total | [13 empty] | 1192.41 | 499.21 | 41.87