## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/A TO ACCOMMODATE FHTC | SM/11575 | Augmentation | Acceptance cum work order for Distribution Network for Augmentation of Ondal (Phase ¿ II/A) Piped Water Supply Scheme including FHTC & allied work within Ondal Block under RCFA Division-I PHE Dte. (Part - 3) | Assistant Engineer 2 | Junior Engineer | ORD/000245/2022-2023 | 2211/RCD-I | 14/09/2022 | 29/10/2022 | UNITED CONSTRUCTION | 88.03 | 74.93 | 85.12 | 90
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/A TO ACCOMMODATE FHTC | SM/11575 | Augmentation | Acceptance cum work order of distribution network for augmentation Of Ondal (Phase-II/A) piped Water Supply scheme including FHTC & allied works Ondal Block under RCFA Div-I PHE Dte.(Part-2) | Assistant Engineer 2 | Junior Engineer | ORD/000299/2022-2023 | 2483/RCD I | 17/10/2022 | 01/12/2022 | SOMNATH SAMANTA | 89.8 | 65.01 | 72.39 | 90
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/A TO ACCOMMODATE FHTC | SM/11575 | Augmentation | Acceptance cum work order of distribution network for augmentation of Ondal (Phase II/A) piped water supply scheme including FHTC & allied work within Ondal Block under RCFA Div-I, PHE Dte. (Part-I) | Assistant Engineer 2 | Junior Engineer | ORD/000296/2022-2023 | 2482/RCD I | 17/10/2022 | 01/12/2022 | SIMA ENTERPRISE | 89.81 | 71.28 | 79.37 | 90
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/A TO ACCOMMODATE FHTC | SM/11575 | Augmentation | Detailed Route Survey, Design Drawing & DPR Preparation for Ondal (Phase-II) Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 03) | Assistant Engineer 2 | Junior Engineer | ORD/000537/2021-2022 | 502/RCD-I | 24/02/2022 | 11/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.54 | 4.54 | 100 | 0
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/A TO ACCOMMODATE FHTC | SM/11575 | Augmentation | Acceptance cum work order for Construction of CWR (Clear Water Reservoir) of capacity 200 cum & allied work at Ramprasadpur H/W Site under Augmentation of Sub Surface Water Supply Scheme of Ondal Phase-II/A Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000575/2022-2023 | 3284/RCDI | 20/12/2022 | 20/03/2023 | SOMNATH SAMANTA | 22.05 | 22.01 | 99.8 | 70
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/A TO ACCOMMODATE FHTC | SM/11575 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000018/2022-2023 | 3131 | 09/12/2022 | 09/12/2022 | Resource Division | 106.94 | 0 | 0 | 0
7 | PASCHIM BARDHAMAN |  | Asansol Mechanical | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/A TO ACCOMMODATE FHTC | SM/11575 | Augmentation | Providing and Installation of Electro-Mechanical Equipments and allied works under Augmentation of Andal (Phase-II/A) Water Supply Scheme, Block : Andal, Dist -Paschim Bardhaman. | Assistant Engineer-I | Junior Engineer-3 | ORD/000435/2022-2023 | 490/AMD | 22/02/2023 | 20/07/2026 | EASTERN INDIA SALES AND SERVICE | 151.5 | 105.83 | 69.85 | 100
8 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/A TO ACCOMMODATE FHTC | SM/11575 | Augmentation | Acceptance cum work order for Additional for Distribution Network for Augmentation of Ondal (Phase-II/A) Piped Water Supply Scheme (Part-1) Block- Andal Dist - Paschim Bardhaman under RCFA Division-I PHE Dte. (Sl No. 08) | Assistant Engineer 2 | Junior Engineer | ORD/000885/2022-2023 | 1129/ RCD I | 24/03/2023 | 23/04/2023 | SIMA ENTERPRISE | 13.76 | 9.36 | 68.05 | 80
9 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/A TO ACCOMMODATE FHTC | SM/11575 | Augmentation | Acceptance cum work order for Additional for Distribution Network for Augmentation of Ondal (Phase-II/A) Piped Water Supply Scheme (Part-2) Block Andal, Dist-Paschim Bardhaman under RCFA Div-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000228/2023-2024 | 2213/RCD-I | 17/07/2023 | 16/08/2023 | SOMNATH SAMANTA | 11.57 | 6.78 | 58.58 | 100
10 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/A TO ACCOMMODATE FHTC | SM/11575 | Augmentation | Acceptance cum work order for Additional for Distribution Network for Augmentation of Ondal (Phase-II/A) Piped Water Supply Scheme (Part-3) Block Andal, Dist-Paschim Bardhaman under RCFA Div-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000230/2023-2024 | 2214/RCD-I | 17/07/2023 | 16/08/2023 | UNITED CONSTRUCTION | 56.6 | 24.99 | 44.16 | 50
11 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/A TO ACCOMMODATE FHTC | SM/11575 | Augmentation | Acceptance cum work order for Repair and renovation works of One no. RCC Elevated Reservoir of capacity 550 cum at Dignala for Augmentation of Ondal Phase-II/A Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 02) | Assistant Engineer 2 | Junior Engineer | ORD/000873/2022-2023 | 1124/ RCD I | 24/03/2023 | 22/06/2023 | M/S SUBHRADEEP | 11 | 9.25 | 84.14 | 100
12 | PASCHIM BARDHAMAN |  | Asansol Mechanical | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/A TO ACCOMMODATE FHTC | SM/11575 | Augmentation | Quotation for enhancement of load at Basudebpur under Augmentation of Andal. |  |  | BILL/00453/2023-2024 | BP-2023-24-33 | 14/09/2023 | 14/09/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.32 | 0 | 0 | 0
13 | PASCHIM BARDHAMAN |  | Asansol Mechanical | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/A TO ACCOMMODATE FHTC | SM/11575 | Augmentation | Quotation Money for Load Enhancement at Andal |  |  | BILL/00023/2023-2024 | BP-2023-24-5 | 19/05/2023 | 19/05/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 11.28 | 0 | 0 | 0
14 | PASCHIM BARDHAMAN |  | Asansol Mechanical | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/A TO ACCOMMODATE FHTC | SM/11575 | Augmentation | Deposit for Earnest Money Application |  |  | BILL/00307/2023-2024 | BP-2023-24-22 | 25/07/2023 | 25/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.05 | 0 | 0 | 0
15 | PASCHIM BARDHAMAN |  | Asansol Mechanical | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/A TO ACCOMMODATE FHTC | SM/11575 | Augmentation | Deposition of the Earnest Money for the proposed enhancement of the load at Ramprasadpur Andal BDN |  |  | BILL/00169/2022-2023 | BP-2022-23-27 | 31/01/2023 | 31/01/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.05 | 0 | 0 | 0
16 | PASCHIM BARDHAMAN |  | Asansol Mechanical | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/A TO ACCOMMODATE FHTC | SM/11575 | Augmentation | Quotation for enhancement of load at 11 KV from 200 KVA to 305 KVA to your premises at Ramprasadpur,Andal, Paschim Burdwan. |  |  | BILL/00223/2022-2023 |  | 23/02/2023 | 23/02/2023 | W.B.S.E.D.C.L | 11.28 | 0 | 0 | 0
17 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/A TO ACCOMMODATE FHTC | SM/11575 | Augmentation | Acceptance cum work order for Balance work for pushing 300 mm dia MS Rising main through 600 mm Dia RCC pipe road crossing trenchless method under NH-19 at front topline more under OCP based Kajora site Augmentation of sub surface water supply scheme ondal phase-II/A under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000179/2024-2025 | 2427/RCD-I | 26/09/2024 | 26/10/2024 | T M CONCRETE CREATION PVT.LTD | 12.98 | 0 | 0 | 100
Total | [13 empty] | 681.57 | 393.99 | 57.81