## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/B TO ACCOMMODATE FHTC | SM/11576 | Augmentation | Distribution network for Augmentation of Ondal (Phase-II/B) Piped Water Supply Scheme including FHTC & allied work within Ondal Block under RCFA Division-I PHE Dte. (Part-2) | Assistant Engineer 2 | Junior Engineer | ORD/000332/2022-2023 | 2837/RCDI | 28/10/2022 | 27/11/2022 | M/S MONI TRADERS | 105.03 | 0 | 0 | 0
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/B TO ACCOMMODATE FHTC | SM/11576 | Augmentation | Formal work order for distribution network for augmentation of Ondal (Phase-II/B) piped Water Supply Scheme including FHTC & allied works within Ondal Block under RCFA Div-I, PHE Dte.(Part-3) | Assistant Engineer 2 | Junior Engineer | ORD/000600/2022-2023 | 15/RCDI | 05/01/2023 | 04/02/2023 | DAS & CHAKRABORTY | 178.26 | 60.64 | 34.02 | 40
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/B TO ACCOMMODATE FHTC | SM/11576 | Augmentation | Distribution network for Augmentation of Ondal (Phase-II/B) Piped Water Supply Scheme including FHTC & allied work within Ondal Block under RCFA Division-I PHE Dte. (Part-1) | Assistant Engineer 2 | Junior Engineer | ORD/000331/2022-2023 | 2836/RCDI | 28/10/2022 | 27/11/2022 | M/S KALYANI ENTERPRISE | 88.58 | 22.06 | 24.91 | 50
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/B TO ACCOMMODATE FHTC | SM/11576 | Augmentation | Acceptance cum work order for laying of 200 mm dia rising main from Dignala OHR ste to proposed OHR site at Andal BL & LRO office for the proposed Augmentation work of Andal Phase-II/B Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000645/2022-2023 | 343/RCDI | 30/01/2023 | 14/02/2023 | D.S.C. CONCERN | 7.65 | 0 | 0 | 20
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/B TO ACCOMMODATE FHTC | SM/11576 | Augmentation | Formal order for distribution network for augmentation of Ondal (Phase -II/B) piped Water Supply scheme including FHTC & allied work within ondal block under RCFA Div-I, PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000780/2022-2023 | 819/RCDI | 10/03/2023 | 09/04/2023 | M/S MONI TRADERS | 108.27 | 34.49 | 31.85 | 60
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/B TO ACCOMMODATE FHTC | SM/11576 | Augmentation | Formal work order for construction of 450 cum capacity 20 mtr staging height RCC over head reservoir pipe connection and cost of pipes, specials at Andal village for Augmentation of Ondal Phase-II/B piped water supply scheme under RCFA Div-I, PHE Dte. in the District of Paschim Bardhaman. | Assistant Engineer 2 | Junior Engineer | ORD/000598/2022-2023 | 18 /RCD I | 05/01/2023 | 14/01/2023 | AMAR CONSTRUCTION | 129.3 | 122.84 | 95 | 100
7 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/B TO ACCOMMODATE FHTC | SM/11576 | Augmentation | Acceptance cum work order forConstruction of Boundary Wall with Gate at OHR Site (Length-160 mtrs) at Ondal Block for Augmentation of Ondal Phase- II/B Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000879/2022-2023 | 1126/ RCD I | 24/03/2023 | 23/04/2023 | AMAR CONSTRUCTION | 13.43 | 6.64 | 49.4 | 100
8 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/B TO ACCOMMODATE FHTC | SM/11576 | Augmentation | Acceptance cum Work Order for Land development with approach road including internal drain at Head Works Site for Augmentation of Ondal Phase II/B Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman (Sl No. 04) | Assistant Engineer 2 | Junior Engineer | ORD/000888/2022-2023 | 1148/RCD-1 | 24/03/2023 | 23/04/2023 | AMAR CONSTRUCTION | 6.5 | 3.04 | 46.84 | 100
9 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/B TO ACCOMMODATE FHTC | SM/11576 | Augmentation | Acceptance cum Work Order for Construction of Guard room with toilet under Ondal Phase-II/B Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 06) | Assistant Engineer 2 | Junior Engineer | ORD/000896/2022-2023 | 1150/RCD-1 | 24/03/2023 | 23/05/2023 | SUBHADEEP DAS | 5.64 | 5.53 | 98.07 | 100
10 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/B TO ACCOMMODATE FHTC | SM/11576 | Augmentation | Acceptance cum Work Order for Construction of Chlorine Room (Size 4.1 m x 3.5 m out to out) at OHR Site for Augmentation of Ondal Phase-II/B Piped Water Supply Scheme under RCFA Division-I PHE Dte.(Sl No. 34) | Assistant Engineer 2 | Junior Engineer | ORD/000915/2022-2023 | 1177/RCD-1 | 24/03/2023 | 22/06/2023 | SUBHADEEP DAS | 4.61 | 3.91 | 84.93 | 100
Total | [13 empty] | 647.27 | 259.15 | 40.04