## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/B TO ACCOMMODATE FHTC | SM/11576 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000016/2022-2023 | 2927/RCD-I | 17/11/2022 | 17/11/2022 | Resource Division | 85.11 | 0 | 0 | 0
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/B TO ACCOMMODATE FHTC | SM/11576 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000019/2022-2023 | 3125 | 09/12/2022 | 09/12/2022 | Resource Division | 220.25 | 0 | 0 | 0
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/B TO ACCOMMODATE FHTC | SM/11576 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000012/2023-2024 | 2206/RCD-I | 17/07/2023 | 17/07/2023 | Resource Division | 24.19 | 0 | 0 | 0
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/B TO ACCOMMODATE FHTC | SM/11576 | Augmentation | Acceptance cum Work Order for Construction of Guard room with toilet under Ondal Phase-II/B Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 06) | Assistant Engineer 2 | Junior Engineer | ORD/000896/2022-2023 | 1150/RCD-1 | 24/03/2023 | 23/05/2023 | SUBHADEEP DAS | 5.64 | 0 | 0 | 100
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/B TO ACCOMMODATE FHTC | SM/11576 | Augmentation | Acceptance cum work order for Allied work of 600 mm Dia RCC pipe road crossing trenchless method jack pushing under NH-19 at Railway Kajora more to Andal Police station under OCP based KAJORA of Augmentation sub surface water supply scheme Ondal Phase-II/B under RCFA Division-I PHE, Dte | Assistant Engineer 2 | Junior Engineer | ORD/000183/2024-2025 | 2431/RCD-I | 26/09/2024 | 25/11/2024 | T M CONCRETE CREATION PVT.LTD | 73.64 | 0 | 0 | 100
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/B TO ACCOMMODATE FHTC | SM/11576 | Augmentation | Distribution network for Augmentation of Ondal (Phase-II/B) Piped Water Supply Scheme including FHTC & allied work within Ondal Block under RCFA Division-I PHE Dte. (Part-1) | Assistant Engineer 2 | Junior Engineer | ORD/000331/2022-2023 | 2836/RCDI | 28/10/2022 | 31/03/2025 | M/S KALYANI ENTERPRISE | 88.58 | 0 | 0 | 60
7 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/B TO ACCOMMODATE FHTC | SM/11576 | Augmentation | Acceptance cum work order for laying of 200 mm dia rising main from Dignala OHR ste to proposed OHR site at Andal BL & LRO office for the proposed Augmentation work of Andal Phase-II/B Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000645/2022-2023 | 343/RCDI | 30/01/2023 | 01/05/2025 | D.S.C. CONCERN | 7.65 | 0 | 0 | 65
8 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/B TO ACCOMMODATE FHTC | SM/11576 | Augmentation | Formal work order for distribution network for augmentation of Ondal (Phase-II/B) piped Water Supply Scheme including FHTC & allied works within Ondal Block under RCFA Div-I, PHE Dte.(Part-3) | Assistant Engineer 2,Assistant Engineer 8 | Junior Engineer,Junior Engineer 15 | ORD/000600/2022-2023 | 15/RCDI | 05/01/2023 | 04/02/2023 | DAS & CHAKRABORTY | 178.26 | 0 | 0 | 85
9 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/B TO ACCOMMODATE FHTC | SM/11576 | Augmentation | Formal order for distribution network for augmentation of Ondal (Phase -II/B) piped Water Supply scheme including FHTC & allied work within ondal block under RCFA Div-I, PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000780/2022-2023 | 819/RCDI | 10/03/2023 | 09/04/2023 | M/S MONI TRADERS | 108.27 | 0 | 0 | 60
10 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/B TO ACCOMMODATE FHTC | SM/11576 | Augmentation | Supply & erection of Swajal Village Boards (102 nos) having M.S. Channel/Angle Posts & 1.5 mm thick M.S. synthetic enamel paint over a coat of red oxied primer including lettering complete at different places under Augmentation of sub surface water based for PWSS Ondal Phase-II/B under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer 2,Assistant Engineer 3 | Junior Engineer 12 | ORD/000349/2024-2025 | Camp-02_Swajal/AE/24-25 | 03/10/2024 | 31/01/2025 | SHARMA ENGINEERING WORKS | 20.55 | 0 | 0 | 50
11 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/B TO ACCOMMODATE FHTC | SM/11576 | Augmentation | Formal work order for construction of 450 cum capacity 20 mtr staging height RCC over head reservoir pipe connection and cost of pipes, specials at Andal village for Augmentation of Ondal Phase-II/B piped water supply scheme under RCFA Div-I, PHE Dte. in the District of Paschim Bardhaman. | Assistant Engineer 2 | Junior Engineer | ORD/000598/2022-2023 | 18 /RCD I | 05/01/2023 | 14/01/2023 | AMAR CONSTRUCTION | 129.3 | 0 | 0 | 100
12 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/B TO ACCOMMODATE FHTC | SM/11576 | Augmentation | Acceptance cum Work Order for Construction of Chlorine Room (Size 4.1 m x 3.5 m out to out) at OHR Site for Augmentation of Ondal Phase-II/B Piped Water Supply Scheme under RCFA Division-I PHE Dte.(Sl No. 34) | Assistant Engineer 2 | Junior Engineer | ORD/000915/2022-2023 | 1177/RCD-1 | 24/03/2023 | 22/06/2023 | SUBHADEEP DAS | 4.61 | 0 | 0 | 100
13 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/B TO ACCOMMODATE FHTC | SM/11576 | Augmentation | Acceptance cum work order forConstruction of Boundary Wall with Gate at OHR Site (Length-160 mtrs) at Ondal Block for Augmentation of Ondal Phase- II/B Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000879/2022-2023 | 1126/ RCD I | 24/03/2023 | 23/04/2023 | AMAR CONSTRUCTION | 13.43 | 0 | 0 | 100
14 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ONDAL PHASE II/B TO ACCOMMODATE FHTC | SM/11576 | Augmentation | Acceptance cum Work Order for Land development with approach road including internal drain at Head Works Site for Augmentation of Ondal Phase II/B Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman (Sl No. 04) | Assistant Engineer 2 | Junior Engineer | ORD/000888/2022-2023 | 1148/RCD-1 | 24/03/2023 | 23/04/2023 | AMAR CONSTRUCTION | 6.5 | 0 | 0 | 100
Total | [13 empty] | 965.99 | 0 | 0