## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Amritnagar Zone-II Piped Water Supply Scheme within RCFA Part-II Area under RCFA Division-I PHE Dte. to accommodate FHTC in Raniganj Block Dist-Paschim Bardhaman | SM/11986 | Augmentation | Detailed Route Survey, Design Drawing & DPR Preparation for Amritnagar Zone-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 05) | Assistant Engineer 2 | Junior Engineer | ORD/000540/2021-2022 | 504/RCD-I | 24/02/2022 | 11/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.23 | 4.23 | 100 | 0
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Amritnagar Zone-II Piped Water Supply Scheme within RCFA Part-II Area under RCFA Division-I PHE Dte. to accommodate FHTC in Raniganj Block Dist-Paschim Bardhaman | SM/11986 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000014/2022-2023 | 2925/RCD-I | 17/11/2022 | 17/11/2022 | Resource Division | 356.25 | 0 | 0 | 0
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Amritnagar Zone-II Piped Water Supply Scheme within RCFA Part-II Area under RCFA Division-I PHE Dte. to accommodate FHTC in Raniganj Block Dist-Paschim Bardhaman | SM/11986 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000022/2022-2023 | 3129 | 09/12/2022 | 09/12/2022 | Resource Division | 60.34 | 0 | 0 | 0
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Amritnagar Zone-II Piped Water Supply Scheme within RCFA Part-II Area under RCFA Division-I PHE Dte. to accommodate FHTC in Raniganj Block Dist-Paschim Bardhaman | SM/11986 | Augmentation | Acceptance cum wor order for Construction of CWR (Clear Water Reservoir) of capacity 200 cum & allied work at Amritnagar under Augmentation of Sub Surface Water Supply Scheme of Amritnagar Zone-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer,Junior Engineer 10,Junior Engineer 12 | ORD/000574/2022-2023 | 3283/RCDI | 20/12/2022 | 20/03/2023 | SOMNATH SAMANTA | 22.04 | 14 | 63.52 | 100
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Amritnagar Zone-II Piped Water Supply Scheme within RCFA Part-II Area under RCFA Division-I PHE Dte. to accommodate FHTC in Raniganj Block Dist-Paschim Bardhaman | SM/11986 | Augmentation | Acceptance cum work order for Additional work for Road crossing of 250 mm dia Rising Main for under Augmentation of Amritnagar Zone-II Piped Water Supply Scheme under Raniganj Block under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer 12 | ORD/000102/2024-2025 | 2122/RCD-I | 27/08/2024 | 26/09/2024 | MD. JAWED KHAN | 8.41 | 8.59 | 102.07 | 100
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Amritnagar Zone-II Piped Water Supply Scheme within RCFA Part-II Area under RCFA Division-I PHE Dte. to accommodate FHTC in Raniganj Block Dist-Paschim Bardhaman | SM/11986 | Augmentation | Acceptance cum Work Order for Construction of Boundary Wall with Gate at OHR Site (Length-80 mtrs) at Amritnagar H/W Site (Damalia village) of Raniganj Block for Augmentation of Amritnagar Zone-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman (Sl No. 03) | Assistant Engineer 2,Assistant Engineer 8 | Junior Engineer,Junior Engineer 12 | ORD/000884/2022-2023 | 1147/RCD-1 | 24/03/2023 | 01/09/2025 | M/S MONDAL CONSTRUCTION | 7.04 | 6.94 | 98.56 | 100
7 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Amritnagar Zone-II Piped Water Supply Scheme within RCFA Part-II Area under RCFA Division-I PHE Dte. to accommodate FHTC in Raniganj Block Dist-Paschim Bardhaman | SM/11986 | Augmentation | Acceptance cum Work Order for Land development with approach road including internal drain at Head Works Site for Augmentation of Amritnagar Zone-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman (Sl No.- 05) | Assistant Engineer 2 | Junior Engineer 10 | ORD/000892/2022-2023 | 1149/RCD-1 | 24/03/2023 | 27/10/2025 | ZEROTH CONTROL SYSTEM | 6.5 | 0 | 0 | 40
8 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Amritnagar Zone-II Piped Water Supply Scheme within RCFA Part-II Area under RCFA Division-I PHE Dte. to accommodate FHTC in Raniganj Block Dist-Paschim Bardhaman | SM/11986 | Augmentation | Acceptance cum Work Order for Special Repair & Renovation of existing High Lift Pump House, Boundary Wall, Guard Room, CWR, Switch Room etc. and allied works at H/W Site of Amritnagar Piped Water Supply Scheme. | Assistant Engineer 2 | Junior Engineer | ORD/000880/2022-2023 | 1145/RCD-1 | 24/03/2023 | 23/04/2023 | RUBY CONSTRUCTION | 9.83 | 9.59 | 97.58 | 0
9 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Amritnagar Zone-II Piped Water Supply Scheme within RCFA Part-II Area under RCFA Division-I PHE Dte. to accommodate FHTC in Raniganj Block Dist-Paschim Bardhaman | SM/11986 | Augmentation | Acceptance cum work order for Balance work of OHR and Construction of new boundary wall, Land developing and Path way and other allied works at Saora mouza, Plot No:2787 at R.C.C over Head Site of Augmentation of Amritnagar Zone-II Piped Water Supply Scheme within RCFA Part-II Area under Raniganj Block under RCFA Division-I, PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000215/2024-2025 | 2550/RCD-I | 29/10/2024 | 01/04/2025 | DAS & CHAKRABORTY | 26.19 | 13.58 | 51.86 | 80
10 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Amritnagar Zone-II Piped Water Supply Scheme within RCFA Part-II Area under RCFA Division-I PHE Dte. to accommodate FHTC in Raniganj Block Dist-Paschim Bardhaman | SM/11986 | Augmentation | Acceptance cum work order of rising main for Amritnagar Zone-II Water Supply Scheme for Ranoganj Block under RCFA Div-I, PHE Dte. | Assistant Engineer 2 | Junior Engineer,Junior Engineer 12 | ORD/000303/2022-2023 | 2513/RCD I | 20/10/2022 | 19/11/2022 | MD. JAWED KHAN | 38.5 | 38.44 | 99.85 | 100
11 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Amritnagar Zone-II Piped Water Supply Scheme within RCFA Part-II Area under RCFA Division-I PHE Dte. to accommodate FHTC in Raniganj Block Dist-Paschim Bardhaman | SM/11986 | Augmentation | Laying of Distribution System to Accommodate FHTC and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN6) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Sub-Surface Water Based Piped Water Supply Scheme for Amritnagar Zone-II under RCFA Division I, PHE Dte.under RCFA Division I, PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000301/2022-2023 | 2455/RCD-I | 13/10/2022 | 01/04/2024 | MACHINO TECHNO | 366.55 | 235.84 | 64.34 | 100
12 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Amritnagar Zone-II Piped Water Supply Scheme within RCFA Part-II Area under RCFA Division-I PHE Dte. to accommodate FHTC in Raniganj Block Dist-Paschim Bardhaman | SM/11986 | Augmentation | Acceptance cum work order for supplying 90 mm dia HDPE pipe line at Murgathol Adibasipara and Old Egera Including repairing different dia pipe line in different places within Amritnagar Distribution Zone under Augmentation of Amritnagar Zone-II Piped Water Supply Scheme under RCFA Division- IPHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000792/2022-2023 | 410/RCD-I | 30/01/2023 | 19/02/2023 | DAS & CHAKRABORTY | 9.23 | 9.18 | 99.5 | 0
13 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Amritnagar Zone-II Piped Water Supply Scheme within RCFA Part-II Area under RCFA Division-I PHE Dte. to accommodate FHTC in Raniganj Block Dist-Paschim Bardhaman | SM/11986 | Augmentation | Acceptance cum work order for Additional work of laying distribution system for Augmentation of Sub-Surface Water Based Piped Water Supply Scheme for Amritnagar Zone-II under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000244/2023-2024 | 2253/RCD-1 | 17/07/2023 | 16/08/2023 | MRITYUNJOY MUKHERJEE & CO. | 62.23 | 62.13 | 99.84 | 100
14 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Amritnagar Zone-II Piped Water Supply Scheme within RCFA Part-II Area under RCFA Division-I PHE Dte. to accommodate FHTC in Raniganj Block Dist-Paschim Bardhaman | SM/11986 | Augmentation | Acceptance cum work order for Balance work of laying distribution system to Augmentation of Sub-Surface Water Based Piped Water Supply Scheme for Amritnagar Zone-II under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000245/2023-2024 | 2255/RCD-1 | 17/07/2023 | 16/08/2023 | MACHINO TECHNO | 28.24 | 28.13 | 99.6 | 100
15 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Amritnagar Zone-II Piped Water Supply Scheme within RCFA Part-II Area under RCFA Division-I PHE Dte. to accommodate FHTC in Raniganj Block Dist-Paschim Bardhaman | SM/11986 | Augmentation | Acceptence cum work order for Additional Work for crossing Nunia River through the riverbed and allied works of Amritnagar Zone-II Water Supply Scheme under RCFA Division-I PHE Dte | Assistant Engineer 2 | Junior Engineer | ORD/000398/2023-2024 | 2580/RCD-I | 07/09/2023 | 22/09/2023 | MD. JAWED KHAN | 7.58 | 7.43 | 97.99 | 100
16 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Amritnagar Zone-II Piped Water Supply Scheme within RCFA Part-II Area under RCFA Division-I PHE Dte. to accommodate FHTC in Raniganj Block Dist-Paschim Bardhaman | SM/11986 | Augmentation | Acceptance cum work order for Balance work of Laying & Pushing of 600 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at Dhunabaid of Dendua for distribution system within command area of Zone-I (Dendua OHR Site) under Augmentation of sub surface water supply scheme for Amritnagar Zone-II under RCFA, Division-1,P.H.E.Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000104/2024-2025 | 2124/RCD-I | 27/08/2024 | 26/09/2024 | DAS & CHAKRABORTY | 12.7 | 0 | 0 | 100
17 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Amritnagar Zone-II Piped Water Supply Scheme within RCFA Part-II Area under RCFA Division-I PHE Dte. to accommodate FHTC in Raniganj Block Dist-Paschim Bardhaman | SM/11986 | Augmentation | Acceptance cum work order for Balance work of Laying & Pushing of 600 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at Pathan Dahwra of Murgasole Mouza under Augmentation of Amritnagar Zone-II Piped Water Supply Scheme under RCFA, Division-1, P.H.E. Dte. | Assistant Engineer 2 | Junior Engineer 12 | ORD/000106/2024-2025 | 2126/RCD-I | 27/08/2024 | 21/09/2024 | DAS & CHAKRABORTY | 7.38 | 5.26 | 71.21 | 100
18 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Amritnagar Zone-II Piped Water Supply Scheme within RCFA Part-II Area under RCFA Division-I PHE Dte. to accommodate FHTC in Raniganj Block Dist-Paschim Bardhaman | SM/11986 | Augmentation | Acceptance cum work order for Additional works of Sinking of 6 (Six) nos. river bed tube wells including collecting main & other allied works at Damalia H/W under RCFA part II at Damodar river under Amritnagar Zone II water supply scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer,Junior Engineer 12 | ORD/000116/2024-2025 | 2136/RCD-I | 27/08/2024 | 31/03/2025 | M/S MONDAL CONSTRUCTION | 12.6 | 0 | 0 | 30
19 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Amritnagar Zone-II Piped Water Supply Scheme within RCFA Part-II Area under RCFA Division-I PHE Dte. to accommodate FHTC in Raniganj Block Dist-Paschim Bardhaman | SM/11986 | Augmentation | Acceptance cum work order for Construction of Boundary Wall with Gate at OHR Site (Length- 120 mtrs) at Nimcha village of Raniganj Block for Augmentation of Amritnagar Zone-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2,Assistant Engineer 8 | Junior Engineer | ORD/000876/2022-2023 | 1125/ RCD I | 24/03/2023 | 01/01/2026 | ZEROTH CONTROL SYSTEM | 10.18 | 0 | 0 | 100
Total | [13 empty] | 1056.04 | 443.34 | 41.98