## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | RETROFITTING OF SEMALYA PWSS FOR PROVIDING FHTC WITHIN JAMURIA BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION I PHE DTE | SM/12024 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000005/2023-2024 | 1854/RCD-I | 31/05/2023 | 31/05/2023 | Resource Division | 7.25 | 0 | 0 | 0
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | RETROFITTING OF SEMALYA PWSS FOR PROVIDING FHTC WITHIN JAMURIA BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION I PHE DTE | SM/12024 | Retrofitting | Formal Work Order for Supplying, laying and aligning of distribution system including FHTC for Shyamla W/S Scheme in Syamla and Bhuri Mouza, Block ¿ Jamuria, Dist ¿ Bardhaman under Shyamla W/S Scheme under RCFA Division-I PHE Dte. (Part ¿ C) | Assistant Engineer 2 | Junior Engineer | ORD/000479/2022-2023 | 2029/RCD-I | 30/08/2022 | 25/06/2025 | SWATI CORPORATION | 337.77 | 234.46 | 69.41 | 85
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | RETROFITTING OF SEMALYA PWSS FOR PROVIDING FHTC WITHIN JAMURIA BLOCK OF PASCHIM BARDHAMAN DISTRICT UNDER RCFA DIVISION I PHE DTE | SM/12024 | Retrofitting | Acceptance cum work order for Construction of 250 cum capacity 20 mtr staging height RCC Over Head Reservoir (pipe connection and cost of pipes, specials at Samlya for Samlya Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Ref Drawing No. PC-I/OHR/10/2012 (Sheet No. 1 & 2) | Assistant Engineer 2 | Junior Engineer | ORD/000459/2022-2023 | 2934/RCD-I | 17/11/2022 | 29/11/2022 | M/S CHANDI CHARAN ROY | 80.02 | 24.01 | 30 | 100
Total | [13 empty] | 425.04 | 258.47 | 60.81