## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-5) UNDER RCFA DIVISION-I PHE DTE. | SM/12025 | Augmentation | Sub Soil Investigation for 450 cum capacity RCC Over Head Reservoir at (Zone-5) of Ondal Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000565/2022-2023 | 3359/RCDI | 23/12/2022 | 30/12/2022 | MOYTEC | 0.49 | 0.49 | 100 | 100
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-5) UNDER RCFA DIVISION-I PHE DTE. | SM/12025 | Augmentation | Formal work order for distribution network including FHTC & allied work at Ondal Block of RCFA Part-II(zone -5) pipe water supply under RCFA Div-I, PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000811/2022-2023 | 954/RCDI | 20/03/2023 | 01/10/2025 | M/S PIONEER CONSTRUCTION | 475.88 | 209.15 | 43.95 | 80
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-5) UNDER RCFA DIVISION-I PHE DTE. | SM/12025 | Augmentation | Formal work order for Supplying laying different HDPE Pipe line for Improvement of RCFA Part-I Water Supply Scheme within Command area of Zone-VIII with LDS work under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000031/2023-2024 | 1614/RCD I | 25/04/2023 | 24/07/2023 | SWATI CORPORATION | 128.33 | 22.19 | 17.29 | 80
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-5) UNDER RCFA DIVISION-I PHE DTE. | SM/12025 | Augmentation | Formal work order for Construction of 450 cum capacity 20 mtrs staging height RCC Over Reservoir (Pipe connection and cost of pipes, specials at Ondal Block (Zone-5) for Augmentation of RCFA Part-II Piped Water Supply Scheme including Soil Investigation and chlorine Room (4.50 x 3.50 m) under RCFA Division-I PHE Dte. In District Paschim Bardhaman. | Assistant Engineer 2 | Junior Engineer | ORD/000042/2023-2024 | 1608/RCD I | 25/04/2023 | 25/04/2024 | HIRANMAY GHOSH | 137.5 | 137.5 | 100 | 50
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-5) UNDER RCFA DIVISION-I PHE DTE. | SM/12025 | Augmentation | Acceptance cum work order for Laying 450 mm dia MS water pipe line with 700 mm dia MS casing pipe for Railway crossing in Salanpur at KM SLS/1136 and SLS/1138 on Bemjomary siding Railway line in Asansol Division under JJM under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000422/2023-2024 | 2620/RCD-I | 13/09/2023 | 28/09/2023 | MD AAMIR KHAN | 38.07 | 32.09 | 84.29 | 100
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-5) UNDER RCFA DIVISION-I PHE DTE. | SM/12025 | Augmentation | Acceptance cum work order for Allied work for bridge with foundation at Chalbalpur under Amritnagar Zone-II for Augmentation of RCFA Part-II (Zone-5) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000513/2023-2024 | 2864/RCD-I | 06/10/2023 | 04/01/2024 | MRITYUNJOY MUKHERJEE & CO. | 87.54 | 87.26 | 99.68 | 100
7 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-5) UNDER RCFA DIVISION-I PHE DTE. | SM/12025 | Augmentation | Acceptance cum work order for Construction of new boundary wall, Land developing and Pathway and other allied works at Nimsa mouza RCC over Head Site at Shyamla under Augmentation of RCFA Part-II (Zone-5) under RCFA Division-I PHE Dte. (Length 188 Mtr) | Assistant Engineer 2 | Junior Engineer | ORD/000519/2023-2024 | 2873/RCD-I | 06/10/2023 | 04/01/2024 | M/S CHANDI CHARAN ROY | 21.97 | 13.21 | 60.12 | 100
8 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-5) UNDER RCFA DIVISION-I PHE DTE. | SM/12025 | Augmentation | Acceptance cum work order for Laying and pushing MS pipe through RCC pipe in different dia and different including cutting welding for barricading jointing for Augmentation of RCFA Part-II (Zone-5) PWSS under Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer 3 | Junior Engineer | ORD/000523/2023-2024 | 2881/RCD-I | 06/10/2023 | 01/04/2024 | MRITYUNJOY MUKHERJEE & CO. | 16.98 | 0 | 0 | 100
9 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-5) UNDER RCFA DIVISION-I PHE DTE. | SM/12025 | Augmentation | Acceptance cum work order for Additional Supplying. Aligning and laying MS pipe (Node no. 45-47, 61-62, 5-16, 44-45) construction of Guard wall, concrete dismantling with re concreting and other allied works for Shyamla & Bhuri Mouzas, Block-Jamuria, Dist-Paschim Bardhaman under Augmentation of RCFA Part-II (Zone-5) under RCFA Division-I PHE Dte. (Part-C) | Assistant Engineer 2 | Junior Engineer | ORD/000524/2023-2024 | 2882/RCD-I | 06/10/2023 | 05/11/2023 | TARA CONSTRUCTION | 13.8 | 10.84 | 78.54 | 100
10 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-5) UNDER RCFA DIVISION-I PHE DTE. | SM/12025 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000019/2023-2024 | 2954/RCD-I | 11/10/2023 | 11/10/2023 | Resource Division | 6.78 | 0 | 0 | 0
Total | [13 empty] | 927.34 | 512.74 | 55.29