## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-6) UNDER RCFA DIVISION-I PHE DTE. | SM/12026 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000020/2023-2024 | 2952/RCD-I | 11/10/2023 | 11/10/2023 | Resource Division | 6.78 | 0 | 0 | 0
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-6) UNDER RCFA DIVISION-I PHE DTE. | SM/12026 | Augmentation | Acceptance cum work order for Supply fitting and allining of 250 mm dia non return valve and 80 mm dia air valve and etc allied works at Bilpahari OCP area on distribution main under Kendra Khottamdihi water supply scheme under RCFA Div-I, PHE Dte. |  | Junior Engineer | ORD/000797/2023-2024 | 2896_RCD-I | 06/10/2023 | 05/11/2023 | M/S UNIT CONSTRUCTION | 2.42 | 0 | 0 | 0
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-6) UNDER RCFA DIVISION-I PHE DTE. | SM/12026 | Augmentation | Acceptance cum work order for Laying & pushing of 600 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at Srirampur Workshop road near Railway Workshop under Ondal Block under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000791/2023-2024 | 3437_RCD_I | 24/11/2023 | 09/12/2023 | M/S UNIT CONSTRUCTION | 9.31 | 0 | 0 | 0
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-6) UNDER RCFA DIVISION-I PHE DTE. | SM/12026 | Augmentation | Acceptance cum work order for Laying and Pushing by adopting trench less technology(e.g.Jack Pushing Method etc) at Kunustoria for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I.PHE Dte.(Zone-7) Segment-5 | Assistant Engineer 2 | Junior Engineer | ORD/001165/2023-2024 | 1017/RCD-I | 16/03/2024 | 31/03/2024 | B.T.M. CONCERN | 22.8 | 21.52 | 94.41 | 100
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-6) UNDER RCFA DIVISION-I PHE DTE. | SM/12026 | Augmentation | Continuation work order for Probable Office expenditure of office of the Executive Engineer to meet up day to day various office & site expenses under RCFA div-I PHE Dte (w.e.f 01.08.2023 to 31.01.2024) | Assistant Engineer 2 | Junior Engineer | ORD/001166/2023-2024 | 2319_RCD-I | 31/07/2023 | 31/01/2024 | M/S KALYANI ENTERPRISE | 4.49 | 0 | 0 | 0
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-6) UNDER RCFA DIVISION-I PHE DTE. | SM/12026 | Augmentation | Acceptance cum work order for Laying & Pushing of 600 mm dia RCC (NP3) Hume pipe by adopting trench less technology at 4 nos location (Dabor more, Achhra Road, Rupnarayanpur Phari, Rupnarayanpur Chittaranjan Road) of Salanpur Block under Improvement of RCFA Part-I (Zone-7, Part-F) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000289/2023-2024 | 2338/RCD-I | 01/08/2023 | 16/08/2023 | GITA CONSTRUCTION | 67.97 | 63.53 | 93.46 | 100
7 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-6) UNDER RCFA DIVISION-I PHE DTE. | SM/12026 | Augmentation | Acceptance cum work order for Construction of Guard room with toilet at Dendua under Salanpur Block for Improvement of RCFA Part-I Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000598/2023-2024 | 3280/RCD-I | 08/11/2023 | 06/02/2024 | D.S.ENTERPRISE | 7.61 | 7.29 | 95.73 | 100
8 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-6) UNDER RCFA DIVISION-I PHE DTE. | SM/12026 | Augmentation | Acceptance cum work order for Allied work Balance Work of Road restoration in connection with Distribution Network including FHTC and allied work at Ondal Block of RCFA Part-II (Zone-6) Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000946/2023-2024 | 454/RCD-1 | 12/02/2024 | 28/03/2024 | MRITYUNJOY MUKHERJEE & CO. | 45.34 | 43.8 | 96.6 | 50
9 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-6) UNDER RCFA DIVISION-I PHE DTE. | SM/12026 | Augmentation | Formal work order for Distribution Network Including FHTC & allied work at Ondal Block of RCFA Part-II (Zone-6) Piped Water Supply Scheme Under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer 3 | Junior Engineer | ORD/000066/2023-2024 | 1763/RCD I | 16/05/2023 | 02/01/2026 | MACHINO TECHNO | 541.2 | 167.23 | 30.9 | 30
10 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-6) UNDER RCFA DIVISION-I PHE DTE. | SM/12026 | Augmentation | Acceptance cum work order for Crossing 600 mm dia MS Pipes under the Railway track by jack pushing technology at different spots and pushing different dia MS Pipes through 600 mm dia MS pipes in connection with the work of estimates for the laying distribution system for Amritnagar Zone-II under Augmentation of RCFA Part-II (Zone- under RCFA Division-I PHE Dte. (Part-B). | Assistant Engineer 2 | Junior Engineer | ORD/000516/2023-2024 | 2867/RCD-I | 06/10/2023 | 21/10/2023 | MACHINO TECHNO | 41.98 | 38.27 | 91.16 | 100
11 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-6) UNDER RCFA DIVISION-I PHE DTE. | SM/12026 | Augmentation | Formal work order for construction of 600 cum capacity 20 mtrs staging height RCC Over Reservoir (Pipe connection and cost of pipes, specials at Ondal Block (Zone-6) for Augmentation of RCFA Part_II Piped Water Supply Scheme including Soil investigation and Chlorine Room (4.50 X 3.50 m) under RCFA Division-I PHE Dte. In District Paschim Bardhaman.(2nd Call). | Assistant Engineer 2 | Junior Engineer | ORD/001016/2023-2024 | 558/RCD-I | 21/02/2024 | 21/02/2025 | MRITYUNJOY MUKHERJEE & CO. | 151 | 75.5 | 50 | 42
12 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-6) UNDER RCFA DIVISION-I PHE DTE. | SM/12026 | Augmentation | Acceptance cum Work Order for Additional work for laying distribution pipe line of providing FHTC at Harispur Taldanga under Madanpur Gram Panchayat of Andal Block of JJM work AUGMENTATION PWSS OF RCFA PART-II (ZONE-6) under RCFA Division-I.PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001169/2023-2024 | 1008/RCD-I | 16/03/2024 | 31/03/2024 | M/S MONDAL ENTERPRISE | 5.56 | 5.55 | 99.8 | 100
13 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-6) UNDER RCFA DIVISION-I PHE DTE. | SM/12026 | Augmentation | Acceptance cum work order for Additional emergency work road restoration, laying of PVC pipe and other allied work for balance part at different location of Ramnagar and adjoining area within Pandabeswar Block for Augmentation PWSS of RCFA Part-II (Zone-6) under RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer | ORD/000705/2025-2026 | 2632/RCD-I | 08/09/2025 | 03/10/2025 | M/S MONDAL ENTERPRISE | 10.1 | 0 | 0 | 90
Total | [13 empty] | 916.57 | 422.7 | 46.12