## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-7) UNDER RCFA DIVISION-I PHE DTE. | SM/12027 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000021/2023-2024 | 2950/RCD-I | 11/10/2023 | 11/10/2023 | Resource Division | 6.78 | 0 | 0 | 0
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-7) UNDER RCFA DIVISION-I PHE DTE. | SM/12027 | Augmentation | Acceptance cum work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-7) Segment-2 | Assistant Engineer 2 | Junior Engineer | ORD/000853/2022-2023 | 1100/RCD I | 23/03/2023 | 21/06/2023 | RELIABLE ENGINEERS CO-OP CONSTRUCTION SOCIETY LTD. | 89.86 | 0 | 0 | 50
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-7) UNDER RCFA DIVISION-I PHE DTE. | SM/12027 | Augmentation | Acceptance cum work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-7) Segment-4 | Assistant Engineer 2 | Junior Engineer | ORD/000858/2022-2023 | 1104/RCD I | 23/03/2023 | 21/06/2023 | M/S MONI TRADERS | 93.11 | 0 | 0 | 45
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-7) UNDER RCFA DIVISION-I PHE DTE. | SM/12027 | Augmentation | Acceptance cum work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-7) Segment-1 | Assistant Engineer 2 | Junior Engineer | ORD/000850/2022-2023 | 1098/ RCD-I | 23/03/2023 | 21/06/2023 | MAK CONSTRUCTION CO. | 97.63 | 0 | 0 | 15
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-7) UNDER RCFA DIVISION-I PHE DTE. | SM/12027 | Augmentation | Additional extra cutting Laterrate / sandstone of distribution network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-VII under RCFA Div-I PHE Dte. (Part-E) | Assistant Engineer 2 | Junior Engineer | ORD/000573/2023-2024 | 2694/RCD-I | 27/09/2023 | 12/10/2023 | TARA CONSTRUCTION | 0.94 | 0 | 0 | 100
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-7) UNDER RCFA DIVISION-I PHE DTE. | SM/12027 | Augmentation | Acceptance cum work order for Additional supplying, Laying & Aligning of HDPE pipe, including providing FHTC retrofitting (left out portion) at Ratibati village under Augmentation PWSS of RCFA Part-II (Zone-7) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001023/2023-2024 | 622/RCD-I | 27/02/2024 | 13/03/2024 | M/S KALYAN ENTERPRISE | 4.09 | 0 | 0 | 100
7 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-7) UNDER RCFA DIVISION-I PHE DTE. | SM/12027 | Augmentation | Way leave permission of 250 mm dia waer pipeline (Jal Jeevan Mision) near LC Gate No. 9/Spl/T near Pandabeswar Station in Asansol Divison of Eastern Railway by RCFA Division-I PHE Dte |  |  | BILL/00987/2024-2025 | 415/24-25 | 05/12/2024 | 05/12/2024 | EASTERN RAILWAY | 68.95 | 0 | 0 | 0
8 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-7) UNDER RCFA DIVISION-I PHE DTE. | SM/12027 | Augmentation | Acceptance cum work order for distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-7) Segment-5 | Assistant Engineer 2 | Junior Engineer | ORD/000863/2022-2023 | 1106/RCD I | 23/03/2023 | 21/06/2023 | B.T.M CONCERN | 94.6 | 0 | 0 | 65
9 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-7) UNDER RCFA DIVISION-I PHE DTE. | SM/12027 | Augmentation | Acceptance cum work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-7) Segment-3 (Sl No. 03) | Assistant Engineer 2 | Junior Engineer | ORD/000856/2022-2023 | 1102/RCD I | 23/03/2023 | 21/06/2023 | RUBY CONSTRUCTION | 94.47 | 0 | 0 | 70
10 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-7) UNDER RCFA DIVISION-I PHE DTE. | SM/12027 | Augmentation | Formal work order for Augmentation of RCFA part-II Piped Water Supply Scheme (Zone-7) with Construction of 450 cum capacity RCC OHR with 20 mtr with staging height including Boundary Walls with gates and land Development, Drain and internal pathway at OHR site under Jamuria Block, District Paschim Bardhaman. | Assistant Engineer 2 | Junior Engineer | ORD/000155/2023-2024 | 1900/RCD-I | 09/06/2023 | 08/06/2024 | TARAPRASAD SARKAR | 150.41 | 0 | 0 | 25
11 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-7) UNDER RCFA DIVISION-I PHE DTE. | SM/12027 | Augmentation | Sub Soil Investigation for 450 cum capacity RCC Over Head Reservoir at (Zone-7) of Jamuria Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000560/2022-2023 | 3354/RCDI | 23/12/2022 | 12/02/2025 | MOYTEC | 0.49 | 0 | 0 | 100
12 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-7) UNDER RCFA DIVISION-I PHE DTE. | SM/12027 | Augmentation | Acceptance Cum work order for Additional work for distribution network for Improvement of RCFA Part-II Water Supply Scheme within command area of Zone-VII under RCFA Division-I PHE Dte. (Part-B) | Assistant Engineer 2 | Junior Engineer | ORD/000675/2022-2023 | 358/RCD I | 30/01/2023 | 01/01/2024 | UNITED CONSTRUCTION | 62.01 | 0 | 0 | 100
13 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-7) UNDER RCFA DIVISION-I PHE DTE. | SM/12027 | Augmentation | Formal work order for Supplying aligning and laying of different dia HDPE pipe line instead of DI pipe line and extension of HDPE pipe to adjacent village of Dendua for distribution system within command area of Zone-I (Dendua OHR Site) of Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000030/2023-2024 | 1615/RCD I | 25/04/2023 | 24/07/2023 | DAS & CHAKRABORTY | 115.96 | 0 | 0 | 100
Total | [13 empty] | 879.29 | 0 | 0