## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-8) UNDER RCFA DIVISION-I PHE DTE. | SM/12028 | Augmentation | Sub Soil Investigation for 250 cum capacity RCC Over Head Reservoir at (Zone-8) of Jamuria Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000561/2022-2023 | 3355/RCDI | 23/12/2022 | 07/02/2025 | MOYTEC | 0.49 | 0.49 | 100 | 100
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-8) UNDER RCFA DIVISION-I PHE DTE. | SM/12028 | Augmentation | Acceptance cum work order for Augmentation of RCFA Part-II Piped Water Supply Scheme (Zone-8) with Construction of 250 cum capacity RCC OHR with 20 mtr with staging height including Boundary Walls with gates and land Development, Drain and internal pathway at OHR site under Jamuria Block, District Paschim Bardhaman, (Sl No. 07). | Assistant Engineer 2 | Junior Engineer | ORD/000005/2023-2024 | 1402 RCD I | 12/04/2023 | 11/04/2024 | PINKI ENTERPRISE | 95.85 | 86.37 | 90.1 | 65
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-8) UNDER RCFA DIVISION-I PHE DTE. | SM/12028 | Augmentation | Acceptance cum work order Laying & Pushing of 600 mm dia RCC (NP3) Hume Pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at 04 nos location (Bus stand/Taxi stand Domohani Bazar, Rural more, Near Domohani Electric Supply Office, BDO Office More) of Barabani Block under Improvement of RCFA Part-I (Zone-11, Part-6) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000231/2023-2024 | 2229/RCD-I | 17/07/2023 | 16/08/2023 | UMA ENTERPRISE | 30.82 | 0 | 0 | 0
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-8) UNDER RCFA DIVISION-I PHE DTE. | SM/12028 | Augmentation | Acceptance cum work order Additional work for the laying of Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-XI (Part-1 Distribution Segment) under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000296/2023-2024 | 2367/RCD-I | 04/08/2023 | 03/09/2023 | R B ENTERPRISE | 47.39 | 40.66 | 85.79 | 86
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-8) UNDER RCFA DIVISION-I PHE DTE. | SM/12028 | Augmentation | Acceptance cum work order for Additional Supplying E.R.M.S Black pipe of approved quality including carring, stacking at works site and other allied works for Improvement RCFA Part-I Water Supply Scheme within command area of Zone VIII under RCFA Div-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000723/2023-2024 | 3612/RCD-1 | 20/12/2023 | 04/01/2024 | SWATI CORPORATION | 2.78 | 0 | 0 | 0
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-8) UNDER RCFA DIVISION-I PHE DTE. | SM/12028 | Augmentation | Acceptance cum work order for Construction of Pump Houses (Size 14 mtr x 10 mtr x 8 mtr) under at Madanpur H/W Site under AUGMENTATION PWSS OF RCFA PART-II (ZONE-8) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000724/2023-2024 | 3611/RCD-1 | 20/12/2023 | 09/07/2025 | D.S.C. CONCERN | 35.91 | 16.6 | 46.22 | 50
7 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-8) UNDER RCFA DIVISION-I PHE DTE. | SM/12028 | Augmentation | Acceptance cum work order for Supplying E.R.M.S Black pipe of approved quality including carring, stacking at works site and other allied works for crossing of 07 nos (Node Point :139-140,153-3,42-43,86-87,60-61, and 38-40 culvert/canal of by the side of PWD road under Improvement RCFA Part-I water Supply scheme within command area of Zone VIII under RCFA Div-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000720/2023-2024 | 3614/RCD-I | 20/12/2023 | 04/01/2024 | TARA CONSTRUCTION | 3.32 | 0 | 0 | 0
8 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-8) UNDER RCFA DIVISION-I PHE DTE. | SM/12028 | Augmentation | Acceptance cum work order for Additional extra cutting Laterate/sandstone of distribution of pipe line at Augmentation of RCFA Part-II (Zione-8) within command area under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000522/2023-2024 | 2880/RCD-I | 06/10/2023 | 04/01/2024 | SWATI CORPORATION | 10.6 | 10.6 | 100 | 100
9 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-8) UNDER RCFA DIVISION-I PHE DTE. | SM/12028 | Augmentation | Acceptence cum work order for Additional (Extra line Node no. 550-550A, 555-548, 554-547, 527-321, 378-296, 397-423, 423-441) supplying, aligning & laying HDPE pipe line of RCFA Part-I Water Supply Scheme within command area of Zone-VII (Part-E) under RCFA Division-I PHE Dte | Assistant Engineer 2 | Junior Engineer | ORD/000406/2023-2024 | 2588/RCD-I | 07/09/2023 | 22/09/2023 | TARA CONSTRUCTION | 7.55 | 7.46 | 98.8 | 100
10 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-8) UNDER RCFA DIVISION-I PHE DTE. | SM/12028 | Augmentation | Acceptance cum work order for Construction of MS pipe carrier bridge, additional (Extra line) supplying, aligning & laying HDPE pipe line and other works of RCFA Part-I Water Supply Scheme within command area of Zone-VIII under RCFA Div-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000297/2023-2024 | 2368/RCD-I | 04/08/2023 | 03/10/2023 | SWATI CORPORATION | 28.11 | 26.64 | 94.76 | 100
11 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-8) UNDER RCFA DIVISION-I PHE DTE. | SM/12028 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000022/2023-2024 | 2948/RCD-I | 11/10/2023 | 11/10/2023 | Resource Division | 6.78 | 0 | 0 | 0
12 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-8) UNDER RCFA DIVISION-I PHE DTE. | SM/12028 | Augmentation | Acceptance cum Work Order for Balance work for laying of different dia HDPE pipe line (left out portion) and other allied works at Amritnagar (Part-A) under Augmentation of Amritnagar Zone-I under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000955/2023-2024 | 2455/RCD-I | 12/02/2024 | 28/03/2024 | M/S SINGH & KONAR CONSTRUCTION | 45.53 | 0 | 0 | 0
13 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-8) UNDER RCFA DIVISION-I PHE DTE. | SM/12028 | Augmentation | Formal work order for Laying distribution system including FHTC for 5 (Two) nos uncovered village viz. Namokeshia and Jorbari within Salanpur Block under Augmentation of RCFA Part-II (zone-10) PWSS under RCFA Division-I PHE Dte. |  | Junior Engineer | ORD/001074/2023-2024 | 806/RCD-I | 13/03/2024 | 11/06/2024 | UMA ENTERPRISE | 107.86 | 0 | 0 | 0
14 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-8) UNDER RCFA DIVISION-I PHE DTE. | SM/12028 | Augmentation | Acceptance cum work order for Supply & Delivery of GI pipe including loading , unloading and carriage to Searsole store under RCFA Part-II PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/001022/2023-2024 | 626/RCD-I | 27/02/2024 | 18/03/2024 | MAKALI ENGINEERING CORPORATION | 93.69 | 93.69 | 100 | 100
15 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-8) UNDER RCFA DIVISION-I PHE DTE. | SM/12028 | Augmentation | Acceptance cum Work Order for Emergent dismantling of RCC Elevated Reservoir capacity 682 cum staging height 20 meter at Mohishila OHR within Asansol Municipal Corporation area of Augmentation PWSS of RCFA Part-II (Zone-8) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001018/2023-2024 | 519/RCD-I | 16/02/2024 | 01/04/2024 | GITA CONSTRUCTION | 17.37 | 17.35 | 99.88 | 100
16 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-8) UNDER RCFA DIVISION-I PHE DTE. | SM/12028 | Augmentation | Way leave permission for water supply poipe line for JJM carrier pipe dia 250 mm at Pandabeswar under Augmentation of RCFA PART-II (ZONE-8) under RCFA Div-I PHE Dte. |  |  | BILL/00864/2024-2025 | 398/24-25 | 29/10/2024 | 29/10/2024 | EASTERN RAILWAY | 1.19 | 0 | 0 | 0
Total | [13 empty] | 535.23 | 299.85 | 56.02