## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-10) UNDER RCFA DIVISION-I PHE DTE. | SM/12029 | Augmentation | Sub Soil investigation for 350 cum capacity RCC Over Head Reservoir at (zone-IX) of Barabani Block for Improvement of RCFA Part-I Piped water Supply Scheme under RCFA Division-I PHE Dte. In the District Paschim Bardhaman. | Assistant Engineer 2 | Junior Engineer | ORD/000580/2023-2024 | 2695/RCD-I | 27/09/2023 | 04/10/2023 | MALLICK ENTERPRISE | 0.98 | 0 | 0 | 0
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-10) UNDER RCFA DIVISION-I PHE DTE. | SM/12029 | Augmentation | Sub Soil Investigation for 450 cum capacity RCC Over Head Reservoir at (Zone-XIII) of Barabani Block for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. In the District of Paschim Bardhaman. | Assistant Engineer 2 | Junior Engineer | ORD/000582/2023-2024 | 2696/RCD-I | 27/09/2023 | 04/10/2023 | JOY HIND TUBEWELLS | 0.98 | 0 | 0 | 0
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-10) UNDER RCFA DIVISION-I PHE DTE. | SM/12029 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000026/2023-2024 | 2955/RCD-I | 11/10/2023 | 11/10/2023 | Resource Division | 6.78 | 0 | 0 | 0
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-10) UNDER RCFA DIVISION-I PHE DTE. | SM/12029 | Augmentation | Acceptance cum work order for Health assessment of existing OHR of Chora (1135Cum) and ancillary structures conducting Non-Destructive Test and thorough visual observation under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000540/2023-2024 | 3025/RCD-1 | 16/10/2023 | 31/10/2023 | RISHAN ENGINEERING CONSULTANCY | 4.97 | 4.97 | 100 | 100
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-10) UNDER RCFA DIVISION-I PHE DTE. | SM/12029 | Augmentation | Acceptance cum work order for Health assessment of existing OHR of Rupnarayanpur (1182 Cum) and ancillary structures conducting Non-Destructive Test and thorough visual observation under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000534/2023-2024 | 3015/RCD-I | 16/10/2023 | 31/10/2023 | SIRCON ENGINEERING SERVICES | 4.98 | 4.98 | 100 | 100
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-10) UNDER RCFA DIVISION-I PHE DTE. | SM/12029 | Augmentation | Acceptance cum work order for Health assessment of existing OHR of DP Colony (450 Cum) and ancillary structures conducting Non-Destructive Test and thorough visual observation under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000533/2023-2024 | 3022/RCD-1 | 16/10/2023 | 31/10/2023 | SIRCON ENGINEERING SERVICES | 4.93 | 4.93 | 100 | 100
7 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-10) UNDER RCFA DIVISION-I PHE DTE. | SM/12029 | Augmentation | Acceptance cum work order for Repairing and restoration of concrete road due to FHTC work at Jitpur Uttarrampur and surrounding villages within Jitpur Uttarrampur Gram Panchayat under Improvement of RCFA Part-I water Supply scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000654/2023-2024 | 3451/RCD-I | 24/11/2023 | 09/12/2023 | DIP ENTERPRISE | 4.49 | 4.38 | 97.48 | 100
8 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-10) UNDER RCFA DIVISION-I PHE DTE. | SM/12029 | Augmentation | Acceptance cum work order for Additional work for laying and distribution system for Improvement of RCFA Part-I Water Supply Scheme under Command area of Zone-VII under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000683/2023-2024 | 3472/RCD-I | 28/11/2023 | 28/12/2023 | GITA CONSTRUCTION | 95.09 | 70.58 | 74.23 | 100
9 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-10) UNDER RCFA DIVISION-I PHE DTE. | SM/12029 | Augmentation | Acceptance cum work order for Laying of different dia HDPE pipe line (left out portion) including adopting trench less technologies and other allied works at Moul Danga village under Barabani Block of Improvement of RCFA Part-I PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000685/2023-2024 | 3284/RCD-1 | 08/11/2023 | 08/12/2023 | SRI KRISHNA ENTERPRISE | 19.21 | 16.46 | 85.68 | 100
10 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-10) UNDER RCFA DIVISION-I PHE DTE. | SM/12029 | Augmentation | Acceptance cum work order for Construction of Guard Wall arrangement to project 450 mm dia the Rising Main at Bidyanandapur of ASTA Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000612/2023-2024 | 3377/RCD-I | 21/11/2023 | 06/12/2023 | SIMA ENTERPRISE | 4.03 | 2.23 | 55.31 | 100
11 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-10) UNDER RCFA DIVISION-I PHE DTE. | SM/12029 | Augmentation | Acceptance cum work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme within command area of Zone-10 (Segment-I) under RCFA Division-I PHE Dte | Assistant Engineer 2 | Junior Engineer | ORD/000860/2022-2023 | 1115/ RCD I | 23/03/2023 | 21/06/2023 | M/S B.K. CONSTRUCTION | 86.29 | 32 | 37.09 | 38
12 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-10) UNDER RCFA DIVISION-I PHE DTE. | SM/12029 | Augmentation | Acceptance cum work order Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme within command area of Zone-10 (Segment-VI) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000866/2022-2023 | 1108/RCD-I | 23/03/2023 | 21/06/2023 | VISUVIOUS | 54.47 | 47.84 | 87.83 | 90
13 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-10) UNDER RCFA DIVISION-I PHE DTE. | SM/12029 | Augmentation | Acceptance cum Work Order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme within command area of Zone-10 (Segment-V) under RCFA Division-I PHE Dte. (Sl No. 07) | Assistant Engineer 2 | Junior Engineer | ORD/000867/2022-2023 | 1110/RCD-I | 23/03/2023 | 21/06/2023 | DIP CONSTRUCTION | 90.17 | 31.53 | 34.97 | 35
14 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-10) UNDER RCFA DIVISION-I PHE DTE. | SM/12029 | Augmentation | Acceptance cum work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme within command area of Zone-10 (Segment-III) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000851/2022-2023 | 1112/ RCD I | 23/03/2023 | 21/06/2023 | UNITED CONSTRUCTION | 86.38 | 65.24 | 75.53 | 75
15 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-10) UNDER RCFA DIVISION-I PHE DTE. | SM/12029 | Augmentation | Acceptance cum work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme within command area of Zone-10 (Segment-II) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000855/2022-2023 | 1113/ RCD I | 23/03/2023 | 09/06/2026 | M/S KONAR CONSTRUCTION | 84.65 | 11.07 | 13.08 | 50
16 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-10) UNDER RCFA DIVISION-I PHE DTE. | SM/12029 | Augmentation | Acceptance cum work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme within command area of Zone-10 (Segment-IV) under RCFA Division-I PHE Division-I PHE Dte. (Sl No. 08). | Assistant Engineer 2 | Junior Engineer | ORD/000053/2023-2024 | 1706/ RCD I | 03/05/2023 | 01/08/2023 | DURGADAS MONDAL | 85.16 | 45.25 | 53.13 | 55
17 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-10) UNDER RCFA DIVISION-I PHE DTE. | SM/12029 | Augmentation | Formal work order for Augmentation of RCFA Part-II Piped Water Supply Scheme (Zone-10) with Construction of 350 cum capacity RCC OHR with 20 mtr with staging height including Boundary Walls with gates and land Development, Drain and internal pathway at OHR site under Jamuria Block, District-Paschim Bardhaman. | Assistant Engineer 2 | Junior Engineer | ORD/000099/2023-2024 | 1845/RCD-I | 31/05/2023 | 30/05/2024 | RUBY CONSTRUCTION | 126.43 | 42.18 | 33.36 | 20
18 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-10) UNDER RCFA DIVISION-I PHE DTE. | SM/12029 | Augmentation | Sub Soil Investigation for 350 cum capacity RCC Over Head Reservoir at (Zone-10) of Jamuria Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000562/2022-2023 | 3356/RCDI | 23/12/2022 | 12/02/2025 | MOYTEC | 0.49 | 0 | 0 | 100
Total | [13 empty] | 760.48 | 383.65 | 50.45