## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-12B) UNDER RCFA DIVISION-I PHE DTE. | SM/12031 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000029/2023-2024 | 2945/RCD-I | 11/10/2023 | 11/10/2023 | Resource Division | 6.78 | 0 | 0 | 0
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-12B) UNDER RCFA DIVISION-I PHE DTE. | SM/12031 | Augmentation | Acceptance cum work order for Allied work of Distribution Network including FHTC & allied work at Ondal Block of RCFA Part-II (Zone-12 A) Piped Water Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000669/2023-2024 | 3436/RCD-1 | 24/11/2023 | 23/01/2024 | MRITYUNJOY MUKHERJEE & CO. | 81.28 | 48.77 | 60 | 65
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-12B) UNDER RCFA DIVISION-I PHE DTE. | SM/12031 | Augmentation | Acceptance cum work order for Health assessment of existing OHR of Barabani (910 Cum) and ancillary structures conducting Non-Destructive Test and thorough visual observation under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000539/2023-2024 | 3018/RCD-I | 16/10/2023 | 31/10/2023 | SIRCON ENGINEERING SERVICES | 4.95 | 4.95 | 100 | 100
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-12B) UNDER RCFA DIVISION-I PHE DTE. | SM/12031 | Augmentation | 100 mm dia water pipe line with 600 mm dia MS Casing pipe line (Jal Jeevan Mission) by R.C.F.A Division-1, PHE DTE, Asansol in between Parasia Siding ¿ New Jambad Siding at Km. CB-2/15-16 in Asansol Division of Eastern Railway under AUGMENTATION PWSS OF RCFA PART-II (ZONE-12B) UNDER RCFA DIVISION-I PHE DTE. |  |  | BILL/00863/2024-2025 | 396/24-25 | 28/10/2024 | 28/10/2024 | EASTERN RAILWAY | 4.58 | 0 | 0 | 0
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-12B) UNDER RCFA DIVISION-I PHE DTE. | SM/12031 | Augmentation | Formal Work Order for Distribution network for RCFA Part-II piped Water Supply Scheme including FHTC & allied work under RCFA Div-I, PHE Dte.(Zone-12B)(Segment-2). | Assistant Engineer 2 | Junior Engineer | ORD/000631/2022-2023 | 485/RCDI | 03/02/2023 | 04/04/2023 | M/S SINGH & KONAR CONSTRUCTION | 155.21 | 92 | 59.27 | 80
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-12B) UNDER RCFA DIVISION-I PHE DTE. | SM/12031 | Augmentation | Acceptance cum work order for Construction of CWR (Clear Water Reservoir) of capacity 200 cum & allied work at Shankarpur under Pandabeswar H/W Site within Pandabeswar Block for Augmentation of PWSS of RCFA Part-II (Zone-12B) under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000558/2024-2025 | 162/RCD-I | 08/01/2025 | 08/04/2025 | DIP CONSTRUCTION | 34.75 | 0 | 0 | 0
7 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-12B) UNDER RCFA DIVISION-I PHE DTE. | SM/12031 | Augmentation | Acceptance cum Work Order for Additional work of allied items at Andal OHR Site under Phase-II/B under RCFA Division-I PHE Dte. AUGMENTATION PWSS OF RCFA PART-II (Zone-12B) | Assistant Engineer 2 | Junior Engineer | ORD/000063/2024-2025 | 1647/RCD-I | 04/07/2024 | 19/07/2024 | AMAR CONSTRUCTION | 5.25 | 5.25 | 99.98 | 100
8 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-12B) UNDER RCFA DIVISION-I PHE DTE. | SM/12031 | Augmentation | Acceptance cum work order for Allied works of laying distribution system of balance work of supply & laying of HDPE pipe under Augmentation of sub-surface water based PWSS for Amritnagar Zone-II under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000942/2023-2024 | 498/RCD-I | 12/02/2024 | 28/03/2024 | MACHINO TECHNO | 78.67 | 76.89 | 97.74 | 100
9 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-12B) UNDER RCFA DIVISION-I PHE DTE. | SM/12031 | Augmentation | Acceptance cum work order for Allied work Balance work of Road restoration in connection with laying distribution system to Accommodate FHTC and providing FHTC including supplying laying fittings fixing of 15 mm NB PVC pipe with all necessary work specials saddle piece etc. all complete for Augmentation of sub-surface water based PWSS for Amritnagar Zone-II under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000941/2023-2024 | 500/RCD-I | 12/02/2024 | 28/03/2024 | MRITYUNJOY MUKHERJEE & CO. | 54.54 | 54.54 | 100 | 100
10 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-12B) UNDER RCFA DIVISION-I PHE DTE. | SM/12031 | Augmentation | Acceptance cum work order for Construction of restoration approach road in Amritnagar Zone-I for Augmentation of RCFA Part-II under RCFA Division-I PHE Dte. (Part-B) | Assistant Engineer 2 | Junior Engineer | ORD/000948/2023-2024 | 499/RCDI | 12/02/2024 | 13/03/2024 | MACHINO TECHNO | 24.72 | 24.7 | 99.91 | 100
Total | [13 empty] | 450.72 | 307.09 | 68.13