## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-12B) UNDER RCFA DIVISION-I PHE DTE. | SM/12031 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000029/2023-2024 | 2945/RCD-I | 11/10/2023 | 11/10/2023 | Resource Division | 6.78 | 0 | 0 | 0
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-12B) UNDER RCFA DIVISION-I PHE DTE. | SM/12031 | Augmentation | Acceptance cum work order for Allied work of Distribution Network including FHTC & allied work at Ondal Block of RCFA Part-II (Zone-12 A) Piped Water Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000669/2023-2024 | 3436/RCD-1 | 24/11/2023 | 23/01/2024 | MRITYUNJOY MUKHERJEE & CO. | 81.28 | 48.77 | 60 | 65
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-12B) UNDER RCFA DIVISION-I PHE DTE. | SM/12031 | Augmentation | Acceptance cum work order for Health assessment of existing OHR of Barabani (910 Cum) and ancillary structures conducting Non-Destructive Test and thorough visual observation under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000539/2023-2024 | 3018/RCD-I | 16/10/2023 | 31/10/2023 | SIRCON ENGINEERING SERVICES | 4.95 | 4.95 | 100 | 100
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-12B) UNDER RCFA DIVISION-I PHE DTE. | SM/12031 | Augmentation | 100 mm dia water pipe line with 600 mm dia MS Casing pipe line (Jal Jeevan Mission) by R.C.F.A Division-1, PHE DTE, Asansol in between Parasia Siding ¿ New Jambad Siding at Km. CB-2/15-16 in Asansol Division of Eastern Railway under AUGMENTATION PWSS OF RCFA PART-II (ZONE-12B) UNDER RCFA DIVISION-I PHE DTE. |  |  | BILL/00863/2024-2025 | 396/24-25 | 28/10/2024 | 28/10/2024 | EASTERN RAILWAY | 4.58 | 0 | 0 | 0
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-12B) UNDER RCFA DIVISION-I PHE DTE. | SM/12031 | Augmentation | Formal Work Order for Distribution network for RCFA Part-II piped Water Supply Scheme including FHTC & allied work under RCFA Div-I, PHE Dte.(Zone-12B)(Segment-2). | Assistant Engineer 2 | Junior Engineer | ORD/000631/2022-2023 | 485/RCDI | 03/02/2023 | 04/04/2023 | M/S SINGH & KONAR CONSTRUCTION | 155.21 | 92 | 59.27 | 80
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-12B) UNDER RCFA DIVISION-I PHE DTE. | SM/12031 | Augmentation | Acceptance cum work order for Construction of CWR (Clear Water Reservoir) of capacity 200 cum & allied work at Shankarpur under Pandabeswar H/W Site within Pandabeswar Block for Augmentation of PWSS of RCFA Part-II (Zone-12B) under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000558/2024-2025 | 162/RCD-I | 08/01/2025 | 08/04/2025 | DIP CONSTRUCTION | 34.75 | 0 | 0 | 0
Total | [13 empty] | 287.55 | 145.72 | 50.68