## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-13) UNDER RCFA DIVISION-I PHE DTE. | SM/12032 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000030/2023-2024 | 2944/RCD-I | 11/10/2023 | 11/10/2023 | Resource Division | 6.78 | 0 | 0 | 0
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-13) UNDER RCFA DIVISION-I PHE DTE. | SM/12032 | Augmentation | Acceptance cum work order for Construction of Guard Room with toilet under Mangalpur Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000922/2023-2024 | 300/RCD-I | 07/02/2024 | 22/02/2024 | M/S SUBHRADEEP | 5.63 | 0 | 0 | 0
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-13) UNDER RCFA DIVISION-I PHE DTE. | SM/12032 | Augmentation | Acceptance cum work order for Repairing of Boundary Wall at Khandra Bisswari OHR Site under RCFA Part-II Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000923/2023-2024 | 299/RCD-I | 07/02/2024 | 23/03/2024 | NATIONAL CONSTRUCTION | 11.15 | 6.65 | 59.65 | 100
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-13) UNDER RCFA DIVISION-I PHE DTE. | SM/12032 | Augmentation | Acceptance cum work order Laying & Pushing of 600 mm dia RCC (NP3) Hume Pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at Charanpur Bus Stand and Faridpur of Barabani Block under Improvement of RCFA Part-I (Zone-11, Part-9) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000238/2023-2024 | 2231/RCD-I | 17/07/2023 | 16/08/2023 | SOMNATH SAMANTA | 14.44 | 14.39 | 99.7 | 100
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-13) UNDER RCFA DIVISION-I PHE DTE. | SM/12032 | Augmentation | Acceptance cum work order for Construction of Boundary Wall with gate (length 200 mtr.) land development with approach road including internal drain at H/W site & construction of guard room with toilet at Baliapur under Barabani Block in Improvement of RCFA Part-I W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000273/2023-2024 | 2330/RCD-I | 01/08/2023 | 30/10/2023 | AMAR CONSTRUCTION | 31.48 | 30.67 | 97.45 | 100
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-13) UNDER RCFA DIVISION-I PHE DTE. | SM/12032 | Augmentation | Acceptance cum work order for Supply and delivery of Centrifugal Pump Motor Set for Nimsha Village (High Lift) at Shemalya under AUGMENTATION PWSS OF RCFA PART-II (ZONE-13) Block - Jamuria, Dist - Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000699/2023-2024 | 3502/RCD-1 | 30/11/2023 | 10/12/2023 | M/S SWAPAN BANERJEE | 21.05 | 21.05 | 100 | 100
7 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-13) UNDER RCFA DIVISION-I PHE DTE. | SM/12032 | Augmentation | Way leave / Track crossing proposal with application ID : ER-ASN-2024-WL-93 at sonachara under Augmentation of RCFA Part-II (Zone-13) under RCFA Division-I PHE Dte |  |  | BILL/00118/2024-2025 | 51/24-25 | 20/05/2024 | 20/05/2024 | EASTERN RAILWAY | 4.9 | 0 | 0 | 0
8 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-13) UNDER RCFA DIVISION-I PHE DTE. | SM/12032 | Augmentation | Way leave / Track crossing proposal with application ID : ER-ASN-2024-WL-95 at Sonachara under Augmentation of RCFA Part-II (Zone-13) under RCFA Division-I PHE Dte |  |  | BILL/00117/2024-2025 | 50/24-25 | 20/05/2024 | 20/05/2024 | EASTERN RAILWAY | 4.58 | 0 | 0 | 0
9 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-13) UNDER RCFA DIVISION-I PHE DTE. | SM/12032 | Augmentation | Formal work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-13) | Assistant Engineer 2 | Junior Engineer | ORD/000068/2023-2024 | 1762/RCD I | 16/05/2023 | 12/11/2023 | MD AAMIR KHAN | 308.67 | 170.31 | 55.18 | 80
10 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-13) UNDER RCFA DIVISION-I PHE DTE. | SM/12032 | Augmentation | Formal work order for Augmentation of RCFA Part-II Piped Water Supply Scheme (zone-13) with Construction of 400 cum capacity RCC OHR with 20 mtr with staging height including Boundary Walls with gates and land Development, Drain ad internal pathway at OHR site under Jamuria Block, District- Paschim Bardhaman. | Assistant Engineer 2 | Junior Engineer | ORD/000100/2023-2024 | 1844/RCD-I | 31/05/2023 | 30/05/2024 | JAYANTA DATTA | 129.69 | 99.19 | 76.49 | 65
11 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-13) UNDER RCFA DIVISION-I PHE DTE. | SM/12032 | Augmentation | Acceptance cum work order for Construction of CWR (Clear Water Reservoir) of capacity 150 cum & allied works at Churulia under Augmentation of Churulia Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000705/2023-2024 | 3501/RCD-1 | 30/11/2023 | 28/02/2024 | SIMA ENTERPRISE | 23.68 | 22.16 | 93.61 | 100
12 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-13) UNDER RCFA DIVISION-I PHE DTE. | SM/12032 | Augmentation | Sub Soil Investigation for 400 cum capacity RCC Over Head Reservoir at (Zone-13) of Pandabeswar Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000553/2022-2023 | 3347/RCDI | 23/12/2022 | 12/02/2025 | MOYTEC | 0.46 | 0 | 0 | 100
13 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-13) UNDER RCFA DIVISION-I PHE DTE. | SM/12032 | Augmentation | Acceptance cum work order Sinking of 6 (Six) nos 200 mm dia river bed tube wells including collecting main for river Damodar at Kalajharia of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000348/2023-2024 | 2482/RCD-I | 23/08/2023 | 22/09/2023 | A. CONSTRUCTION CO. | 13.15 | 11.12 | 84.56 | 100
Total | [13 empty] | 575.64 | 375.55 | 65.24