## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14A) UNDER RCFA DIVISION-I PHE DTE. | SM/12033 | Augmentation | Acceptance cum work order for Additional work for laying MS pipe and allied works including adopting trench less technology (e.g. Jack Pushing Method etc) at Amnala irrigation Damp within command area of Zone-IX Part-I distribution system under Improvement of RCFA Part-I PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000672/2023-2024 | 3439/RCD-1 | 24/11/2023 | 09/12/2023 | KHEPI MAA TRADERS | 22.98 | 0 | 0 | 100
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14A) UNDER RCFA DIVISION-I PHE DTE. | SM/12033 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000031/2023-2024 | 2943/RCD-I | 11/10/2023 | 11/10/2023 | Resource Division | 6.78 | 0 | 0 | 0
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14A) UNDER RCFA DIVISION-I PHE DTE. | SM/12033 | Augmentation | Restoration and repairing work form Ch. 6.889 km to Ch 12.7 mm km of Chinchuria-Bhuri road under Asansol Division, PWD for laying pipe line under JJM |  |  | BILL/00464/2023-2024 | 236/23-24 | 29/08/2023 | 29/08/2023 | EXECUTIVE ENGINEER, ASANSOL DIVISION, PWD | 68.17 | 0 | 0 | 0
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14A) UNDER RCFA DIVISION-I PHE DTE. | SM/12033 | Augmentation | Formal work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-14A) | Assistant Engineer 2 | Junior Engineer | ORD/000027/2023-2024 | 1617/RCD I | 25/04/2023 | 22/10/2023 | KONAR CONSTRUCTION | 365.88 | 0 | 0 | 35
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14A) UNDER RCFA DIVISION-I PHE DTE. | SM/12033 | Augmentation | Sub Soil Investigation for 1250 cum capacity RCC Over Head Reservoir at (Zone-14A) of Pandabeswar Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000554/2022-2023 | 3348/RCDI | 23/12/2022 | 12/02/2025 | G. MITRA & ASSOCIATES | 0.5 | 0 | 0 | 100
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14A) UNDER RCFA DIVISION-I PHE DTE. | SM/12033 | Augmentation | Acceptance cum work order for Laying of different dia MS & HDPE Pipe line and mending works at Chanchani (Sansad-XII) of Ukhra area under Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. (Part-D) | Assistant Engineer 2 | Junior Engineer | ORD/000771/2022-2023 | 397/RCDI | 30/01/2023 | 01/03/2023 | M/S B.K. CONSTRUCTION | 11.94 | 0 | 0 | 100
7 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14A) UNDER RCFA DIVISION-I PHE DTE. | SM/12033 | Augmentation | Formal work order for Augmentation of RCFA Part-II Piped Water Supply Scheme (Zone-14A) with Construction of 1250 cum capacity RCC OHR with staging height including Boundary Walls with gates and land Development, Drain and internal pathway at OHR site under Jamuria Block, District Paschim Bardhaman. | Assistant Engineer 2 | Junior Engineer | ORD/000102/2023-2024 | 1842/RCD-I | 31/05/2023 | 30/05/2024 | A. CONSTRUCTION CO. | 277.09 | 0 | 0 | 40
8 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14A) UNDER RCFA DIVISION-I PHE DTE. | SM/12033 | Augmentation | Acceptance cum work order for Health assessment of existing OHR of Majiara (250 Cum) and ancillary structures conducting Non-Destructive Test and thorough visual observation under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000542/2023-2024 | 3020/RCD-I | 16/10/2023 | 31/10/2023 | SIRCON ENGINEERING SERVICES | 4.92 | 0 | 0 | 100
9 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14A) UNDER RCFA DIVISION-I PHE DTE. | SM/12033 | Augmentation | Acceptance cum work order for Balance work of in connection with Improvement of RCFA Part-I Water Supply Scheme within command area of Zone-V with LDS & FHTC work | Assistant Engineer 2 | Junior Engineer | ORD/000655/2023-2024 | 3427/RCD-1 | 24/11/2023 | 02/05/2024 | MACHINO TECHNO | 58.12 | 0 | 0 | 100
Total | [13 empty] | 816.38 | 0 | 0