## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14B) UNDER RCFA DIVISION-I PHE DTE. | SM/12039 | Augmentation | Acceptance cum work order for Additional work for distribution network including supply of Hume pipe, G.I. pipe and adopting trench less technologies at 02 (Two) locations in connection to Zone-I Part-A Dendua OHR for Improvement of RCFA Part-I Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000294/2023-2024 | 2365/RCD-I | 04/08/2023 | 03/09/2023 | ASHA CONSTRUCTION | 15.08 | 14.43 | 95.73 | 100
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14B) UNDER RCFA DIVISION-I PHE DTE. | SM/12039 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000032/2023-2024 | 2942/RCD-I | 11/10/2023 | 11/10/2023 | Resource Division | 6.78 | 0 | 0 | 0
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14B) UNDER RCFA DIVISION-I PHE DTE. | SM/12039 | Augmentation | Acceptance cum work order for Sinking of 03 (Three) nos. 200 mm dia river bed tube well including laying of 250 mm dia HDPE pipe line in the river of Ajoy for Ukhra Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000717/2023-2024 | 3546/RCD-1 | 07/12/2023 | 06/01/2024 | B.T.M. CONCERN | 21.19 | 1.96 | 9.27 | 10
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14B) UNDER RCFA DIVISION-I PHE DTE. | SM/12039 | Augmentation | Acceptance cum work order for Repairing and restoration of concrete road due to FHTC work at Kallya and surrounding villages within Kallya Gram Panchayat under Improvement of RCFA Part-I water Supply scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000658/2023-2024 | 3452/RCD-I | 24/11/2023 | 09/12/2023 | JAI MAHARAJ ENTERPRISE | 3.71 | 3.69 | 99.52 | 100
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14B) UNDER RCFA DIVISION-I PHE DTE. | SM/12039 | Augmentation | Formal work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-14B) | Assistant Engineer 2 | Junior Engineer | ORD/000071/2023-2024 | 1761/RCD I | 16/05/2023 | 01/01/2026 | MD AAMIR KHAN | 409.77 | 65.24 | 15.92 | 15
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14B) UNDER RCFA DIVISION-I PHE DTE. | SM/12039 | Augmentation | Acceptance cum work order for Shifting of existing rising main for construction of new Pump House at Dendua OHR Campus under Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000599/2023-2024 | 3281/RCD-I | 08/11/2023 | 06/02/2024 | D.S.ENTERPRISE | 12.45 | 12.26 | 98.47 | 100
7 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14B) UNDER RCFA DIVISION-I PHE DTE. | SM/12039 | Augmentation | Acceptance cum work order for Laying & pushing of 600 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc) of Water Pipe Lines at Railway Gate (Node No 116 to 128) under AUGMENTATION PWSS OF RCFA PART-II (ZONE-14B) under RCFA Division-I PHE Dte | Assistant Engineer 2 | Junior Engineer,Junior Engineer 12 | ORD/000661/2023-2024 | 3431/RCD-1 | 24/11/2023 | 22/02/2024 | SINGHA ROY & CO. | 44.79 | 37.7 | 84.17 | 100
8 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14B) UNDER RCFA DIVISION-I PHE DTE. | SM/12039 | Augmentation | Acceptance cum work order for Construction of CWR (Clear Water Reservoir) of capacity 150 cum & allied work at Baidyanathpur under AUGMENTATION PWSS OF RCFA PART-II (ZONE-14B) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000681/2023-2024 | 3473/RCD-I | 28/11/2023 | 01/06/2025 | MAA ENTERPRISE | 23.33 | 20.84 | 89.33 | 25
9 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14B) UNDER RCFA DIVISION-I PHE DTE. | SM/12039 | Augmentation | Acceptance cum work order of additional works of Dismantling & concrete works, Jack Pushing Supplying, Aligning and laying and other allied works at distribution system Networks for Shyamlya in Nimsa mouza under Shyamlya Gram Panchayat under Jamuria Block of Augmentation of PWSS RCFA Part-II (Zone-14B) under R.C.F.A Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000713/2023-2024 | 2883/RCD-I | 06/10/2023 | 01/04/2025 | A CONSTRUCTION CO | 37.4 | 14.4 | 38.5 | 100
10 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14B) UNDER RCFA DIVISION-I PHE DTE. | SM/12039 | Augmentation | Acceptance cum work order for Balance and other allied works for construction of store room at work site for(Zone-4A) of Pandabeswar and Andal Block for Augmentation of RCFA Part-II (Zone-14B) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer 11 | ORD/000542/2024-2025 | 145/RCD-I | 08/01/2025 | 08/04/2025 | RANJIB GHATAK | 20.29 | 0 | 0 | 70
11 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14B) UNDER RCFA DIVISION-I PHE DTE. | SM/12039 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000004/2024-2025 | 381/RCD-I | 28/02/2025 | 28/02/2025 | Resource Division | 30.8 | 0 | 0 | 0
12 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14B) UNDER RCFA DIVISION-I PHE DTE. | SM/12039 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000001/2025-2026 | 810/RCD-I | 16/04/2025 | 16/04/2025 | Resource Division | 61.6 | 0 | 0 | 0
Total | [13 empty] | 687.19 | 170.53 | 24.82