## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14C) UNDER RCFA DIVISION-I PHE DTE. | SM/12040 | Augmentation | Continuation work order for Supplying, fitting, fixing and fabrication of sign board including printing and carriage to different area with necessary allied works in connection with Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000589/2023-2024 | 2263/RCD-I | 19/07/2023 | 08/08/2023 | UNITED CONSTRUCTION | 17.51 | 10.12 | 57.78 | 60
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14C) UNDER RCFA DIVISION-I PHE DTE. | SM/12040 | Augmentation | Formal work order for Distribution Network for RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-14C) | Assistant Engineer 2 | Junior Engineer | ORD/000604/2022-2023 | 38/RCD-I | 11/01/2023 | 11/04/2023 | PRADIP KUMAR DEB | 378.29 | 291.68 | 77.11 | 100
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14C) UNDER RCFA DIVISION-I PHE DTE. | SM/12040 | Augmentation | Acceptence cum work order for Supplying aligning & laying 90 mm dia HDPE pipe line bye pass at Kallya, Dharashpur & Pahargara under Chotkara Kanskuli W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000401/2023-2024 | 2583/RCD-I | 07/09/2023 | 22/09/2023 | ASHA CONSTRUCTION | 8.67 | 8.54 | 98.54 | 100
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14C) UNDER RCFA DIVISION-I PHE DTE. | SM/12040 | Augmentation | Acceptance cum work order for Additional work supplying, laying and pushing of 600 mm dia MS cashing pipe for Railway crossing by Jack Pushing method with 150 mm dia MS water carrier pipe in Rupnarayanpur in between 232/16-18 (SLS-RNPR) in Asansol Division under distribution network Improvement RCFA Part-I Water Supply Scheme within command area of Zone-VII (Part-E) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000659/2023-2024 | 3430/RCD-1 | 24/11/2023 | 08/01/2024 | TARA CONSTRUCTION | 55.01 | 50.99 | 92.68 | 100
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14C) UNDER RCFA DIVISION-I PHE DTE. | SM/12040 | Augmentation | Continuation work order for Supplying, fitting, fixing and fabrication of sign board including printing and carriage to different area with necessary allied works in connection with Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. |  | Junior Engineer | ORD/001080/2023-2024 | 2382_A_RCD_I | 07/08/2023 | 27/08/2023 | UNITED CONSTRUCTION | 17.51 | 17.08 | 97.51 | 100
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14C) UNDER RCFA DIVISION-I PHE DTE. | SM/12040 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000033/2023-2024 | 2941/RCD-I | 11/10/2023 | 11/10/2023 | Resource Division | 6.78 | 0 | 0 | 0
7 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14C) UNDER RCFA DIVISION-I PHE DTE. | SM/12040 | Augmentation | Acceptance cum Work Order for Additional work along with Construction of Guard room with Toilet for Construction of 150 cum capacity RCC OHR with 20 Mtr staging height RCC Over Head Reservoir Piped connection and cost of pipes, specials at Augmentation of PWSS of RCFA Part-II (Zone-14C) Piped Water Supply Scheme under RCFA Division-I PHE Dte | Assistant Engineer 2 | Junior Engineer | ORD/000054/2024-2025 | 1744/RCD-I | 18/07/2024 | 31/03/2025 | NATIONAL CONSTRUCTION | 12.73 | 2.98 | 23.42 | 85
8 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14C) UNDER RCFA DIVISION-I PHE DTE. | SM/12040 | Augmentation | Acceptance cum work order for Balance Work of Road Restoration In Connection With Improvement of RCFA _Part-I Water Supply Scheme for Amritnagar Zone-II of Augmentation PWSS of RCFA Part-II (Zone-14C) under RCFA Division PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000108/2024-2025 | 2130/RCD-I | 27/08/2024 | 26/09/2024 | T M CONCRETE CREATION PVT.LTD | 48.27 | 47.82 | 99.08 | 100
9 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14C) UNDER RCFA DIVISION-I PHE DTE. | SM/12040 | Augmentation | Acceptance cum work order for Construction of Additional works of Pump House and other allied works at Damalia H/W Site for Augmentation PWSS of RCFA Part-II (Zone-14C) under RCFA, Division-I, PHE Dte. | Assistant Engineer 2 | Junior Engineer 10,Junior Engineer 12 | ORD/000094/2024-2025 | 2128/RCD-I | 27/08/2024 | 11/10/2024 | B.T.M. CONCERN | 15.28 | 15.12 | 98.97 | 100
10 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14C) UNDER RCFA DIVISION-I PHE DTE. | SM/12040 | Augmentation | Acceptance cum work order for Balance work of dismantling of concrete, restoration of road including pipe crossing by adopting trenchless technologies (e.g. Jack Pushing Method etc.) 03 nos. location at Haripur (Zone-14C) within Pandabeswar Block of Augmentation of PWSS RCFA Part-II (Zone-14C) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000537/2024-2025 | 140/RCD-I | 08/01/2025 | 08/04/2025 | MD AAMIR KHAN | 85.12 | 0 | 0 | 60
11 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-14C) UNDER RCFA DIVISION-I PHE DTE. | SM/12040 | Augmentation | Acceptance cum work order for Balance work for crossing of NH-60 by Jack Pushing Method and allied works at Haripur near CB Cure Hospital within Pandabeswar Block of Augmentation PWSS of RCFA Part-II (Zone-14C) under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer 4 | Junior Engineer | ORD/000252/2025-2026 | 1474/RCD-I | 15/05/2025 | 04/06/2025 | MD AAMIR KHAN | 13.99 | 0 | 0 | 100
Total | [13 empty] | 659.15 | 444.33 | 67.41