## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-15) UNDER RCFA DIVISION-I PHE DTE. | SM/12041 | Augmentation | Sub Soil Investigation for 450 cum capacity RCC Over Head Reservoir at (Zone-15) of Jamuria Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000563/2022-2023 | 3357/RCDI | 23/12/2022 | 30/12/2022 | MOYTEC | 0.49 | 0 | 0 | 0
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-15) UNDER RCFA DIVISION-I PHE DTE. | SM/12041 | Augmentation | Formal work order for construction of CWR 150 cum, sub station building of H/W site, pump house, chlorine room and other allied work (Bank of Ajoy river) under Semalya water Supply Scheme under RCFA Div-I, PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000917/2022-2023 | 1216/RCDI | 24/03/2023 | 03/11/2026 | SHILPA UDDOYG ENGINEERING CO-OP SOCIETY LTD. | 120.09 | 75.06 | 62.5 | 100
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-15) UNDER RCFA DIVISION-I PHE DTE. | SM/12041 | Augmentation | Formal work order for Augmentation of RCFA Part-II Pipe Water Supply Scheme (Zone-15) with Construction of 450 cum capacity RCC OHR with 20 mtr with staging height including Boundary Walls with under Jamuria Block, District Paschim Bardhaman. | Assistant Engineer 2 | Junior Engineer | ORD/000101/2023-2024 | 1843/RCD-I | 31/05/2023 | 30/05/2024 | GITA CONSTRUCTION | 150.65 | 0 | 0 | 0
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-15) UNDER RCFA DIVISION-I PHE DTE. | SM/12041 | Augmentation | Supplying, fitting, fixing and fabrication of sign board including printing and carriage to different area with necessary allied works in connection with Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000321/2023-2024 | Camp-02-Sign-Board-AE-II | 30/06/2023 | 20/07/2023 | UNITED CONSTRUCTION | 17.51 | 15.83 | 90.41 | 70
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-15) UNDER RCFA DIVISION-I PHE DTE. | SM/12041 | Augmentation | Acceptance cum work order for Allied work for bridge at Chalbalpur in connection with the laying distribution system for Amritnagar Zone-II under Augmentation of RCFA Part-II (Zone-15) under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer 3 | Junior Engineer | ORD/000514/2023-2024 | 2865/RCD-I | 06/10/2023 | 04/01/2024 | MRITYUNJOY MUKHERJEE & CO. | 70.4 | 52.84 | 75.06 | 100
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-15) UNDER RCFA DIVISION-I PHE DTE. | SM/12041 | Augmentation | Acceptance cum work order for Construction of CWR (Clear Water Reservoir) of capacity 100 cum & allied work at Bagdiha under Augmentation of RCFA Part-II (Zone-15) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000520/2023-2024 | 2877/RCD-I | 06/10/2023 | 04/01/2024 | M/S KALYANI ENTERPRISE | 18.69 | 0 | 0 | 0
7 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-15) UNDER RCFA DIVISION-I PHE DTE. | SM/12041 | Augmentation | Formal Work Order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-15) | Assistant Engineer 2,Assistant Engineer 3,Assistant Engineer 8 | Junior Engineer | ORD/000254/2023-2024 | 2299/RCD-I | 24/07/2023 | 01/01/2026 | SWATI CORPORATION | 516.27 | 197.04 | 38.17 | 100
8 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-15) UNDER RCFA DIVISION-I PHE DTE. | SM/12041 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000034/2023-2024 | 2940/RCD-I | 11/10/2023 | 11/10/2023 | Resource Division | 6.78 | 0 | 0 | 0
9 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-15) UNDER RCFA DIVISION-I PHE DTE. | SM/12041 | Augmentation | Way leave track crossing proposal with application ID - ER-ASN-2024-WL-57 Payment of wayleave facility charges. |  |  | BILL/00546/2024-2025 | 273/24-25 | 05/09/2024 | 05/09/2024 | EASTERN RAILWAY | 9.09 | 0 | 0 | 0
10 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-15) UNDER RCFA DIVISION-I PHE DTE. | SM/12041 | Augmentation | Way leave / Track crossing proposal with application ID : ER-ASN-2024-WL-92 at Ukhra under Augmentation of RCFA Part-II (Zone-15) under RCFA Division-I PHE Dte |  |  | BILL/00115/2024-2025 | 48/24-25 | 20/05/2024 | 20/05/2024 | EASTERN RAILWAY | 16.46 | 0 | 0 | 0
11 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-15) UNDER RCFA DIVISION-I PHE DTE. | SM/12041 | Augmentation | Restoration work for laying of 450 mm D.I. K9 pipeline under JJM work within the paved carriageway from Ch. 0.000 km to Ch. kmp at Right Side, Ch 03.006 km to Ch. 3.206 kmp at left side & ch. 4.570 km to Ch. 5.000 kmp at left side of Ukhra-Haripur Road under Asansol Division, PWD in the district of Paschim Bardhaman |  |  | BILL/00880/2024-2025 | 401/24-25 | 11/11/2024 | 11/11/2024 | EXECUTIVE ENGINEER, ASANSOL DIVISION, PWD | 24.61 | 0 | 0 | 0
12 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-15) UNDER RCFA DIVISION-I PHE DTE. | SM/12041 | Augmentation | Acceptance Order for distribution network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC within command area of Zone-15 under JAMURIA Block in the district of Paschim Bardhhaman under RCFA Division - I PHE Dte. [PART-C] | Assistant Engineer 8 | Junior Engineer | ORD/000526/2025-2026 | 2148/RCD-I | 28/07/2025 | 01/03/2026 | UNITED CONSTRUCTION | 129.89 | 0 | 0 | 55
13 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-15) UNDER RCFA DIVISION-I PHE DTE. | SM/12041 | Augmentation | Proposal for laying of underground water pipeline of R.C.F.A Division-I, P.H.E Dte. along & across NH-19 (Old NH-2) in the stretches - along from Km 485+400 to Km 489+050 (LHS), Km 486+427 to Km 488+599 (RHS) & Km 488+651 to Km 489+100 (RHS) & across at Km 486+910 & Km 488+854, Dist-Paschim Bardhaman, West Bengal. for Bank Guarantee |  |  | BILL/01330/2025-2026 |  | 29/10/2025 | 29/10/2025 | NATIONAL HIGHWAY AUTHORITY OF INDIA | 19.89 | 0 | 0 | 0
14 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-15) UNDER RCFA DIVISION-I PHE DTE. | SM/12041 | Augmentation | 6 lanning of Barwa-Adda Panagarh Section of NH-2 from Km. 398.240 to km 521.120 including Panagarh Bypass in the states of Jharkhand and West Bengal under NHDP Phase V on Toll on DBFOT pattern : Proposal for laying of under ground water pipeline of RCFA Division-I PHE Dte along & across NH-19 (Old NH-2) in the stretches along from Km 485+400 to Km 489+050 (LHS) , Km 486+427 to Km 488+599 (RHS) & km 488+651 to Km 489+100 (RHS) & across at Km 486+910 & km 488+854, District Pachim Bardhaman : Deposition of fees - reg. |  |  | BILL/00173/2025-2026 | 218/25-26 | 30/07/2025 | 30/07/2025 | NATIONAL HIGHWAY AUTHORITY OF INDIA | 33.2 | 0 | 0 | 0
Total | [13 empty] | 1134.02 | 340.78 | 30.05