## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-16) UNDER RCFA DIVISION-I PHE DTE. | SM/12042 | Augmentation | Acceptance cum work order for Construction of Chlorine Room of size (4.50 x 3.50 M) at (Zone-16) of Raniganj Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman (Sl No. 31) | Assistant Engineer 2 | Junior Engineer | ORD/000911/2022-2023 | 1175/RCD I | 24/03/2023 | 22/06/2023 | N.R. CONSTRUCTION | 4.61 | 0 | 0 | 0
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-16) UNDER RCFA DIVISION-I PHE DTE. | SM/12042 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000035/2023-2024 | 2939/RCD-I | 11/10/2023 | 11/10/2023 | Resource Division | 6.78 | 0 | 0 | 0
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-16) UNDER RCFA DIVISION-I PHE DTE. | SM/12042 | Augmentation | Sub Soil Investigation for 600 cum capacity RCC Over Head Reservoir at (Zone-16) of Raniganj Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000559/2022-2023 | 3353/RCDI | 23/12/2022 | 30/12/2022 | MOYTEC | 0.49 | 0.49 | 100 | 100
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-16) UNDER RCFA DIVISION-I PHE DTE. | SM/12042 | Augmentation | Acceptance cum work order for Balance work for laying of HDPE pipeline and PVC pipeline and allied works at Nabagram, Ukhra (Sansad-VI) Chatterjee para and Bahula Colony under RCFA Part-II Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000660/2023-2024 | 3453/RCD-I | 24/11/2023 | 09/12/2023 | MD AAMIR KHAN | 4.36 | 4.24 | 97.31 | 100
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-16) UNDER RCFA DIVISION-I PHE DTE. | SM/12042 | Augmentation | Acceptance cum work order for Additional Supplying aligning laying HDPE pipe Mechanical fitting supplying sluice valve and other allied works at (Mouza-Sahenganj) under Zone-16 Part-II W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001019/2023-2024 | 572/RCD-I | 23/02/2024 | 24/03/2024 | KRISHNA KUMAR TODI HUF | 36.45 | 36.45 | 100 | 100
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-16) UNDER RCFA DIVISION-I PHE DTE. | SM/12042 | Augmentation | Formal work word for Distribution Network for RCFA Part-II Pipe Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-16). | Assistant Engineer 2 | Junior Engineer | ORD/000039/2023-2024 | 1606/RCD I | 25/04/2023 | 01/01/2024 | JOY HIND TUBEWELLS | 488.35 | 417.76 | 85.55 | 100
7 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-16) UNDER RCFA DIVISION-I PHE DTE. | SM/12042 | Augmentation | Acceptance cum Work Order for Distribution Network for Improvement RCFA Part-II Water Supply Scheme within command area of Zone-16 including FHTC work (Part-A) under RCFA Div-I PHE Dte. (Mouza-Sahebganj) | Assistant Engineer 2 | Junior Engineer | ORD/000532/2022-2023 | 3160/RCD-I | 13/12/2022 | 12/01/2023 | KRISHNA KUMAR TODI HUF | 88.68 | 79.11 | 89.22 | 100
Total | [13 empty] | 629.71 | 538.06 | 85.45