## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-16) UNDER RCFA DIVISION-I PHE DTE. | SM/12042 | Augmentation | Acceptance cum Work Order for Distribution Network for Improvement RCFA Part-II Water Supply Scheme within command area of Zone-16 including FHTC work (Part-A) under RCFA Div-I PHE Dte. (Mouza-Sahebganj) | Assistant Engineer 2 | Junior Engineer | ORD/000532/2022-2023 | 3160/RCD-I | 13/12/2022 | 12/01/2023 | KRISHNA KUMAR TODI HUF | 88.68 | 79.11 | 89.22 | 100
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-16) UNDER RCFA DIVISION-I PHE DTE. | SM/12042 | Augmentation | Sub Soil Investigation for 600 cum capacity RCC Over Head Reservoir at (Zone-16) of Raniganj Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000559/2022-2023 | 3353/RCDI | 23/12/2022 | 30/12/2022 | MOYTEC | 0.49 | 0.49 | 100 | 100
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-16) UNDER RCFA DIVISION-I PHE DTE. | SM/12042 | Augmentation | Acceptance cum work order for Construction of Chlorine Room of size (4.50 x 3.50 M) at (Zone-16) of Raniganj Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman (Sl No. 31) | Assistant Engineer 2 | Junior Engineer | ORD/000911/2022-2023 | 1175/RCD I | 24/03/2023 | 22/06/2023 | N.R. CONSTRUCTION | 4.61 | 0 | 0 | 0
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-16) UNDER RCFA DIVISION-I PHE DTE. | SM/12042 | Augmentation | Formal work word for Distribution Network for RCFA Part-II Pipe Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-16). | Assistant Engineer 2 | Junior Engineer | ORD/000039/2023-2024 | 1606/RCD I | 25/04/2023 | 01/01/2024 | JOY HIND TUBEWELLS | 488.35 | 417.76 | 85.55 | 100
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-16) UNDER RCFA DIVISION-I PHE DTE. | SM/12042 | Augmentation | Formal work order for Construction of 600 cum capacity 20 mtr. Staging height RCC Over head Reservoir (pipe connection and cost of pipes, special at Raniganj Block (Zone-16) for Augmentation of RCFA Division-II piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman. Ref Drawing No. PC-I/OHR/2012 (Sheet No. 1 & 2) | Assistant Engineer 2 | Junior Engineer | ORD/000156/2023-2024 | 1899/RCD-I | 09/06/2023 | 09/06/2024 | ASHA CONSTRUCTION | 154.85 | 93.83 | 60.59 | 45
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-16) UNDER RCFA DIVISION-I PHE DTE. | SM/12042 | Augmentation | Acceptance cum work order for Balance work for laying of HDPE pipeline and PVC pipeline and allied works at Nabagram, Ukhra (Sansad-VI) Chatterjee para and Bahula Colony under RCFA Part-II Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000660/2023-2024 | 3453/RCD-I | 24/11/2023 | 09/12/2023 | MD AAMIR KHAN | 4.36 | 4.24 | 97.31 | 100
7 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-16) UNDER RCFA DIVISION-I PHE DTE. | SM/12042 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000035/2023-2024 | 2939/RCD-I | 11/10/2023 | 11/10/2023 | Resource Division | 6.78 | 0 | 0 | 0
8 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-16) UNDER RCFA DIVISION-I PHE DTE. | SM/12042 | Augmentation | Acceptance cum work order for Additional Supplying aligning laying HDPE pipe Mechanical fitting supplying sluice valve and other allied works at (Mouza-Sahenganj) under Zone-16 Part-II W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001019/2023-2024 | 572/RCD-I | 23/02/2024 | 24/03/2024 | KRISHNA KUMAR TODI HUF | 36.45 | 36.45 | 100 | 100
9 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-16) UNDER RCFA DIVISION-I PHE DTE. | SM/12042 | Augmentation | Acceptance cum work order for Crossing 600 mm dia MS pipes under the Railway track by jack pushing technology at different spots and pushing diff. dia M.S pipes throgh 600 mm dia MS pipes in connection with the work for the laying distribution system for Augmentation of Sub - Surface water based piped water supply scheme for Amritnagar Zone -II for Augmentation of PWSS RCFA Part-II (Zone-16) Under RCFA Division -I PHE. Dte. | Assistant Engineer 2,Assistant Engineer 3 | Junior Engineer | ORD/000192/2024-2025 | 2419/RCD-I | 26/09/2024 | 01/04/2025 | MRITYUNJOY MUKHERJEE & CO. | 40.11 | 34.45 | 85.89 | 70
Total | [13 empty] | 824.67 | 666.34 | 80.8