## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-11) UNDER RCFA DIVISION-I PHE DTE. | SM/12210 | Augmentation | Acceptance cum work order for Construction of Chlorine Room of size (4.50 x 3.50 M) at (Zone-11) of Raniganj Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000092/2023-2024 | 1755/RCD-I | 12/05/2023 | 10/08/2023 | MAA DURGA ENTERPRISE | 4.6 | 0 | 0 | 0
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-11) UNDER RCFA DIVISION-I PHE DTE. | SM/12210 | Augmentation | Acceptance cum work order Laying & Pushing of 600 mm dia RCC (NP3) Hume Pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at Amnala more to towards Amnala village surrounding area (Zone-IX) under Improvement of RCFA Part-I (Zone-11) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000226/2023-2024 | 2228/RCD-I | 17/07/2023 | 16/08/2023 | KHEPI MAA TRADERS | 13.09 | 13.09 | 100 | 100
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-11) UNDER RCFA DIVISION-I PHE DTE. | SM/12210 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000027/2023-2024 | 2947/RCD-I | 11/10/2023 | 11/10/2023 | Resource Division | 6.78 | 0 | 0 | 0
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-11) UNDER RCFA DIVISION-I PHE DTE. | SM/12210 | Augmentation | Formal work order for distribution network for RCFA Part-II Piped Water Supply including FHTC & allied work under RCFA Div-I, PHE Dte.(Zone-11) | Assistant Engineer 2 | Junior Engineer | ORD/000003/2023-2024 | 1390/RCD I | 11/04/2023 | 10/07/2023 | M/S SRI MAHADEO ENTERPRISES | 294.95 | 247.45 | 83.9 | 85
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-11) UNDER RCFA DIVISION-I PHE DTE. | SM/12210 | Augmentation | Acceptance cum work order for Trial Run for Barabani Kashidanga under Improvement of RCFA Part-I (Zone-XI) Piped W/S Scheme under RCFA Division-I PHE Dte. (180 days) | Assistant Engineer 2 | Junior Engineer | ORD/000665/2023-2024 | 3455/RCD-I | 24/11/2023 | 22/05/2024 | UNITED CONSTRUCTION | 1.08 | 0 | 0 | 0
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-11) UNDER RCFA DIVISION-I PHE DTE. | SM/12210 | Augmentation | Acceptence cum work order for Additional work repairing old plaster surface, color washing, painting and R.B.T. (Reinforced Barbed Tape) Concertina fencing on wall and allied works at Kalyaneswari Inspection Bungalow under RCFA Division-I PHE Dte | Assistant Engineer 2 | Junior Engineer | ORD/000399/2023-2024 | 2581/RCD-I | 07/09/2023 | 22/09/2023 | JYOGOMAYA ENTERPRISE | 5.71 | 5.14 | 90.01 | 100
7 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-11) UNDER RCFA DIVISION-I PHE DTE. | SM/12210 | Augmentation | Acceptance cum work order for Health assessment of existing OHR of Ethora (779 Cum) and ancillary structures conducting Non-Destructive Test and thorough visual observation under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000535/2023-2024 | 3016/RCD-I | 16/10/2023 | 31/10/2023 | SIRCON ENGINEERING SERVICES | 4.93 | 4.93 | 100 | 100
8 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-11) UNDER RCFA DIVISION-I PHE DTE. | SM/12210 | Augmentation | Acceptance cum work order for Health assessment of existing OHR of Pariharpur (900 Cum) and ancillary structures conducting Non-Destructive Test and thorough visual observation under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000536/2023-2024 | 3023/RCD-1 | 16/10/2023 | 31/10/2023 | RISHAN ENGINEERING CONSULTANCY | 4.95 | 4.95 | 100 | 100
9 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-11) UNDER RCFA DIVISION-I PHE DTE. | SM/12210 | Augmentation | Acceptance cum work order for Health assessment of existing OHR of Amritnagar (1135 Cum) and ancillary structures conducting Non-Destructive Test and thorough visual observation under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000543/2023-2024 | 3026/RCD-1 | 16/10/2023 | 31/10/2023 | RISHAN ENGINEERING CONSULTANCY | 4.97 | 4.97 | 100 | 100
10 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-11) UNDER RCFA DIVISION-I PHE DTE. | SM/12210 | Augmentation | Acceptance cum work order for Additional work for laying distribution main over concrete pillar including supply of rubber gusket within Zone-XI Part-I under Improvement of RCFA Part-I Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000676/2023-2024 | 3475/RCD-I | 28/11/2023 | 13/12/2023 | R B ENTERPRISE | 4.89 | 1.86 | 37.94 | 100
11 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-11) UNDER RCFA DIVISION-I PHE DTE. | SM/12210 | Augmentation | Acceptance cum work order for Additional supplying, aligning, laying HDPE & PVC pipe line, construction of sluice valve chamber and other allied works under Tirat Mouza (Taldanga, Pathan Dhaora & Shyamdanga) W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000648/2023-2024 | 3425/RCD-1 | 24/11/2023 | 24/12/2023 | RUBY CONSTRUCTION | 6.78 | 6.65 | 98.02 | 100
12 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-11) UNDER RCFA DIVISION-I PHE DTE. | SM/12210 | Augmentation | Acceptance cum work order for Sinking of 3 (Three) nos 200 mm dia river bed tube well including collecting main in the river of Damodar at D.P Colony H/W Site for D P Colony Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000645/2023-2024 | 3423/RCD-1 | 24/11/2023 | 09/12/2023 | DURGA DAS MONDAL | 9.53 | 9.49 | 99.53 | 100
13 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-11) UNDER RCFA DIVISION-I PHE DTE. | SM/12210 | Augmentation | Acceptance cum work order for Additional works of Dismantling & concrete works, Supplying, Aligning & Laying HDPE Pipe and other allied works at distribution system Network for Shyamlya in Chatrisganda Mouza under Shyamlya Gram Panchayat under Jamuria Block under RCFA Division-I PHE Dte. (Part-B) | Assistant Engineer 2 | Junior Engineer | ORD/000701/2023-2024 | 3499/RCD-1 | 30/11/2023 | 30/12/2023 | DAWN CONSTRUCTION | 45.48 | 45.02 | 99 | 100
14 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-11) UNDER RCFA DIVISION-I PHE DTE. | SM/12210 | Augmentation | Acceptance cum work order for Additional work for laying collecting and other allied works at DP Colony PWSS under RCFA Division-I PHE Dte. Augmentation PWSS of RCFA Part-II (Zone-11) | Assistant Engineer 2 | Junior Engineer | ORD/000947/2023-2024 | 505/RCD-I | 12/02/2024 | 13/03/2024 | DURGA DAS MONDAL | 7.01 | 6.9 | 98.49 | 100
15 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-11) UNDER RCFA DIVISION-I PHE DTE. | SM/12210 | Augmentation | Acceptance cum Work Order for Extension of Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone - XI (Part-8 Distribution Segment) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001120/2023-2024 | 926/RCD-I | 15/03/2024 | 04/04/2024 | SIMA ENTERPRISE | 7.02 | 6.79 | 96.77 | 100
16 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-11) UNDER RCFA DIVISION-I PHE DTE. | SM/12210 | Augmentation | Acceptance cum work order for Additional work for the laying of Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area Zone-VII of Augmentation of RCFA Part-II (Zone-11) PWSS under RCFA Division-I PHE Dte. (Part-D) | Assistant Engineer 2 | Junior Engineer | ORD/001215/2023-2024 | 935_RCD_I | 15/03/2024 | 30/03/2024 | KONAR CONSTRUCTION | 23.57 | 23.52 | 99.78 | 100
17 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-11) UNDER RCFA DIVISION-I PHE DTE. | SM/12210 | Augmentation | Way leave / Track crossing proposal with application ID : ER-ASN-2024-WL-91 at Pandabeswar under Augmentation of RCFA Part-II (Zone-11) under RCFA Division-I PHE Dte |  |  | BILL/00114/2024-2025 | 47/24-25 | 20/05/2024 | 20/05/2024 | EASTERN RAILWAY | 5.45 | 0 | 0 | 0
18 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-11) UNDER RCFA DIVISION-I PHE DTE. | SM/12210 | Augmentation | Way leave track crossing proposal with application ID - ER-ASN-2024-WL-56 Payment of wayleave facility charges. |  |  | BILL/00545/2024-2025 | 272/24-25 | 05/09/2024 | 05/09/2024 | EASTERN RAILWAY | 6.27 | 0 | 0 | 0
19 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-11) UNDER RCFA DIVISION-I PHE DTE. | SM/12210 | Augmentation | Way leave / Track crossing proposal with application ID : ER-ASN-2024-WL-90 at Pandabeswar under Augmentation of RCFA Part-II (Zone-11) under RCFA Division-I PHE Dte |  |  | BILL/00116/2024-2025 | 49/24-25 | 20/05/2024 | 20/05/2024 | EASTERN RAILWAY | 5.45 | 0 | 0 | 0
20 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-11) UNDER RCFA DIVISION-I PHE DTE. | SM/12210 | Augmentation | Way leave / Track crossing proposal with application ID : ER-ASN-2024-WL-18 under Augmentation of RCFA Part-II (Zone-11) under RCFA Division-I PHE Dte |  |  | BILL/00156/2024-2025 | 69/24-25 | 30/05/2024 | 30/05/2024 | EASTERN RAILWAY | 14.3 | 0 | 0 | 0
21 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-11) UNDER RCFA DIVISION-I PHE DTE. | SM/12210 | Augmentation | Sub Soil Investigation for 350 cum capacity RCC Over Head Reservoir at (Zone-11) of Raniganj Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000556/2022-2023 | 3350/RCDI | 23/12/2022 | 31/01/2025 | MOYTEC | 0.49 | 0.49 | 100 | 100
22 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART-II (ZONE-11) UNDER RCFA DIVISION-I PHE DTE. | SM/12210 | Augmentation | Formal work order for Construction of 350 cum capacity 20 mtr. staging height RCC Over Head Reservoir (pipe connection and cost of pipes, specials at Raniganj Block (Zone-11) for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District Paschim Bardhaman. Ref Drawing No. PC-I/OHR/2012 (Sheet No. 1 & 2) | Assistant Engineer 2 | Junior Engineer | ORD/000097/2023-2024 | 1841/RCD-I | 31/05/2023 | 31/05/2024 | DAS & CHAKRABORTY | 115.95 | 104.36 | 90 | 90
Total | [13 empty] | 593.26 | 485.61 | 81.85