## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE | SM/12215 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000013/2023-2024 | 2933/RCD-I | 11/10/2023 |  | Resource Division | 6.78 | 0 | 0 | 0
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE | SM/12215 | Augmentation | Way leave / track crossing proposal with Application ID ER-ASN-2023-WL-71 for Nimcha - J.K.Nagar under AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) under RCFA Division-I, PHE Dte |  |  | BILL/00790/2023-2024 | 378/23-24 | 22/11/2023 |  | EASTERN RAILWAY | 0.11 | 0 | 0 | 0
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE | SM/12215 | Augmentation | Way leave / track crossing proposal with Application ID ER-ASN-2023-WL-72 for Nimcha - J.K.Nagar under AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) under RCFA Division-I, PHE Dte |  |  | BILL/00788/2023-2024 | 382/23-24 | 22/11/2023 |  | EASTERN RAILWAY | 0.09 | 0 | 0 | 0
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE | SM/12215 | Augmentation | Way leave / track crossing proposal with Application ID ER-ASN-2023-WL-70 for Nimcha - J.K.Nagar under AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) under RCFA Division-I, PHE Dte |  |  | BILL/00791/2023-2024 | 379/23-24 | 22/11/2023 |  | EASTERN RAILWAY | 0.11 | 0 | 0 | 0
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE | SM/12215 | Augmentation | Way leave / track crossing proposal with Application ID ER-ASN-2023-WL-69 for Nimcha - J.K.Nagar under AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) under RCFA Division-I, PHE Dte |  |  | BILL/00792/2023-2024 | 380/23-24 | 22/11/2023 |  | EASTERN RAILWAY | 0.09 | 0 | 0 | 0
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE | SM/12215 | Augmentation | Way leave / track crossing proposal with Application ID ER-ASN-2023-WL-68 for Nimcha - J.K.Nagar under AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) under RCFA Division-I, PHE Dte |  |  | BILL/00793/2023-2024 | 381/23-24 | 22/11/2023 |  | EASTERN RAILWAY | 0.09 | 0 | 0 | 0
7 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE | SM/12215 | Augmentation | Way leave / track crossing proposal with Application ID ER-ASN-2023-WL-67 for Nimcha - Kalipahari under AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) under RCFA Division-I, PHE Dte |  |  | BILL/00794/2023-2024 | 383/23-24 | 22/11/2023 |  | EASTERN RAILWAY | 0.14 | 0 | 0 | 0
8 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE | SM/12215 | Augmentation | Acceptance cum work order for Conducting route survey, design rising main network and preparation & submission of source augmentation DPR for Parasia Water Supply Scheme for Implementation of JJM at Jamuria Block under RCFA DIVISION-I, P.H.E. Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000507/2023-2024 | 2969/RCD-I | 11/10/2023 | 26/10/2023 | SIRCON ENGINEERING SERVICES | 4.97 | 2.49 | 50 | 100
9 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE | SM/12215 | Augmentation | Acceptance cum work order for Conducting route survey, design rising main network and preparation & submission of source augmentation DPR for BAHADURPUR Water Supply Scheme for Implementation of JJM at Jamuria Block under RCFA DIVISION-I, P.H.E. Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000508/2023-2024 | 2970/RCD-I | 11/10/2023 | 26/10/2023 | SIRCON ENGINEERING SERVICES | 4.97 | 2.49 | 50 | 100
10 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE | SM/12215 | Augmentation | Acceptance cum work order for Conducting route survey, design rising main network and preparation & submission of source augmentation DPR for Panchgachia & Majiara Water Supply Scheme for Implementation of JJM at Barabani Block under RCFA DIVISION-I, P.H.E. Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000512/2023-2024 | 2974/RCD-I | 11/10/2023 | 26/10/2023 | SIRCON ENGINEERING SERVICES | 4.97 | 2.49 | 50 | 100
11 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE | SM/12215 | Augmentation | Acceptance cum work order for Conducting route survey, design rising main network and preparation & submission of source augmentation DPR for RATIBATI Water Supply Scheme for Implementation of JJM at Jamuria Block under RCFA DIVISION-I, P.H.E. Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000510/2023-2024 | 2972/RCD-I | 11/10/2023 | 26/10/2023 | SIRCON ENGINEERING SERVICES | 4.97 | 2.49 | 50 | 100
12 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE | SM/12215 | Augmentation | Acceptance cum work order for Conducting route survey, design rising main network and preparation & submission of source augmentation DPR for BAHULA Water Supply Scheme for Implementation of JJM at Pandabeswar Block under RCFA DIVISION-I, P.H.E. Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000511/2023-2024 | 2973/RCD-I | 11/10/2023 | 26/10/2023 | RISHAN ENGINEERING CONSULTANCY | 4.97 | 2.49 | 50 | 100
13 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE | SM/12215 | Augmentation | Acceptance cum work order for Conducting route survey, design rising main network and preparation & submission of source augmentation DPR for HARIPUR Water Supply Scheme for Implementation of JJM at Pandabeswar Block under RCFA DIVISION-I, P.H.E. Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000509/2023-2024 | 2971/RCD-I | 11/10/2023 | 26/10/2023 | RISHAN ENGINEERING CONSULTANCY | 4.97 | 2.49 | 50 | 100
14 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE | SM/12215 | Augmentation | Acceptance cum work order for Supplying, Aligning, laying HDPE pipe & Supply Sluice Valve & construction of sluice valve chamber including providing FHTC and other allied works at Ratibati village Ratibati W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000469/2023-2024 | 2874/RCD-1 | 06/10/2023 | 05/11/2023 | NIYATI CONSTRUCTION | 7.87 | 3.93 | 49.95 | 100
15 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE | SM/12215 | Augmentation | Acceptance cum work order for Emergency repairing of damaged collecting main in river Damodar and allied works at Surjanagar H/W site of Surjanagar W/S Scheme under RCFA Division -I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000620/2023-2024 | 3383/RCD-I | 21/11/2023 | 06/12/2023 | MD. JAWED KHAN | 4.27 | 2.14 | 50.03 | 100
16 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE | SM/12215 | Augmentation | Acceptance cum work order for Supplying aligning, Laying of PVC pipe, HDPE pipe sluice valve, Sluice valve chamber and other allied works at Oriapara, Chapui Vaskadaora 7 nos pit to Rangadanga Talbagan under Ratibati Gram Panchayet under RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000637/2023-2024 | 3419/RCD-1 | 24/11/2023 | 24/12/2023 | M/S KALYAN ENTERPRISE | 7.78 | 3.89 | 50 | 100
17 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE | SM/12215 | Augmentation | Acceptance cum work order for Withdrawing, supplying, aligning Relaying of 80 mm dia PVC pipe line, repairing of street stand post and other allied works at Goylapara under Tirat Gram Panchyat under RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000639/2023-2024 | 3420/RCD-1 | 24/11/2023 | 24/12/2023 | M/S KALYAN ENTERPRISE | 6.24 | 0 | 0 | 100
18 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE | SM/12215 | Augmentation | Acceptance cum work order for 2nos of Emergency repairing work of 450 mm dia rising main at Upper Jamdoba and Nichu Para under RCFA Part-II W7S scheme under RCFA Div-I, PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000483/2023-2024 | 2890/RCD-I | 06/10/2023 | 21/10/2023 | KHEPI MAA TRADERS | 2.29 | 1.15 | 50 | 100
19 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE | SM/12215 | Augmentation | Acceptance cum work order for Laying of 90mm dia HDPE pipe and allied works at Bauri para of Khandra area of Block-Ondal under RCFA Part-II water supply scheme under RCFA Div-I, PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000487/2023-2024 | 2893/RCD-I | 06/10/2023 | 21/10/2023 | KHEPI MAA TRADERS | 2.33 | 1.16 | 49.96 | 100
20 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE | SM/12215 | Augmentation | Acceptance cum work order for Laying 450 mm dia MS water pipe line with 700 mm dia MS casing pipe for Railway crossing in between KM 227/27-29 and between Salanpur (SLS) Rupnarayanpur (RNPR) in Asansol Division under JJM under RCFA Division-I PHE Dte | Assistant Engineer 2 | Junior Engineer | ORD/000423/2023-2024 | 2621/RCD-I | 13/09/2023 | 28/09/2023 | MAK CONSTRUCTION CO. | 62.81 | 62.23 | 99.07 | 100
21 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE | SM/12215 | Augmentation | Emergent Sinking of one no.200 x 165 mm Rig box tubewell at ADM Bunglow, Asansol, Paschim Bardhaman, Under R.C.F.A Div-I, PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000888/2023-2024 | SpotNITCamp-02/ADMBunglow | 09/01/2024 | 16/01/2024 | M/S CHANDI CHARAN ROY | 7.5 | 3.72 | 49.58 | 100
22 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE | SM/12215 | Augmentation | Acceptance cum work order for Emergency work for Withdrawing and Relaying of collecting main and other allied works at Damalia H/W under RCFA part II at Damodar river under Amritnagar water supply scheme under RCFA Division -I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000608/2023-2024 | 3368/RCD-1 | 21/11/2023 | 06/12/2023 | M/S KALYAN ENTERPRISE | 2.78 | 1.39 | 50 | 100
23 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE | SM/12215 | Augmentation | Acceptance cum work order for Laying 450 mm dia MS water pipe line with 700 mm dia MS casing pipe for Railway crossing in Salanpur in between KM 227/31-33 and Salanpur (SLS) ¿ Rupnarayanpur (RNPR) Station in Asansol Division of JJM under Augmentation of RCFA Part-II (Zone-3) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000518/2023-2024 | 2870/RCD-I | 06/10/2023 | 05/11/2023 | SWATI CORPORATION | 67.3 | 30.05 | 44.65 | 100
24 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE | SM/12215 | Augmentation | Acceptance cum Work Order for Replacing existing UPVC pipe line with HDPE at Marickkota and different village under Salanpur Block under RCFA Part-I PWSS under RCFA Division-I PHE Dte | Assistant Engineer 2 |  | ORD/000981/2023-2024 | 509/RCD-I | 12/02/2024 | 28/03/2024 | SUKHENDU MAJUMDAR | 6.37 | 0 | 0 | 0
25 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE | SM/12215 | Augmentation | Continuation work order for Conducting route survey, design rising main network and preparation & submission of source augmentation DPR for Improvement of Collector well by infiltration gallery at Kalajharia Part-II W/S Scheme | Assistant Engineer 2 |  | ORD/001011/2023-2024 | 3523-B/RCD-I | 04/12/2023 | 19/12/2023 | SIRCON ENGINEERING SERVICES | 4.97 | 2.49 | 50 | 100
26 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE | SM/12215 | Augmentation | Continuation of work order for Conducting route survey, design rising main network and preparation & submission of source Augmentation DPR for Ukhra OHR of RCFA (Part-I) PWSS. | Assistant Engineer 2 |  | ORD/001008/2023-2024 | 3523-A/RCD-I | 04/12/2023 | 19/12/2023 | SIRCON ENGINEERING SERVICES | 4.97 | 2.49 | 50 | 100
27 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE | SM/12215 | Augmentation | Continuation work order for Conducting route survey, design rising main network and preparation & submission of source augmentation DPR for Madanpur OHR of RCFA (Part-I) PWSS under RCFA DIVISION-I , P.H.E Dte. | Assistant Engineer 2 |  | ORD/001012/2023-2024 | 3523-C/RCD-I | 04/12/2023 | 19/12/2023 | SIRCON ENGINEERING SERVICES | 4.97 | 2.49 | 50 | 100
28 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE | SM/12215 | Augmentation | Acceptance cum Work Order for Additional works of sinking of 3 (Three) nos. 200 mm dia river bed tube well including collecting main in the river Damodar at Gourbazar H/W Site for Hourbazar Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000982/2023-2024 | 510/RCD-I | 12/02/2024 | 08/03/2024 | R B ENTERPRISE | 12.96 | 6.26 | 48.3 | 100
29 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE | SM/12215 | Augmentation | Acceptance cum Work Order for Additional work for Road Crossing by adopting trenchless technology at 3 (Three) nos locations near ECL stack yard including restoration of road from Dabor more to Amdanga more in connection to rising main Part-A under Improvement of RCFA Part-I in Connection of Rising Main (Part-A) under RCFA Division-I PHE Dte | Assistant Engineer 2 |  | ORD/000957/2023-2024 | 482/RCD-I | 12/02/2024 | 28/03/2024 | MD AAMIR KHAN | 44.01 | 21.97 | 49.92 | 100
30 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE | SM/12215 | Augmentation | Acceptance cum Work Order for Laying MS pipe over bridge / culvert including adopting trench less technology (e.g. Jack Pushing Method etc) at 4 (Four) nos location within laying distribution system of Amritnagar (Part-A) under Augmentation of Amritnagar Zone-I PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000959/2023-2024 | 483/RCD-I | 12/02/2024 | 28/03/2024 | TARAPRASAD SARKAR | 25.18 | 12.49 | 49.58 | 100
31 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE | SM/12215 | Augmentation | Acceptance cum work order for Additional Supplying Aligning & laying HDPE pipe supplying sluice valve and others allied works of different places under Nutun Egara under Narayankuri W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000933/2023-2024 | 496/RCD-1 | 12/02/2024 | 28/03/2024 | DIP CONSTRUCTION | 8.67 | 4.33 | 49.98 | 100
32 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE | SM/12215 | Augmentation | Formal work order for distribution network for RCFA Part-II Piped water Supply Scheme including FHTC & allied works under RCFA Div-I, PHE Dte. (Zone-3)(Ukhra) | Assistant Engineer 2 | Junior Engineer | ORD/000821/2022-2023 | 1002/RCDI | 22/03/2023 | 20/07/2023 | SINGHA ROY & CO. | 392.43 | 313.68 | 79.93 | 86
33 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE | SM/12215 | Augmentation | Acceptance cum Work Order for Balance work for laying of different dia HDPE pipe line (left out portion) and other allied works at Amritnagar (Part-A) under Augmentation of Amritnagar Zone-I under RCFA Division-I PHE Dte | Assistant Engineer 2 | Junior Engineer 12 | ORD/000991/2023-2024 | 481/RCD-I | 12/02/2024 | 28/03/2024 | M/S SINGH & KONAR CONSTRUCTION | 45.53 | 0 | 0 | 0
34 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE | SM/12215 | Augmentation | Acceptance cum work order for Construction of Pump House at Shyamla for Kendra Khottamdihi Water Supply Scheme under RCFA Division-I.PHE Dte | Assistant Engineer 2 |  | ORD/001208/2023-2024 | 1015/RCD-I | 16/03/2024 | 15/05/2024 | GHOSH ENTERPRISE | 30.83 | 0 | 0 | 0
35 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE | SM/12215 | Augmentation | Acceptance cum work order for Additional providing FHTC of retrofitting at kumardiha Village (left out portion) of Kumardiha Mouza, GP-Ratibati Block Raniganj of Ratibati Water supply scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/001206/2023-2024 | 1023/RCD-I | 16/03/2024 | 15/04/2024 | SAYAN CONSTRUCTION | 5.65 | 0 | 0 | 0
36 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE | SM/12215 | Augmentation | Acceptance cum Work Order for Additional work of 50 cum/hr capacity I.E. Plant at Churulia and Madanpur Head Works Site Augmentation of RCFA Part-II (Zone-3) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000989/2023-2024 | 475/RCD-I | 12/02/2024 | 12/04/2024 | TARAPRASAD SARKAR | 31.29 | 11.73 | 37.5 | 100
37 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE | SM/12215 | Augmentation | Acceptance cum Work Order for Additional works of dismantling & concrete works, laterite and sand filling at distribution system network for RCFA Part-II (Zone-3) PWSS including FHTC & allied works under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer,Junior Engineer 12 | ORD/000977/2023-2024 | 493/RCD-I | 12/02/2024 | 18/03/2024 | SINGHA ROY & CO. | 77.52 | 17.51 | 22.59 | 45
38 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) UNDER RCFA DIVISION-I PHE DTE | SM/12215 | Augmentation | Acceptance cum Work Order for Additional repairing and maintenance work of RCC Elevated reservoir, Boundary Wall and other allied works at Mangalpur of 25000 gallon capacity under Augmentation of RCFA Part-II (Zone-3) Water Supply Scheme under RCFA Division-I PHE Dte | Assistant Engineer 2 | Junior Engineer | ORD/001186/2023-2024 | 938/RCD-I | 15/03/2024 | 30/03/2024 | M/S SUBHRADEEP | 16.89 | 8.26 | 48.92 | 100
Total | [13 empty] | 920.69 | 528.27 | 57.38