## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART II (ZONE 4A) UNDER RCFA DIVISION-I PHE DTE. | SM/12219 | Augmentation | Acceptance cum work order for Construction of Store Room at Head Works Site for (Zone-4A) of Pandabeswar and Andal Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman. (Sl No. 29) | Assistant Engineer 2 | Junior Engineer | ORD/000902/2022-2023 | 1173/RCD I | 24/03/2023 | 22/06/2023 | RANJIB GHATAK | 4.61 | 0 | 0 | 0
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART II (ZONE 4A) UNDER RCFA DIVISION-I PHE DTE. | SM/12219 | Augmentation | Acceptance cum work order for construction of Chlorine Room of Size (4.50 x 3.50 m) at (Zone-VII) of Salanpur Block for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000657/2022-2023 | 356/RCDI | 30/01/2023 | 14/02/2023 | DAS & SARKAR ENTERPRISE | 4.6 | 3.78 | 82.11 | 100
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART II (ZONE 4A) UNDER RCFA DIVISION-I PHE DTE. | SM/12219 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000014/2023-2024 | 2934/RCD-I | 11/10/2023 | 11/10/2023 | Resource Division | 6.78 | 0 | 0 | 0
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART II (ZONE 4A) UNDER RCFA DIVISION-I PHE DTE. | SM/12219 | Augmentation | Acceptance cum work order for Health assessment of existing OHR of ASTA (1135 Cum) and ancillary structures conducting Non-Destructive Test and thorough visual observation under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000531/2023-2024 | 3021/RCD-I | 16/10/2023 | 31/10/2023 | SIRCON ENGINEERING SERVICES | 4.98 | 4.98 | 100 | 100
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART II (ZONE 4A) UNDER RCFA DIVISION-I PHE DTE. | SM/12219 | Augmentation | Acceptance cum work order for Health assessment of existing OHR of Dendua(1135Cum) and ancillary structure sconducting Non-Destructive Test and thorough visual observation under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000532/2023-2024 | 3014/RCD-I | 16/10/2023 | 31/10/2023 | SIRCON ENGINEERING SERVICES | 4.98 | 4.98 | 100 | 100
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART II (ZONE 4A) UNDER RCFA DIVISION-I PHE DTE. | SM/12219 | Augmentation | Acceptance cum work order for Construction for Additional works of MS manifold including interconnection in beetween CWR and pump house and etc allied works at Samlya H/W under Samlya W/S Scheme under RCFA Division-I PHe Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000571/2023-2024 | 2869/RCD-I | 06/10/2023 | 21/10/2023 | MAA ENTERPRISE | 6.41 | 6.16 | 95.99 | 100
7 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART II (ZONE 4A) UNDER RCFA DIVISION-I PHE DTE. | SM/12219 | Augmentation | Laying of distribution system at Khottamdihi village including FHTC works under Kendra Khottamdihi W/S Scheme under RCFA Div-I, PHE dte. | Assistant Engineer 2 | Junior Engineer | ORD/000399/2022-2023 | 2643/RCDI | 28/10/2022 | 10/06/2023 | JAYANTA DATTA | 100 | 0 | 0 | 100
8 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART II (ZONE 4A) UNDER RCFA DIVISION-I PHE DTE. | SM/12219 | Augmentation | Acceptance cum work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-4A) (Part-B)(Sl No. 12) | Assistant Engineer 2 | Junior Engineer | ORD/000870/2022-2023 | 1116/RCD-I | 23/03/2023 | 21/06/2023 | BABA LOKNATH ENTERPRISE | 71.02 | 48.63 | 68.48 | 80
9 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART II (ZONE 4A) UNDER RCFA DIVISION-I PHE DTE. | SM/12219 | Augmentation | Acceptance cum work order Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-4A) (Part-C) | Assistant Engineer 2 | Junior Engineer | ORD/000868/2022-2023 | 1118/RCD-I | 23/03/2023 | 21/06/2023 | UNITED CONSTRUCTION | 81.57 | 75.71 | 92.81 | 90
10 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART II (ZONE 4A) UNDER RCFA DIVISION-I PHE DTE. | SM/12219 | Augmentation | Acceptance cum work order Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-4A) (Part-E) | Assistant Engineer 2 | Junior Engineer | ORD/000869/2022-2023 | 1120/RCD-I | 23/03/2023 | 31/05/2025 | JAYANTA DATTA | 91.65 | 20.35 | 22.21 | 70
11 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART II (ZONE 4A) UNDER RCFA DIVISION-I PHE DTE. | SM/12219 | Augmentation | Formal work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-4A) (Part-A). | Assistant Engineer 2 | Junior Engineer | ORD/000041/2023-2024 | 1604/RCD I | 25/04/2023 | 22/10/2023 | PINKI ENTERPRISE | 115.02 | 87.84 | 76.37 | 85
12 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART II (ZONE 4A) UNDER RCFA DIVISION-I PHE DTE. | SM/12219 | Augmentation | Acceptance cum work order Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-4A) (Part-D) (Sl No. 14) | Assistant Engineer 2 | Junior Engineer | ORD/000054/2023-2024 | 1707/ RCD I | 03/05/2023 | 01/08/2023 | MD. JAWED KHAN | 69.87 | 49.08 | 70.25 | 80
13 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART II (ZONE 4A) UNDER RCFA DIVISION-I PHE DTE. | SM/12219 | Augmentation | Acceptance cum work order for Construction of Chlorine Room (Size 4.1 m x 3.5 m out to out) at Shankarpur OHR Site for Augmentation of RCFA part-II (Zone-4A and 4B) Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 27) | Assistant Engineer 2 | Junior Engineer,Junior Engineer 11 | ORD/000904/2022-2023 | 1171/RCD I | 24/03/2023 | 26/12/2023 | RANJIB GHATAK | 4.61 | 0 | 0 | 100
14 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART II (ZONE 4A) UNDER RCFA DIVISION-I PHE DTE. | SM/12219 | Augmentation | Continuation work order for Providing FHTC through Retrofitting at Bhaluka & Sonepur Bazari under Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. under JJM (RCFA Part-II) | Assistant Engineer 2 | Junior Engineer | ORD/000825/2022-2023 | 801/RCD-I | 06/03/2023 | 05/04/2023 | MACHINO TECHNO | 67.77 | 65.09 | 96.05 | 100
15 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART II (ZONE 4A) UNDER RCFA DIVISION-I PHE DTE. | SM/12219 | Augmentation | Acceptance cum work order for Approach road and others necessary allied works at Front Gate to village road for Shankarpur OHR Site (Zone-4A and 4B) Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No 28) | Assistant Engineer 2 | Junior Engineer,Junior Engineer 11 | ORD/000908/2022-2023 | 1172/RCD I | 24/03/2023 | 23/05/2023 | RANJIB GHATAK | 3.78 | 3.7 | 97.81 | 100
16 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART II (ZONE 4A) UNDER RCFA DIVISION-I PHE DTE. | SM/12219 | Augmentation | Acceptance cum work order for Health assessment of existing OHR of Searsole (900 Cum) and ancillary structures conducting Non-Destructive Test and thorough visual observation under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000538/2023-2024 | 3024/RCD-1 | 16/10/2023 | 31/10/2023 | RISHAN ENGINEERING CONSULTANCY | 4.95 | 4.95 | 100 | 100
17 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART II (ZONE 4A) UNDER RCFA DIVISION-I PHE DTE. | SM/12219 | Augmentation | Acceptance cum Work Order for Additional work for laying MS pipe and allied works including adopting trench less technology b(e.g. Jack Pushing Method etc) of 02 (Two) nos location at Sankarpur (near Footbal ground ) and Shankarpur GP office under Augmentation of RCFA Part-II (Zone-4A) PWSS (Part-C ) under RCFA Division-I PHE Dte. (2nd Call) | Assistant Engineer 2 |  | ORD/000913/2023-2024 | 213/RCD-I | 29/01/2024 | 13/02/2024 | UNITED CONSTRUCTION | 13.08 | 11.74 | 89.77 | 100
18 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION PWSS OF RCFA PART II (ZONE 4A) UNDER RCFA DIVISION-I PHE DTE. | SM/12219 | Augmentation | Acceptance cum Work Order for Allied work for bridge, road and other allied work at Amritnagar Zone-I under RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000965/2023-2024 | 508/RCD-I | 12/02/2024 | 13/03/2024 | MACHINO TECHNO | 81.93 | 81.91 | 99.97 | 100
Total | [13 empty] | 737.6 | 468.89 | 63.57