## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS Of RCFA Part-II (Zone-18) Under RCFA Division-I Phe Dte. | SM/12220 | Augmentation | Acceptance cum Work Order for Construction of Chlorine Room of size (4.50 x 3.50 M) at (Zone-18) of Raniganj Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman. (Sl No. 32) | Assistant Engineer 2 | Junior Engineer | ORD/000914/2022-2023 | 1176/RCD-1 | 24/03/2023 | 22/06/2023 | GOPAL CONSTRUCTION | 4.61 | 0 | 0 | 0
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS Of RCFA Part-II (Zone-18) Under RCFA Division-I Phe Dte. | SM/12220 | Augmentation | Acceptance cum work order for Additional works of extra cutting Laterate/sand stone of distribution network for RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Zone-18) | Assistant Engineer 2 | Junior Engineer | ORD/000466/2023-2024 | 2872/RCD-1 | 06/10/2023 | 04/01/2024 | SWATI CORPORATION | 21.83 | 21.48 | 98.39 | 100
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS Of RCFA Part-II (Zone-18) Under RCFA Division-I Phe Dte. | SM/12220 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000037/2023-2024 | 2937/RCD-I | 11/10/2023 | 11/10/2023 | Resource Division | 6.78 | 0 | 0 | 0
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS Of RCFA Part-II (Zone-18) Under RCFA Division-I Phe Dte. | SM/12220 | Augmentation | Sub Soil Investigation for 450 cum capacity RCC Over Head Reservoir at (Zone-18) of Raniganj Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000557/2022-2023 | 3351/RCDI | 23/12/2022 | 30/12/2022 | MOYTEC | 0.49 | 0.49 | 100 | 100
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS Of RCFA Part-II (Zone-18) Under RCFA Division-I Phe Dte. | SM/12220 | Augmentation | Acceptance cum work order for Additional works of concrete dismantling & re concreting with other allied works at distribution networks including additional laying of pipe line for RCFA Part-II Piped Water Supply Scheme under RCFA Div-I PHE Dte. (Zone-18) | Assistant Engineer 2 | Junior Engineer | ORD/000493/2023-2024 | 2885/RCD-1 | 06/10/2023 | 05/11/2023 | SWATI CORPORATION | 73.24 | 60.8 | 83.01 | 100
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS Of RCFA Part-II (Zone-18) Under RCFA Division-I Phe Dte. | SM/12220 | Augmentation | Acceptance cum work order for Construction of Godown for stacking of Cholorine at Searsole Head Work site of Augmentation PWSS Of RCFA Part-II (Zone-18) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000980/2023-2024 | 466/RCD-1 | 12/02/2024 | 12/05/2024 | M/S MONDAL ENTERPRISE | 9.5 | 9.27 | 97.59 | 100
7 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS Of RCFA Part-II (Zone-18) Under RCFA Division-I Phe Dte. | SM/12220 | Augmentation | Formal work order for distribution network for RCFA Part-II Piped water Supply Scheme including FHTC & allied work under RCFA Div-I, PHE Dte.(Zone-18) | Assistant Engineer 2,Assistant Engineer 3 | Junior Engineer,Junior Engineer 12 | ORD/000816/2022-2023 | 998/RCDI | 22/03/2023 | 01/01/2026 | SWATI CORPORATION | 454.37 | 284.71 | 62.66 | 100
8 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS Of RCFA Part-II (Zone-18) Under RCFA Division-I Phe Dte. | SM/12220 | Augmentation | Formal work order for Construction of 450 cum capacity 20 mtr. staging height RCC Over Head Reservoir (Pipe connection and cost of pipes. specials at Raniganj Block (Zone-18) for Augmentation of RCFA Part-II piped Water Supply Scheme under RCFA Division-I PHe Dte. in the District of Paschim Bardhaman. Ref Drawing No. PC-I/OHR/04/2022 (Sheet No. 1 & 2) | Assistant Engineer 2 | Junior Engineer | ORD/000154/2023-2024 | 1901/RCD-I | 09/06/2023 | 09/06/2024 | SRI KRISHNA ENTERPRISE | 130.86 | 39.26 | 30 | 20
Total | [13 empty] | 701.67 | 416 | 59.29