## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS Of RCFA Part-II (Zone-18) Under RCFA Division-I Phe Dte. | SM/12220 | Augmentation | Sub Soil Investigation for 450 cum capacity RCC Over Head Reservoir at (Zone-18) of Raniganj Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000557/2022-2023 | 3351/RCDI | 23/12/2022 | 30/12/2022 | MOYTEC | 0.49 | 0.49 | 100 | 100
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS Of RCFA Part-II (Zone-18) Under RCFA Division-I Phe Dte. | SM/12220 | Augmentation | Acceptance cum Work Order for Construction of Chlorine Room of size (4.50 x 3.50 M) at (Zone-18) of Raniganj Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman. (Sl No. 32) | Assistant Engineer 2 | Junior Engineer | ORD/000914/2022-2023 | 1176/RCD-1 | 24/03/2023 | 22/06/2023 | GOPAL CONSTRUCTION | 4.61 | 0 | 0 | 0
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS Of RCFA Part-II (Zone-18) Under RCFA Division-I Phe Dte. | SM/12220 | Augmentation | Formal work order for distribution network for RCFA Part-II Piped water Supply Scheme including FHTC & allied work under RCFA Div-I, PHE Dte.(Zone-18) | Assistant Engineer 2,Assistant Engineer 3,Assistant Engineer 8 | Junior Engineer,Junior Engineer 12 | ORD/000816/2022-2023 | 998/RCDI | 22/03/2023 | 01/01/2027 | SWATI CORPORATION | 454.37 | 284.71 | 62.66 | 100
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS Of RCFA Part-II (Zone-18) Under RCFA Division-I Phe Dte. | SM/12220 | Augmentation | Formal work order for Construction of 450 cum capacity 20 mtr. staging height RCC Over Head Reservoir (Pipe connection and cost of pipes. specials at Raniganj Block (Zone-18) for Augmentation of RCFA Part-II piped Water Supply Scheme under RCFA Division-I PHe Dte. in the District of Paschim Bardhaman. Ref Drawing No. PC-I/OHR/04/2022 (Sheet No. 1 & 2) | Assistant Engineer 2 | Junior Engineer | ORD/000154/2023-2024 | 1901/RCD-I | 09/06/2023 | 09/06/2024 | SRI KRISHNA ENTERPRISE | 130.86 | 39.26 | 30 | 20
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS Of RCFA Part-II (Zone-18) Under RCFA Division-I Phe Dte. | SM/12220 | Augmentation | Sub Soil Investigation for 900 cum capacity RCC Over Head Reservoir at (Zone-VII) of Salanpur Block for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000380/2023-2024 | 2553/RCD-I | 31/08/2023 | 07/09/2023 | SINGHA ROY & CO. | 0.98 | 0.98 | 100 | 100
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS Of RCFA Part-II (Zone-18) Under RCFA Division-I Phe Dte. | SM/12220 | Augmentation | Acceptance cum work order for Laying & pushing of 600 mm dia RCC Hume pipe (NP3) by adopting trench less technology (e.g. Jack pushing method), MS water carrier pipe and other allied works at distribution network for RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Zone-18) | Assistant Engineer 2 | Junior Engineer | ORD/000473/2023-2024 | 2862/RCD-I | 06/10/2023 | 02/04/2025 | SWATI CORPORATION | 44.91 | 39.27 | 87.44 | 100
7 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS Of RCFA Part-II (Zone-18) Under RCFA Division-I Phe Dte. | SM/12220 | Augmentation | Acceptance cum work order for Additional works of extra cutting Laterate/sand stone of distribution network for RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Zone-18) | Assistant Engineer 2 | Junior Engineer | ORD/000466/2023-2024 | 2872/RCD-1 | 06/10/2023 | 04/01/2024 | SWATI CORPORATION | 21.83 | 21.48 | 98.39 | 100
8 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS Of RCFA Part-II (Zone-18) Under RCFA Division-I Phe Dte. | SM/12220 | Augmentation | Acceptance cum work order for Additional works of concrete dismantling & re concreting with other allied works at distribution networks including additional laying of pipe line for RCFA Part-II Piped Water Supply Scheme under RCFA Div-I PHE Dte. (Zone-18) | Assistant Engineer 2 | Junior Engineer | ORD/000493/2023-2024 | 2885/RCD-1 | 06/10/2023 | 05/11/2023 | SWATI CORPORATION | 73.24 | 60.8 | 83.01 | 100
9 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS Of RCFA Part-II (Zone-18) Under RCFA Division-I Phe Dte. | SM/12220 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000037/2023-2024 | 2937/RCD-I | 11/10/2023 | 11/10/2023 | Resource Division | 6.78 | 0 | 0 | 0
10 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS Of RCFA Part-II (Zone-18) Under RCFA Division-I Phe Dte. | SM/12220 | Augmentation | Acceptance cum work order for Construction of Godown for stacking of Cholorine at Searsole Head Work site of Augmentation PWSS Of RCFA Part-II (Zone-18) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000980/2023-2024 | 466/RCD-1 | 12/02/2024 | 12/05/2024 | M/S MONDAL ENTERPRISE | 9.5 | 9.27 | 97.59 | 100
11 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS Of RCFA Part-II (Zone-18) Under RCFA Division-I Phe Dte. | SM/12220 | Augmentation | Acceptance cum work order for Additional work related to Rising Main Part-A for concrete cutting and road restoration at Ethora village including interconnection and Barabani OHR including Bituminous road cutting etc allied works under Improvement of RCFA Part-I PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000978/2023-2024 | 465/RCD-1 | 12/02/2024 | 13/03/2024 | M/S MONDAL ENTERPRISE | 25.64 | 24.96 | 97.36 | 100
12 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS Of RCFA Part-II (Zone-18) Under RCFA Division-I Phe Dte. | SM/12220 | Augmentation | Acceptance cum Work Order for Additional works of extra cutting laterate / sandstone of distribution network for RCFA Part-II Piped Water Supply Scheme under RCFA Div-I PHE Dte. (Zone-18) | Assistant Engineer 2 |  | ORD/000944/2023-2024 | 489/RCD-I | 12/02/2024 | 28/03/2024 | TARA CONSTRUCTION | 9.36 | 9.32 | 99.53 | 100
13 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS Of RCFA Part-II (Zone-18) Under RCFA Division-I Phe Dte. | SM/12220 | Augmentation | Acceptance cum work order for Carring, stacking of different dia (80 mm to 700 mm dia) C.I./D.I. specials, valves grannual chlorine etc including surface dressing, road base at Searsole Stack yard under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000976/2023-2024 | 463/RCD-1 | 12/02/2024 | 03/03/2024 | M/S MONDAL ENTERPRISE | 10.95 | 10.91 | 99.59 | 100
14 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS Of RCFA Part-II (Zone-18) Under RCFA Division-I Phe Dte. | SM/12220 | Augmentation | Formal work order for Acceptance order for Construction of 700 cum capacity 20 mtr staging height RCC Over Head Reservior (pipe connection and cost of pipes, specials and land devlopment with approached road including internal drain at Mohishila OHR within Asansol Municipal Corporation area under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001078/2023-2024 | 805/RCD-I | 13/03/2024 | 09/09/2024 | GITA CONSTRUCTION | 180.36 | 95.61 | 53.01 | 82
Total | [13 empty] | 973.87 | 597.05 | 61.31