## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone - 9 A) | SM/12221 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000024/2023-2024 | 2951/RCD-I | 11/10/2023 | 11/10/2023 | Resource Division | 6.78 | 0 | 0 | 0
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone - 9 A) | SM/12221 | Augmentation | Acceptance cum Work Order for Additional work for distribution network for Augmentation of RCFA Part-II Piped Water Supply Scheme within command area of Zone-9A(Segment-III) under RCFA Division-I. PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001176/2023-2024 | 1016/RCD-I | 16/03/2024 | 30/04/2024 | UNITED CONSTRUCTION | 35.76 | 0 | 0 | 70
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone - 9 A) | SM/12221 | Augmentation | Formal work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I Phe Dte. (Zone-9A) | Assistant Engineer 2 | Junior Engineer | ORD/000073/2023-2024 | 1760/RCD I | 16/05/2023 | 01/09/2025 | ASHA CONSTRUCTION | 345.86 | 0 | 0 | 80
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone - 9 A) | SM/12221 | Augmentation | Acceptance cum Work Order for Repairing of Boundary Wall for 45 mtr at Chora OHR Site of RCFA Part-II (Zone- 9, 9A and 9B) PWSS Block-Pandabeswar under RCFA Division-I PHE Dte. (Sl No. 01) | Assistant Engineer 2 | Junior Engineer | ORD/000916/2022-2023 | 1144/RCD-1 | 24/03/2023 | 08/04/2023 | N.R. CONSTRUCTION | 4.61 | 0 | 0 | 100
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone - 9 A) | SM/12221 | Augmentation | Acceptance cum work order for Balance work and crossing road by trenchless technology in different site connection with distribution network including FHTC & allied work at Andal Block of Augmentation PWSS RCFA Part-II (Zone-9A) under RCFA Division-I PHE, Dte | Assistant Engineer 2 | Junior Engineer | ORD/000193/2024-2025 | 2420/RCD-I | 26/09/2024 | 10/11/2024 | MACHINO TECHNO | 69.72 | 0 | 0 | 100
Total | [13 empty] | 462.72 | 0 | 0