## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone - 9) | SM/12222 | Augmentation | Acceptance cum work order for Repair and renovation works of one no RCC Elevated Reservoir of capacity 1362 cum at Chora for RCFA Part-II (Zone-9, 9A & 9B) Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 12) | Assistant Engineer 2 | Junior Engineer | ORD/000844/2022-2023 | 1078/RCD I | 23/03/2023 | 18/12/2023 | ASHA CONSTRUCTION | 17.06 | 7.44 | 43.59 | 0
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone - 9) | SM/12222 | Augmentation | Acceptance cum work order for Construction of Store Room at Chora of Pandabeswar Block for Augmentation of RCFA Part-II (Zone-9) Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman (Sl No. 25) | Assistant Engineer 2 | Junior Engineer | ORD/000894/2022-2023 | 1168/RCD I | 24/03/2023 | 22/06/2023 | M/S S.K. ENTERPRISE | 4.61 | 0 | 0 | 0
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone - 9) | SM/12222 | Augmentation | Acceptance cum work order for Laying of different dia HDPE pipe line at Pure Jambad Hattala Zone, Real Jambad under Bahula (CT) (Jl No. 30, Block-Pandabeswar under Improvement of RCFA Part-II Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000593/2022-2023 | 3299/RCD I | 20/12/2022 | 18/02/2023 | GITA CONSTRUCTION | 78.64 | 21.9 | 27.85 | 90
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone - 9) | SM/12222 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000023/2023-2024 | 2949/RCD-I | 11/10/2023 |  | Resource Division | 6.78 | 0 | 0 | 0
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone - 9) | SM/12222 | Augmentation | Acceptance cum work order for Distribution Network for RCFA Part-II Piped Water Supply Scheme including FHTC & allied works under RCFA Division-I PHE Dte.(Zone-9) Parshkol (Part-B)(Sl No. 16) | Assistant Engineer 2 | Junior Engineer | ORD/000846/2022-2023 | 1081/RCD I | 23/03/2023 | 21/06/2023 | ALOKESH BANERJEE | 40.44 | 13.78 | 34.08 | 35
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone - 9) | SM/12222 | Augmentation | Acceptance cum work order for Laying of 110 mm dia and 90 mm dia HDPE pipe line including chokage cleaning and other allied works of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. (Part-A) | Assistant Engineer 2 | Junior Engineer | ORD/000663/2023-2024 | 3432/RCD-1 | 24/11/2023 | 24/12/2023 | JAI MAHARAJ ENTERPRISE | 6.86 | 3.43 | 50 | 100
7 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone - 9) | SM/12222 | Augmentation | Acceptance cum work order for 2 nos Emergency repairing work of 450mm dia rising main at Basu Vata and Jamdoba under RCFA Part-II water supply scheme under RCFA Div-I, PHE Dte | Assistant Engineer 2 | Junior Engineer | ORD/000610/2023-2024 | 3376/RCD-I | 21/11/2023 | 06/12/2023 | KHEPI MAA TRADERS | 2.16 | 1.08 | 50 | 100
8 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone - 9) | SM/12222 | Augmentation | Emergency repairing work 750 mm dia Rising main at Kalyaneswari Dendua road under RCFA Part-I W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000736/2023-2024 | Camp_02_Kalyaneswari_AE_I | 06/10/2023 | 21/10/2023 | MD AAMIR KHAN | 2.75 | 1.34 | 48.52 | 100
9 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone - 9) | SM/12222 | Augmentation | Acceptance cum work order for Construction of Chlorine Room of size (4.50 x 3.50 M) at Chora of Pandabeswar Block for Augmentation of RCFA Part-II (Zone-9) Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman (2nd Call) | Assistant Engineer 2 |  | ORD/000915/2023-2024 | 212/RCD-I | 29/01/2024 | 28/04/2024 | KALYAN DAWN | 4.57 | 0 | 0 | 0
10 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone - 9) | SM/12222 | Augmentation | Acceptance cum work order for Construction of Pump House at Dendua for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000696/2022-2023 | 487/RCDI | 03/02/2023 | 04/05/2023 | D.S. ENTERPRISE | 30.3 | 11.76 | 38.81 | 77
11 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone - 9) | SM/12222 | Augmentation | Sub Soil Investigation for 900 cum capacity RCC Over Head Reservoir at (Zone-XI) of Barabani Block for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000973/2022-2023 | 3148/RCD-I | 12/12/2022 | 19/12/2022 | AMAR CONSTRUCTION | 0.98 | 0.49 | 50 | 100
12 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone - 9) | SM/12222 | Augmentation | Formal work order for Distribution Network for RCFA Prt-II Pipe Water Supply scheme including FHTC & allied ork under RCFA Division-I PHE Dte. (Zone-9) Parshkol (Part-A) | Assistant Engineer 2 | Junior Engineer | ORD/000038/2023-2024 | 1607/RCD I | 25/04/2023 | 24/07/2023 | MD AAMIR KHAN | 107.46 | 25.2 | 23.45 | 100
13 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone - 9) | SM/12222 | Augmentation | Way leave / Track crossing proposal with application ID : ER-ASN-2024-WL-08 at Andal under Augmentation of RCFA Part-II (Zone-9) under RCFA Division-I PHE Dte |  |  | BILL/00112/2024-2025 | 46/24-25 | 20/05/2024 |  | EASTERN RAILWAY | 4.81 | 0 | 0 | 0
14 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone - 9) | SM/12222 | Augmentation | Acceptence cum work order for Dedicated line towards Paharpur village, Kallya village and necessary repairing including supply of valve construction of valve chamber etc. within Distribution Network of Dabor OHR under Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000395/2023-2024 | 2577/RCD-I | 07/09/2023 | 22/09/2023 | DHRUBA ENTERPRISE | 9.05 | 3.65 | 40.33 | 100
15 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone - 9) | SM/12222 | Augmentation | Way leave / Track crossing proposal with application ID : ER-ASN-2024-WL-10 under Augmentation of RCFA Part-II (Zone-9) under RCFA Division-I PHE Dte |  |  | BILL/00155/2024-2025 | 68/24-25 | 30/05/2024 |  | EASTERN RAILWAY | 4.73 | 0 | 0 | 0
16 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone - 9) | SM/12222 | Augmentation | Acceptance cum work order for Protecting apparatus of collecting main including other allied works under RCFA Part-II PWSS (Zone-9) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000014/2024-2025 | 1516/RCD-I | 14/06/2024 | 29/06/2024 | MAKALI ENGINEERING CORPORATION | 99.5 | 74.54 | 74.91 | 100
17 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone - 9) | SM/12222 | Augmentation | Acceptance cum work order for Supply of different dia Sluice valve, including C.I. / D.I. Specials to the Searsole Store of RCFA Part-II (Zone-9) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000015/2024-2025 | 1518/RCD-I | 14/06/2024 | 29/06/2024 | MAKALI ENGINEERING CORPORATION | 77.57 | 38.78 | 50 | 100
18 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone - 9) | SM/12222 | Augmentation | Acceptance cum work order for Allied work of laying dia HDPE Pipe line and allied works at Raghunathchak, Raniganj Chati, Baliapur and adjacent area under Zone-9 for Augmentation of RCFA Part-II Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000517/2023-2024 | 2868/RCD-I | 06/10/2023 | 05/11/2023 | MACHINO TECHNO | 89.05 | 11.55 | 12.97 | 50
Total | [13 empty] | 587.32 | 214.94 | 36.6