## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-2) Block - Andal, Dist - Paschim Bardhaman | SM/12223 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000017/2023-2024 | 2958/RCD-I | 11/10/2023 | 11/10/2023 | Resource Division | 6.78 | 0 | 0 | 0
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-2) Block - Andal, Dist - Paschim Bardhaman | SM/12223 | Augmentation | Acceptance cum work order for Balance work for laying MS pipe and allied works including Adopting trench less technology (e.g. Jack Pushing Method etc) for crossing of important roads (2 nos location at zone-4A) of Augmentation PWSS of RCFA Part-II (Zone-2) under RCFA Division-I, P.H.E. Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000110/2024-2025 | 2132/RCD-I | 27/08/2024 | 26/09/2024 | UNITED CONSTRUCTION | 39.74 | 32.91 | 82.83 | 100
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-2) Block - Andal, Dist - Paschim Bardhaman | SM/12223 | Augmentation | Sub Soil Investigation for 900 cum capacity RCC Over Head Reservoir at (Zone-2) of Ondal Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000564/2022-2023 | 3358/RCDI | 23/12/2022 | 30/12/2022 | MOYTEC | 0.49 | 0.48 | 98.32 | 100
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-2) Block - Andal, Dist - Paschim Bardhaman | SM/12223 | Augmentation | Acceptance cum work order for Providing FHTC through Retrofitting at Pathakpara Block Anda & Pandabeswar of Ukhra under Augmentation of RCFA Part-II (Zone-2) PWSS under RCFA Division-I PHE Dte. (Part-C) | Assistant Engineer 2 | Junior Engineer | ORD/000680/2022-2023 | 367/RCDI | 30/01/2023 | 01/03/2023 | JAI MAHARAJ ENTERPRISE | 5.62 | 5.2 | 92.55 | 100
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-2) Block - Andal, Dist - Paschim Bardhaman | SM/12223 | Augmentation | Acceptance cum work order for Repairing of damaged collecting main in river Damodar rising main to D.P Colony OHR and allied works of DP colony W/S scheme under RCFA Division -I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000611/2023-2024 | 3370/RCD-1 | 21/11/2023 | 06/12/2023 | DURGA DAS MONDAL | 4.98 | 4.42 | 88.74 | 100
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-2) Block - Andal, Dist - Paschim Bardhaman | SM/12223 | Augmentation | Acceptance cum work order for Laying of different dia HDPE pipe line towards Teli Para (Sansad -XIV) under Ukhra area Block- Andal & Pandabswar of Augmentation of RCFA Part-II (Zone-2) Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer 11 | ORD/000559/2023-2024 | 3188/RCD-I | 01/11/2023 | 16/11/2023 | NILIMA CONSTRUCTION | 2.49 | 2.3 | 92.53 | 100
7 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-2) Block - Andal, Dist - Paschim Bardhaman | SM/12223 | Augmentation | Acceptance cum work order for Additional for supplying & laying M.S pipe, Supplying specials for Interconnection work for Improvement of RCFA Part-I for Augmentation of RCFA Part-II (Zone-2) PWSS within command area of Zone-VIII under RCFA Div-I, PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000085/2024-2025 | 2110/RCD-I | 27/08/2024 | 21/09/2024 | TARA CONSTRUCTION | 13.73 | 13.21 | 96.2 | 100
8 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-2) Block - Andal, Dist - Paschim Bardhaman | SM/12223 | Augmentation | Payment of Way leave Plan & Survey charges for track crossing proposal with Application ID ER-ASN2024-WL-18 dt 15.04.2024 |  |  | BILL/00012/2024-2025 | 11/24-25 | 24/04/2024 | 24/04/2024 | EASTERN RAILWAY | 0.25 | 0 | 0 | 0
9 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-2) Block - Andal, Dist - Paschim Bardhaman | SM/12223 | Augmentation | PAYMENT OF WALEAVE PLAN & SURVEY CHARGES ER-ASN-2024-WL-10 |  |  | BILL/00002/2024-2025 | 03/24-25 | 18/04/2024 | 18/04/2024 | EASTERN RAILWAY | 0.08 | 0 | 0 | 0
10 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-2) Block - Andal, Dist - Paschim Bardhaman | SM/12223 | Augmentation | Formal work order for Construction of 900 cum capacity 20 mtr staging height RCC Over Head Reservoir (pipe connection and cost of pipes, specials at Amritnagar Zone-II Piped Water Supply Scheme under RCFA Division-I, PHE Dte. in the District of Paschim Bardhaman. | Assistant Engineer 2 | Junior Engineer | ORD/000157/2023-2024 | 1902/RCD-I | 09/06/2023 | 09/02/2024 | M/S SANTANU PALIT & CO. | 182.7 | 54.81 | 30 | 70
11 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-2) Block - Andal, Dist - Paschim Bardhaman | SM/12223 | Augmentation | Formal Work Order for Additional supplying laying 280 mm & 225 mm dia HDPE pipe line for Improvement of RCFA Part-I Water Supply Scheme within command area of Zone-VIII under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000311/2023-2024 | 2384/RCD-I | 07/08/2023 | 06/10/2023 | SWATI CORPORATION | 124.64 | 97.3 | 78.07 | 80
12 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-2) Block - Andal, Dist - Paschim Bardhaman | SM/12223 | Augmentation | Acceptance cum work order for Distribution of pipe line from Alinagar OHR to Khattardihi Village via Minsa Das Para including Laying & Pushing by adopting trench less technology (e.g, Jack Pushing Method etc) & other allied work under Shyamla GP under Augmentation PWSS of RCFA Part-II (Zone-2) Block - Andal, Dist - Paschim Bardhaman under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000515/2024-2025 | 115/RCD-I | 08/01/2025 | 22/02/2025 | SILPO UDYOG ENGINEERING CONSTRUCTIONS | 47.67 | 9.81 | 20.57 | 80
13 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-2) Block - Andal, Dist - Paschim Bardhaman | SM/12223 | Augmentation | Acceptance cum work order for Laying of different dia HDPE Pipe Line including concrete cutting, mending etc allied works towards Pathakpara (Sansad-XV) Block Andal & Pandabeswar of Ukhra under Additional works under Ukhra & its adjoining mouzas water supply scheme under RCFA Division-I PHE Dte. |  |  | ORD/000693/2022-2023 | 382/RCD I | 30/01/2023 | 14/02/2023 | B.T.M CONCERN | 20.71 | 20.34 | 98.19 | 100
14 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-2) Block - Andal, Dist - Paschim Bardhaman | SM/12223 | Augmentation | Formal work order for Distribution Network & allied work at Ondal Block of RCFA Part-II (Zone-II) Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000028/2023-2024 | 1618/RCD I | 25/04/2023 | 01/05/2024 | M/S UNIT CONSTRUCTION | 231.44 | 209.84 | 90.67 | 100
15 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-2) Block - Andal, Dist - Paschim Bardhaman | SM/12223 | Augmentation | Acceptance cum work order Laying & Pushing of 600 mm dia RCC (NP3) Hume Pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at 01 (One) location on Salanpur ¿ Khuidica road and supplying and laying MS pipe near culvert and gas line including ancillary work within command area of Zone-I (Dendua OHR Site) Part-C under Improvement of RCFA Part-I PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000220/2023-2024 | 2225/RCD-I | 17/07/2023 | 01/04/2024 | DAS & CHAKRABORTY | 15.47 | 12.05 | 77.92 | 100
16 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-2) Block - Andal, Dist - Paschim Bardhaman | SM/12223 | Augmentation | Formal Work order for construction of 900 cum capacity 20 mtrs staging height RCC Over Reservoir (Pipe connection and cost of pipes, specials at Ondal Block (Zone-2) for Augmentation of RCFA Part-II Piped Water Supply Scheme including Soil Investigation and chlorine Room (4.50 x 3.50) under RCFA Division-I PHE Dte. In District Paschim Bardhaman. | Assistant Engineer 2 | Junior Engineer | ORD/000098/2023-2024 | 1846/RCD-I | 31/05/2023 | 31/05/2024 | M/S CHANDI CHARAN ROY | 199.25 | 199.25 | 100 | 90
17 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-2) Block - Andal, Dist - Paschim Bardhaman | SM/12223 | Augmentation | Acceptance cum work order for Supplying, aligning & Laying of different dia HDPE pipe line and allied works for dedicated line to Chotkara village and Satta under Chotkara Kanskuli W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000579/2023-2024 | 2989-RCD-I | 12/10/2023 | 27/10/2023 | SHREE DURGA ENTERPRISE | 5.85 | 5.83 | 99.68 | 100
18 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-2) Block - Andal, Dist - Paschim Bardhaman | SM/12223 | Augmentation | Acceptance cum work order for Additional works for Laying & pushing of 600mm dia RCC hume pipe (NP3) by adopting trench less technology (e.g Jack pushing method) , MS water carrier pipe and other allied works at different location (Node point:- 226-232, 289-292, 441-442, 69-76, 63-64, 256-272 ) of distribution network for Augmentation PWSS of RCFA Part-II (Zone-2) under RCFA Div-I, PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000089/2024-2025 | 2114/RCD-I | 27/08/2024 | 26/10/2024 | SWATI CORPORATION | 35.82 | 0 | 0 | 100
Total | [13 empty] | 937.72 | 667.77 | 71.21