## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-I) Block-Andal, Dist-Paschim Bardhaman | SM/12224 | Augmentation | Formal work order for Distribution Network including FHTC & allied work at Ondal Block of RCFA Part-II (Zone-I) Pipe Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000037/2023-2024 | 1609/RCD I | 25/04/2023 | 24/07/2023 | GITA CONSTRUCTION | 245.36 | 156.7 | 63.87 | 65
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-I) Block-Andal, Dist-Paschim Bardhaman | SM/12224 | Augmentation | Formal Work Order for Construction of Sub-station, CWR and Pump House including toilet at Ethora under Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000173/2023-2024 | 2009/RCD-I | 26/06/2023 | 24/10/2023 | D.S. ENTERPRISE | 122.25 | 43.74 | 35.78 | 40
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-I) Block-Andal, Dist-Paschim Bardhaman | SM/12224 | Augmentation | Acceptance cum work order for Laying & Pushing of 600 mm dia RCC (NP3) Hume Pipe by adopting trench less technology (e.g. Jack Pushing Method etc) 02 (Two) Nos. Near Dakshin Khanda Dharmaraj Tala and Khandra BPHC under Ondal Block under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000656/2023-2024 | 3428/RCD-1 | 24/11/2023 | 09/12/2023 | UNITED CONSTRUCTION | 18.39 | 17.65 | 95.99 | 100
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-I) Block-Andal, Dist-Paschim Bardhaman | SM/12224 | Augmentation | Acceptance cum work order for Construction of Guard Wall arrangement to project 450 mm dia the Rising Main at Jagrdih, Gopal area ASTA Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000601/2023-2024 | 3283/RCD-I | 08/11/2023 | 23/11/2023 | SIMA ENTERPRISE | 6.12 | 6.11 | 99.73 | 100
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-I) Block-Andal, Dist-Paschim Bardhaman | SM/12224 | Augmentation | Urgent Basis rapairing of 50 sqmm x 4 core Al Armoured Damaged cable line street Light Providing of FHTC Pipe line near Andal More to Culvert (Bridge) under Dignala OHR dite under Andal W/s scheme under RCFA Division-I, PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000560/2023-2024 | SpotNit_Camp_02/AndalMore | 09/10/2023 | 19/10/2023 | T R ENTERPRISE | 6.17 | 6.16 | 99.84 | 100
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-I) Block-Andal, Dist-Paschim Bardhaman | SM/12224 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000015/2023-2024 | 2935/RCD-I | 11/10/2023 | 11/10/2023 | Resource Division | 6.78 | 0 | 0 | 0
7 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-I) Block-Andal, Dist-Paschim Bardhaman | SM/12224 | Augmentation | Acceptance cum Work Order for Additional work for concrete cutting and concreting and distribution network for RCFA Part-II PWSS including FHTC and allied work under RCFA Division-I PHE Dte. Zone-12B (Segement 2) | Assistant Engineer 2 |  | ORD/001170/2023-2024 | 1009/RCD-I | 16/03/2024 | 31/03/2024 | M/S SINGH & KONAR CONSTRUCTION | 31.75 | 0 | 0 | 0
8 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-I) Block-Andal, Dist-Paschim Bardhaman | SM/12224 | Augmentation | Acceptance cum Work Order for Additional work for laying pipeline and allied works from Kelejora Health Centre Crossing towards Barabani Village (ICML Road) withthin Zone XIII of Augmentation RCFA Part-II (Zone-I) PWSS under RCFA Division-I PHE Dte | Assistant Engineer 2 | Junior Engineer | ORD/001171/2023-2024 | 1011/RCD-I | 16/03/2024 | 31/08/2024 | PINKI ENTERPRISE | 31.63 | 0 | 0 | 100
9 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-I) Block-Andal, Dist-Paschim Bardhaman | SM/12224 | Augmentation | Acceptance cum Work Order for Additional supplying laying 90 mm dia, HDPE pipe line at Tentul Tala and Damalia Village including repairing different dia pipe line in different places in Tirat Mouza within Amritnagar Distribution Zone under Augmentation Part-II W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001139/2023-2024 | 937/RCD-I | 15/03/2024 | 30/03/2024 | RUBY CONSTRUCTION | 6.88 | 6.85 | 99.54 | 100
10 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-I) Block-Andal, Dist-Paschim Bardhaman | SM/12224 | Augmentation | Acceptance cum Work Order for Additional work for Laying of Rising main including allied works of for extension of Bonjemary Colliery and ECL Railway siding under Improvement of RCFA Part-II Zone-8 under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001109/2023-2024 | 914/RCD-I | 15/03/2024 | 29/04/2024 | MD AAMIR KHAN | 38.46 | 38.42 | 99.91 | 100
11 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-I) Block-Andal, Dist-Paschim Bardhaman | SM/12224 | Augmentation | Acceptance cum Work Order for Additional work Distribution Network for Augmentation of RCFA Part-II (Zone-1) Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Part-C) | Assistant Engineer 2 | Junior Engineer | ORD/001123/2023-2024 | 929/RCD-I | 15/03/2024 | 29/04/2024 | UNITED CONSTRUCTION | 32.03 | 24.47 | 76.39 | 100
12 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-I) Block-Andal, Dist-Paschim Bardhaman | SM/12224 | Augmentation | Acceptance cum work order for Additional work of laying of rising main at Surjanagar Head Work Site to High lift site and interconnection of collecting main to CWR in the river of Damodar under Augmentation of RCFA Part-II (Zone-I) PWSS under RCFA Division-I. PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001175/2023-2024 | 1014/RCD-I | 16/03/2024 | 30/04/2024 | MAK CONSTRUCTION CO | 40.81 | 10.39 | 25.45 | 100
13 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-I) Block-Andal, Dist-Paschim Bardhaman | SM/12224 | Augmentation | Acceptance cum Work Order for Dedicated pipe line beyond Patal Lakhi Mandir including FHTC connections and allied works for Augmentation PWSS of RCFA Part-II (Zone-I) under RCFA Division - I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/001131/2023-2024 | 916/RCD-I | 15/03/2024 | 14/04/2024 | RAJAT BARAN CHAND | 17.3 | 17.12 | 99.01 | 100
14 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-I) Block-Andal, Dist-Paschim Bardhaman | SM/12224 | Augmentation | Acceptance cum Work Order for Additional work for Shifting of 450 mm dia Rising main for ECL Railway siding near Dalmia OCP for extension of Bonjemari Colliery under Improvement of RCFA Part-II Zone-8 under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001108/2023-2024 | 913/RCD-I | 15/03/2024 | 29/04/2024 | MD AAMIR KHAN | 43.51 | 42.65 | 98.02 | 100
15 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-I) Block-Andal, Dist-Paschim Bardhaman | SM/12224 | Augmentation | Acceptance cum Work Order for Additional work for concrete cutting, restoration of road and allied works Dakshin Khanda area under RCFA Part-II W/S Scheme PHE Dte. [Zone-1A] | Assistant Engineer 2 | Junior Engineer | ORD/001111/2023-2024 | 917/RCD-I | 15/03/2024 | 14/04/2024 | UNITED CONSTRUCTION | 17.04 | 16.94 | 99.38 | 100
16 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-I) Block-Andal, Dist-Paschim Bardhaman | SM/12224 | Augmentation | Acceptance cum Work Order for Additional work for Construction of pillar, MS pipe, specials, GI Pipe and allied works within Zone-I near Dendua under Augmentation PWSS of RCFA Part-II (Zone-I) under RCFA Division-I PHE Dte | Assistant Engineer 1 | Junior Engineer | ORD/001118/2023-2024 | 924/RCD-I | 15/03/2024 | 29/04/2024 | SWATI CORPORATION | 25.03 | 24.35 | 97.27 | 100
Total | [13 empty] | 689.51 | 411.55 | 59.69