## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone - 9 B) | SM/12225 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000025/2023-2024 | 2953/RCD-I | 11/10/2023 | 11/10/2023 | Resource Division | 6.78 | 0 | 0 | 0
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone - 9 B) | SM/12225 | Augmentation | Acceptance cum work order Repair and renovation works of One no RCC Elevated Reservoir of Capacity 1362 cum at Khandra for Augmentation RCFA Part-II (Zone-9B) Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000247/2023-2024 | 2234/RCD-I | 17/07/2023 | 16/08/2023 | UNITED CONSTRUCTION | 16.43 | 16.29 | 99.12 | 100
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone - 9 B) | SM/12225 | Augmentation | Formal work order for distribution network for RCFA Part-II piped Water Supply Scheme including FHTC & allied work under RCFA Div-I, PHE Dte. (Zone-9B)(Part-A) | Assistant Engineer 2 | Junior Engineer | ORD/000630/2022-2023 | 486/RCDI | 03/02/2023 | 05/03/2023 | M/S MONDAL ENTERPRISE | 156.13 | 71.14 | 45.57 | 70
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone - 9 B) | SM/12225 | Augmentation | Formal work order for Distribution Network for RCFA Part-II Piped Water Supply Scheme Including FHTC & allied work under RCFA Division-I PHE Dte. (Zone 9B) (Part-B) | Assistant Engineer 2 | Junior Engineer | ORD/000001/2023-2024 | 1348/RCD-I | 04/04/2023 | 04/05/2023 | M/S SANTANU PALIT & CO. | 156.13 | 33.23 | 21.29 | 30
Total | [13 empty] | 335.46 | 120.66 | 35.97