## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-1A) Block - Andal, Dist - Paschim Bardhaman | SM/12227 | Augmentation | Acceptance cum work order for Additional work laying of different dia HDPE & MS pipe including installation of sluice valve and chamber in different location of Dakshin Khanda & Khandra GP under Ondal Block under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000468/2023-2024 | 2860/RCD-I | 06/10/2023 | 05/11/2023 | UNITED CONSTRUCTION | 25.34 | 22.45 | 88.61 | 90
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-1A) Block - Andal, Dist - Paschim Bardhaman | SM/12227 | Augmentation | Laying of different dia distribution pipe line at Ghosalpara, Dharmarajtala, Sabarpara, Dagalpara, Ghosalpara, Kamarpara, MajhiPara etc area of Dakshin Khanda area under Augmentation of RCFA Part-II (Zone-1A) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000586/2022-2023 | 3294/RCD I | 20/12/2022 | 03/02/2023 | UNITED CONSTRUCTION | 52.8 | 52.4 | 99.24 | 0
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-1A) Block - Andal, Dist - Paschim Bardhaman | SM/12227 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000016/2023-2024 | 2936/RCD-I | 11/10/2023 | 11/10/2023 | Resource Division | 6.78 | 0 | 0 | 0
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-1A) Block - Andal, Dist - Paschim Bardhaman | SM/12227 | Augmentation | Survey Charges for Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-66 dt 22.11.2023 in Indian railway from Andal to Andal Junction Cabin under Augmentation of RCFA Pt-II (Zone-1A) under RCFA Division-I, PHE Dte. |  |  | BILL/00822/2023-2024 | test | 30/11/2023 | 30/11/2023 | EASTERN RAILWAY | 0.24 | 0 | 0 | 0
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-1A) Block - Andal, Dist - Paschim Bardhaman | SM/12227 | Augmentation | Survey Charges for Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-65 dt 22.11.2023 in Indian railway from Andal to Bhaktarnagar under Augmentation of RCFA Pt-II (Zone-1A) under RCFA Division-I, PHE Dte. |  |  | BILL/00821/2023-2024 | 390/23-24 | 29/11/2023 | 29/11/2023 | EASTERN RAILWAY | 0.25 | 0 | 0 | 0
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-1A) Block - Andal, Dist - Paschim Bardhaman | SM/12227 | Augmentation | Acceptance cum Work Order for Additional work line concrete cutting and allied works for Augmentation of Nutondanga RCFA Part-II (Zone-1A) piped W/S Scheme of durgapur sub-Division under RCFA division-I PHE dte. | Assistant Engineer 2,Assistant Engineer 3 | Junior Engineer | ORD/000909/2023-2024 | 214/RCD-I | 29/01/2024 | 28/02/2024 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 35.52 | 35.52 | 99.99 | 70
7 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-1A) Block - Andal, Dist - Paschim Bardhaman | SM/12227 | Augmentation | Acceptance cum Work Order for Sinking of 3 (Three) nos river bed tube wells including collecting main manifold sluice valve chamber reinforcement and other allied works at Damalia H/W under RCFA Part-II at Damodar river under Augmentation of Amritnagar Zone-II Water Supply Scheme under RCFA Division-I PHE Dte. (Part-B) | Assistant Engineer 2 |  | ORD/000971/2023-2024 | 486/RCD-I | 12/02/2024 | 08/03/2024 | M/S KALYAN ENTERPRISE | 10.68 | 10.57 | 98.9 | 100
8 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-1A) Block - Andal, Dist - Paschim Bardhaman | SM/12227 | Augmentation | Acceptance cum Work Order for Additional work for Electrical wiring of C and D type quarter building, PHE Housing Complex and Installation of street including arrangement and fedar box and other allied works under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000961/2023-2024 | 484/RCD-I | 12/02/2024 | 27/02/2024 | T R ENTERPRISE | 13.35 | 13.32 | 99.75 | 100
9 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-1A) Block - Andal, Dist - Paschim Bardhaman | SM/12227 | Augmentation | Acceptance cum work order for Construction of FHTC Platform in different household at Dakshin Khanda (Jl No. 36) Block ¿ Andal under Augmentation of RCFA Part-II (Zone-1A) PWSS under RCFA Division-I PHE Dte. |  |  | ORD/000759/2022-2023 | 385/RCD I | 30/01/2023 | 16/03/2023 | UNITED CONSTRUCTION | 34.42 | 28.04 | 81.46 | 100
10 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-1A) Block - Andal, Dist - Paschim Bardhaman | SM/12227 | Augmentation | Formal work order for distribution network for RCFA Part-II piped water supply Scheme including FHTC & allied work under RCFA Div-I, PHE Dte (Zone-1A) (Ukhra) | Assistant Engineer 2 | Junior Engineer | ORD/000781/2022-2023 | 818/RCDI | 10/03/2023 | 31/08/2025 | ASHA CONSTRUCTION | 249.09 | 53.6 | 21.52 | 70
Total | [13 empty] | 428.48 | 215.89 | 50.39