## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-1A) Block - Andal, Dist - Paschim Bardhaman | SM/12227 | Augmentation | Acceptance cum work order for Additional work laying of different dia HDPE & MS pipe including installation of sluice valve and chamber in different location of Dakshin Khanda & Khandra GP under Ondal Block under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000468/2023-2024 | 2860/RCD-I | 06/10/2023 | 05/11/2023 | UNITED CONSTRUCTION | 25.34 | 22.45 | 88.61 | 90
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-1A) Block - Andal, Dist - Paschim Bardhaman | SM/12227 | Augmentation | Laying of different dia distribution pipe line at Ghosalpara, Dharmarajtala, Sabarpara, Dagalpara, Ghosalpara, Kamarpara, MajhiPara etc area of Dakshin Khanda area under Augmentation of RCFA Part-II (Zone-1A) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000586/2022-2023 | 3294/RCD I | 20/12/2022 | 03/02/2023 | UNITED CONSTRUCTION | 52.8 | 52.4 | 99.24 | 0
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-1A) Block - Andal, Dist - Paschim Bardhaman | SM/12227 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000016/2023-2024 | 2936/RCD-I | 11/10/2023 | 11/10/2023 | Resource Division | 6.78 | 0 | 0 | 0
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-1A) Block - Andal, Dist - Paschim Bardhaman | SM/12227 | Augmentation | Survey Charges for Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-66 dt 22.11.2023 in Indian railway from Andal to Andal Junction Cabin under Augmentation of RCFA Pt-II (Zone-1A) under RCFA Division-I, PHE Dte. |  |  | BILL/00822/2023-2024 | test | 30/11/2023 | 30/11/2023 | EASTERN RAILWAY | 0.24 | 0 | 0 | 0
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-1A) Block - Andal, Dist - Paschim Bardhaman | SM/12227 | Augmentation | Survey Charges for Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-65 dt 22.11.2023 in Indian railway from Andal to Bhaktarnagar under Augmentation of RCFA Pt-II (Zone-1A) under RCFA Division-I, PHE Dte. |  |  | BILL/00821/2023-2024 | 390/23-24 | 29/11/2023 | 29/11/2023 | EASTERN RAILWAY | 0.25 | 0 | 0 | 0
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-1A) Block - Andal, Dist - Paschim Bardhaman | SM/12227 | Augmentation | Acceptance cum Work Order for Additional work line concrete cutting and allied works for Augmentation of Nutondanga RCFA Part-II (Zone-1A) piped W/S Scheme of durgapur sub-Division under RCFA division-I PHE dte. | Assistant Engineer 2,Assistant Engineer 3 | Junior Engineer | ORD/000909/2023-2024 | 214/RCD-I | 29/01/2024 | 28/02/2024 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 35.52 | 35.52 | 99.99 | 70
7 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-1A) Block - Andal, Dist - Paschim Bardhaman | SM/12227 | Augmentation | Acceptance cum Work Order for Sinking of 3 (Three) nos river bed tube wells including collecting main manifold sluice valve chamber reinforcement and other allied works at Damalia H/W under RCFA Part-II at Damodar river under Augmentation of Amritnagar Zone-II Water Supply Scheme under RCFA Division-I PHE Dte. (Part-B) | Assistant Engineer 2 |  | ORD/000971/2023-2024 | 486/RCD-I | 12/02/2024 | 08/03/2024 | M/S KALYAN ENTERPRISE | 10.68 | 10.57 | 98.9 | 100
8 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-1A) Block - Andal, Dist - Paschim Bardhaman | SM/12227 | Augmentation | Acceptance cum Work Order for Additional work for Electrical wiring of C and D type quarter building, PHE Housing Complex and Installation of street including arrangement and fedar box and other allied works under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000961/2023-2024 | 484/RCD-I | 12/02/2024 | 27/02/2024 | T R ENTERPRISE | 13.35 | 13.32 | 99.75 | 100
9 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-1A) Block - Andal, Dist - Paschim Bardhaman | SM/12227 | Augmentation | Acceptance cum work order for Construction of FHTC Platform in different household at Dakshin Khanda (Jl No. 36) Block ¿ Andal under Augmentation of RCFA Part-II (Zone-1A) PWSS under RCFA Division-I PHE Dte. |  |  | ORD/000759/2022-2023 | 385/RCD I | 30/01/2023 | 16/03/2023 | UNITED CONSTRUCTION | 34.42 | 28.04 | 81.46 | 100
10 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-1A) Block - Andal, Dist - Paschim Bardhaman | SM/12227 | Augmentation | Formal work order for distribution network for RCFA Part-II piped water supply Scheme including FHTC & allied work under RCFA Div-I, PHE Dte (Zone-1A) (Ukhra) | Assistant Engineer 2 | Junior Engineer | ORD/000781/2022-2023 | 818/RCDI | 10/03/2023 | 31/08/2025 | ASHA CONSTRUCTION | 249.09 | 53.6 | 21.52 | 70
11 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-1A) Block - Andal, Dist - Paschim Bardhaman | SM/12227 | Augmentation | Acceptance cum work order Laying 160 mm dia HDPE pipe line along Domahani Jamuria Road under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000921/2022-2023 | 1254/RCD-I | 27/03/2023 | 11/04/2023 | NATIONAL CONSTRUCTION | 3.85 | 3.84 | 99.83 | 100
12 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-1A) Block - Andal, Dist - Paschim Bardhaman | SM/12227 | Augmentation | Acceptance cum work order for Additional work 300 mm dia MS pipe line for Singharani Bridge crossing and Kajora at Madanpur under RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000636/2023-2024 | 3418/RCD-1 | 24/11/2023 | 24/12/2023 | MD. JAWED KHAN | 11.59 | 11.05 | 95.34 | 100
13 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-1A) Block - Andal, Dist - Paschim Bardhaman | SM/12227 | Augmentation | Acceptance cum work order for Balance work for distribution network for Augmentation of Ondal Phase-II/A Piped Water Supply Scheme including FHTC and allied works within Ondal Block under RCFA Division-I PHE Dte. (Part-I) | Assistant Engineer 2 |  | ORD/000988/2023-2024 | 470/RCD-1 | 12/02/2024 | 13/03/2024 | SIMA ENTERPRISE | 5.59 | 4.39 | 78.5 | 100
14 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-1A) Block - Andal, Dist - Paschim Bardhaman | SM/12227 | Augmentation | Allied work of laying distribution system of Balance Work of laying distribution system to Accommodate FHTC and providing FHTC including supplying laying fittings fixing of 15 NB PVC pipe with all necessary work specials saddle piece etc. all complete for Augmentation of sub-surface water based PWSS for Amritnagar Zone-II under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000934/2023-2024 | 497/RCD-I | 12/02/2024 | 28/03/2024 | MACHINO TECHNO | 73.78 | 72.39 | 98.12 | 100
15 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation PWSS of RCFA Part-II (Zone-1A) Block - Andal, Dist - Paschim Bardhaman | SM/12227 | Augmentation | Acceptance cum work order for Laying of 90 mm HDPE pipe line inter connection stand post and other allied works at Dakshin Khanda, Moira and adjacent area under RCFA Part-II Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000990/2023-2024 | 471/RCD-1 | 12/02/2024 | 13/03/2024 | UNITED CONSTRUCTION | 9.57 | 9.43 | 98.55 | 100
Total | [13 empty] | 532.86 | 316.99 | 59.49