## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission under RCFA Division-I PHE Dte. District - Paschim Bardhaman | SM/13358 | Support-WQMSP | Continuation work order for Engaging 1 (One) no. Chemist / Bacteriologist, 1 no. Laboratory Assistant & 1 no.Laboratory Attandant for testing of water from different water supply schemes, makig report, communicating with the facilitators of different Gram Panchayet etc. at Water Testing laboratory under RCFA Division-I, P.H.E. Dte. (01.07.2022 to 31.08.2022) | Assistant Engineer 2 | Junior Engineer | ORD/000135/2022-2023 | 1530/RCD-I | 30/06/2022 | 29/08/2022 | MUKUL HAZARI | 0.71 | 0.71 | 100 | 0
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission under RCFA Division-I PHE Dte. District - Paschim Bardhaman | SM/13358 | Support-WQMSP | Acceptance cum work order for Chemical and materials for Paschim Bardhaman Water Testing District Laboratory under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000714/2023-2024 | 3547/RCD-I | 07/12/2023 | 14/12/2023 | MUKUL HAZARI | 3.12 | 3.12 | 100 | 100
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | Operational Charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission under RCFA Division-I PHE Dte. District - Paschim Bardhaman | SM/13358 | Support-WQMSP | Acceptance cum work order for engaging 1(one)no. chemist(one)no Bacteriologist ,1 no laboratory Assistant & 1(one) of Laboratory Attendant for testing of water from different water supply schemes ,making report communicating with the facilitators of different gram panchyat etc at Paschim Bardhaman water Testing District laboratory under RCFA Div-I ,PHE Dte | Assistant Engineer 2 | Junior Engineer | ORD/001038/2022-2023 | 383_RCD-I | 30/01/2023 | 30/01/2024 | M/S. BANDANA ENTERPRISE | 1.61 | 1.61 | 100 | 100
Total | [13 empty] | 5.44 | 5.44 | 100