## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER SUPPLY SCHEME FOR AMRITNAGAR ZONE I WITHIN RCFA PART II AREA UNDER RCFA DIVISION I TO ACCOMMODATE FHTC | SM/13418 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000021/2022-2023 | 3126 | 09/12/2022 | 09/12/2022 | Resource Division | 86.94 | 0 | 0 | 0
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER SUPPLY SCHEME FOR AMRITNAGAR ZONE I WITHIN RCFA PART II AREA UNDER RCFA DIVISION I TO ACCOMMODATE FHTC | SM/13418 | Augmentation | Formal work order for Laying of Distribution System to Accommodate FHTC and Providing FHTC including Supplying laying, fitting, fixing of 15 mm NB PVC (Schedule 80) 20 mm OD HDPE (PE 100, PN 6) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Sub-Surface Water Based Piped Water Supply Scheme for Amritnagar Zone-II under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001036/2022-2023 | 2455./RCD-I | 02/11/2022 | 01/05/2023 | MACHINO TECHNO | 130.76 | 104.24 | 79.72 | 90
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER SUPPLY SCHEME FOR AMRITNAGAR ZONE I WITHIN RCFA PART II AREA UNDER RCFA DIVISION I TO ACCOMMODATE FHTC | SM/13418 | Augmentation | Detailed Route Survey, Design Drawing & DPR Preparation for Amritnagar Zone-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. (sL no. 01) | Assistant Engineer 2 | Junior Engineer | ORD/000534/2021-2022 | 500/RCD-I | 24/02/2022 | 11/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.04 | 4.04 | 100 | 0
4 | PASCHIM BARDHAMAN |  | Asansol Mechanical | AUGMENTATION OF SUB SURFACE WATER SUPPLY SCHEME FOR AMRITNAGAR ZONE I WITHIN RCFA PART II AREA UNDER RCFA DIVISION I TO ACCOMMODATE FHTC | SM/13418 | Augmentation | Providing and Installation of Electro-Mechanical Equipments and allied Works at Damalia under Augmentation of Amritnagar Zone-I Water Supply Scheme, Block : Raniganj, Dist -Paschim Bardhaman. | Assistant Engineer-I | Junior Engineer-5 | ORD/000432/2022-2023 | 484/AMD | 22/02/2023 | 22/02/2024 | ORIENTAL ENGINEERING CO. | 114.65 | 72.08 | 62.87 | 100
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER SUPPLY SCHEME FOR AMRITNAGAR ZONE I WITHIN RCFA PART II AREA UNDER RCFA DIVISION I TO ACCOMMODATE FHTC | SM/13418 | Augmentation | Acceptance cum Work Order for Pipe line crossing adopting trench less Technology (e.g. Jack Pushing method etc.) near Deshbandhu Park, Chittaranjan Road, Joadbari Rupnarayanpur from node no 921 to 924 RCFA Part-I PWSS within command area of Zone-VII under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000979/2023-2024 | 494/RCD-I | 12/02/2024 | 27/02/2024 | KONAR CONSTRUCTION | 6.55 | 6.55 | 100 | 100
6 | PASCHIM BARDHAMAN |  | Asansol Mechanical | AUGMENTATION OF SUB SURFACE WATER SUPPLY SCHEME FOR AMRITNAGAR ZONE I WITHIN RCFA PART II AREA UNDER RCFA DIVISION I TO ACCOMMODATE FHTC | SM/13418 | Augmentation | Providing & fitting, fixing of lighting luminaries, electrical wiring of pump house with yard lighting arrangement and other allied works at New Damalia Pump House under Amritnagar Zone-I, within RCFA Part-II Area Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-5 | ORD/000073/2024-2025 | 1204/AMD | 07/08/2024 | 21/09/2024 | M/S JIT ENTERPRISE | 4.09 | 3.95 | 96.53 | 100
7 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER SUPPLY SCHEME FOR AMRITNAGAR ZONE I WITHIN RCFA PART II AREA UNDER RCFA DIVISION I TO ACCOMMODATE FHTC | SM/13418 | Augmentation | Formal work order for laying of distribution system to accommodate FHTC and providing FHTC including supplying, laying, fitting, fixing of 15 mm NB PVC (schedule 80)/20 mm OD HDPE (PE100,PN6) pipe with all necessary specials, saddle piece etc. all complete at Egara, Amkula and part of Nimcha Mouza Part-B) for Augmnentation of Sub-Surface Water Based Piped Water Supply Scheme for Amritnagar Zone-I under RCFA Division I, PHE Dte.under RCFA Division I,PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000603/2022-2023 | 37/RCD I | 11/01/2023 | 09/02/2025 | TARAPRASAD SARKAR | 164.7 | 43.33 | 26.31 | 50
8 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER SUPPLY SCHEME FOR AMRITNAGAR ZONE I WITHIN RCFA PART II AREA UNDER RCFA DIVISION I TO ACCOMMODATE FHTC | SM/13418 | Augmentation | Formal work order for laying of distribution system to accommodate FHTC and proving FHTC including supplying, laying,fitting, fixing of 15 mm NB PVC (schedule 80)/20 mm OD HDPE (PE100,PN6) pipe wth all necessary specials, saddle piece etc all complete at Murgasole mouza for augmentation of Sub surface Water Based Piped Water Supply Scheme for Amritnagar Zone-I under RCFA Div-I, PHE Dte. under RCFA Div-I, PHE Dte. |  |  | ORD/000605/2022-2023 | 35/RCD I | 11/01/2023 | 11/04/2023 | DAS & CHAKRABORTY | 113.18 | 45.55 | 40.25 | 0
9 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER SUPPLY SCHEME FOR AMRITNAGAR ZONE I WITHIN RCFA PART II AREA UNDER RCFA DIVISION I TO ACCOMMODATE FHTC | SM/13418 | Augmentation | Formal work order for Construction of 900 cum capacity 20 mtr staging height RCC Over Head Reservoir (pipe connection and cost of pipes, specials at Amritnagar Zone-II Piped Water Supply Scheme under RCFA Division-I, PHE Dte. in the District of Paschim Bardhaman. | Assistant Engineer 2 | Junior Engineer | ORD/000157/2023-2024 | 1902/RCD-I | 09/06/2023 | 09/02/2024 | M/S SANTANU PALIT & CO. | 182.7 | 73.08 | 40 | 70
10 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER SUPPLY SCHEME FOR AMRITNAGAR ZONE I WITHIN RCFA PART II AREA UNDER RCFA DIVISION I TO ACCOMMODATE FHTC | SM/13418 | Augmentation | Acceptance cum Work Order for Balance work for laying of different dia HDPE pipe line (left out portion) and other allied works at Amritnagar (Part-A) under Augmentation of Amritnagar Zone-I under RCFA Division-I PHE Dte | Assistant Engineer 2 | Junior Engineer 12 | ORD/000991/2023-2024 | 481/RCD-I | 12/02/2024 | 28/03/2024 | M/S SINGH & KONAR CONSTRUCTION | 45.53 | 32.24 | 70.8 | 80
11 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER SUPPLY SCHEME FOR AMRITNAGAR ZONE I WITHIN RCFA PART II AREA UNDER RCFA DIVISION I TO ACCOMMODATE FHTC | SM/13418 | Augmentation | Acceptance cum Work Order for Balance work for Laying of different dia HDPE pipe line (left out portion) and other allied works at Amritnagar (Part-B) under Augmentation of Amritnagar Zone-I under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer 12 | ORD/000951/2023-2024 | 478/RCD-I | 12/02/2024 | 28/03/2024 | TARAPRASAD SARKAR | 44.86 | 31.52 | 70.25 | 80
12 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER SUPPLY SCHEME FOR AMRITNAGAR ZONE I WITHIN RCFA PART II AREA UNDER RCFA DIVISION I TO ACCOMMODATE FHTC | SM/13418 | Augmentation | Acceptance cum Work Order for Additional work for laying of DI pipe under Augmentation of Amritnagar Zone-I PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer 12 | ORD/000985/2023-2024 | 473/RCD-I | 12/02/2024 | 27/02/2024 | M/S SINGH & KONAR CONSTRUCTION | 8.65 | 2.84 | 32.78 | 80
13 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER SUPPLY SCHEME FOR AMRITNAGAR ZONE I WITHIN RCFA PART II AREA UNDER RCFA DIVISION I TO ACCOMMODATE FHTC | SM/13418 | Augmentation | Acceptance cum work order Additional work for supply and laying HDPE pipe instead of DI pipe for the work of laying distribution system under Augmentation of Amritnagar Zone-I under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer 12 | ORD/000952/2023-2024 | 501/RCD-I | 12/02/2024 | 28/03/2024 | M/S SINGH & KONAR CONSTRUCTION | 30.11 | 15.98 | 53.06 | 50
14 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER SUPPLY SCHEME FOR AMRITNAGAR ZONE I WITHIN RCFA PART II AREA UNDER RCFA DIVISION I TO ACCOMMODATE FHTC | SM/13418 | Augmentation | Acceptance cum work order for Sinking of 4 (Four) nos. 200 mm dia river bed tube well in river Damodar including laying of collecting main (HDPE & MS) of Augmentation of Amritnagar Water Supply Scheme (Phase-I & II) under RCFA Division-I PHE Dte. 2nd Call | Assistant Engineer 2 | Junior Engineer | ORD/000367/2022-2023 | 2875/RCD-I | 07/11/2022 | 07/12/2022 | NIYATI CONSTRUCTION | 24.5 | 17.68 | 72.14 | 0
15 | PASCHIM BARDHAMAN |  | RCFA Division -I | AUGMENTATION OF SUB SURFACE WATER SUPPLY SCHEME FOR AMRITNAGAR ZONE I WITHIN RCFA PART II AREA UNDER RCFA DIVISION I TO ACCOMMODATE FHTC | SM/13418 | Augmentation | Acceptance work order for sinking of 6 nos river bed 200 dia tube well including laying of collecting main for augmentation of sub surface water based piped water supply scheme for Amritnagar Zone-I within RCFA Part-II area under RCFA Div-I, PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000614/2022-2023 | 3272/RCDI | 20/12/2022 | 19/01/2023 | M/S MONDAL CONSTRUCTION | 13.37 | 13.37 | 100 | 100
Total | [13 empty] | 974.65 | 466.43 | 47.86