## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | Asansol Mechanical | SOURCE AUGMENTATION OF OCP WATER BASED WATER SUPPLY SCHEME FOR KAJORA AND ITS ADJOINING AREAS TO ACCOMMODATE FHTC IN ONDAL BLOCK, DISTRICT - PASCHIM BARDHAMAN | SM/14888 | Augmentation | Quotation Money for New Connection at Kajora |  |  | BILL/00079/2023-2024 | BP-2023-24-16 | 23/06/2023 | 23/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.31 | 0 | 0 | 0
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | SOURCE AUGMENTATION OF OCP WATER BASED WATER SUPPLY SCHEME FOR KAJORA AND ITS ADJOINING AREAS TO ACCOMMODATE FHTC IN ONDAL BLOCK, DISTRICT - PASCHIM BARDHAMAN | SM/14888 | Augmentation | Acceptance cum Work Order for Construction of Pump House under at Kajora under Kajora OCP based PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001122/2023-2024 | 928/RCD-I | 15/03/2024 | 13/06/2024 | MACHINO TECHNO | 35.86 | 35.85 | 99.95 | 100
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | SOURCE AUGMENTATION OF OCP WATER BASED WATER SUPPLY SCHEME FOR KAJORA AND ITS ADJOINING AREAS TO ACCOMMODATE FHTC IN ONDAL BLOCK, DISTRICT - PASCHIM BARDHAMAN | SM/14888 | Augmentation | Acceptance cum work order for Additional work for Laying 300 mm dia Raising Main through 600 mm dia MS pipe by trenchless technique under railway / NH / SH for the OCP base PWSS of Kajora (Ghanashampur OCP) of OCP Kajora PWSS under RCFA Division -1 PHE Dte. . | Assistant Engineer 2 | Junior Engineer | ORD/000101/2024-2025 | 2121/RCD-I | 27/08/2024 | 11/10/2024 | T M CONCRETE CREATION PVT.LTD | 57.67 | 45.88 | 79.55 | 100
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | SOURCE AUGMENTATION OF OCP WATER BASED WATER SUPPLY SCHEME FOR KAJORA AND ITS ADJOINING AREAS TO ACCOMMODATE FHTC IN ONDAL BLOCK, DISTRICT - PASCHIM BARDHAMAN | SM/14888 | Augmentation | Formal work order for Source Augmentation of OCP based PWSS of Kajora (Ghanashampur OCP) including, Intake Arrangement, Construction of Steel Truss Bridge, Guardroom, CWR, Boundary Wall, Laying of Rising Main, Land Development etc. & other allied works of OCP Kajora PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000192/2023-2024 | 2148/RCD-I | 12/07/2023 | 12/04/2024 | MRITYUNJOY MUKHERJEE & CO. | 120.71 | 119.78 | 99.23 | 16
5 | PASCHIM BARDHAMAN |  | Asansol Mechanical | SOURCE AUGMENTATION OF OCP WATER BASED WATER SUPPLY SCHEME FOR KAJORA AND ITS ADJOINING AREAS TO ACCOMMODATE FHTC IN ONDAL BLOCK, DISTRICT - PASCHIM BARDHAMAN | SM/14888 | Augmentation | Supply, delivery & installation of Electro-Mechanical equipment and other allied works at Kajora Piped Water Supply Scheme under Asansol Mechanical Division, P.H.E Dte. Block-Andal, District-Paschim Bardhaman. | Assistant Engineer-I | Junior Engineer-5 | ORD/000431/2022-2023 | 483/AMD | 22/02/2023 | 08/07/2025 | ORIENTAL ENGINEERING CO. | 393.09 | 286.06 | 72.77 | 100
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | SOURCE AUGMENTATION OF OCP WATER BASED WATER SUPPLY SCHEME FOR KAJORA AND ITS ADJOINING AREAS TO ACCOMMODATE FHTC IN ONDAL BLOCK, DISTRICT - PASCHIM BARDHAMAN | SM/14888 | Augmentation | Acceptance cum work order for Route Survey & Preparation of DPR for Augmentation of Kajora Piped Water Supply Scheme. Augmentation of Kajora Piped Water Supply Scheme including Providing FHTC Block : Andal District- Paschim Bardhaman. | Assistant Engineer 2 | Junior Engineer 12 | ORD/000617/2023-2024 | 3381/RCD-I | 21/11/2023 | 06/12/2023 | APEX ENGINEERING | 2.54 | 2.54 | 99.99 | 100
7 | PASCHIM BARDHAMAN |  | RCFA Division -I | SOURCE AUGMENTATION OF OCP WATER BASED WATER SUPPLY SCHEME FOR KAJORA AND ITS ADJOINING AREAS TO ACCOMMODATE FHTC IN ONDAL BLOCK, DISTRICT - PASCHIM BARDHAMAN | SM/14888 | Augmentation | Acceptance cum work order for Additional Work For Concrete , MS Girder In connection With source Augmentation of OCP Based PWSS of Kajora (Ghanashampur OCP ) including intake arrangement construction of steel Truss Bridge , Guard room ,CWR, Boundary wall, Laying of raising main, Land development etc, and other allied works of OCP Kajora PWSS under RCFA Division 1 PHE Dte. | Assistant Engineer 2,Assistant Engineer 3 | Junior Engineer | ORD/000098/2024-2025 | 2118/RCD-I | 27/08/2024 | 15/11/2025 | MACHINO TECHNO | 82.14 | 0 | 0 | 100
8 | PASCHIM BARDHAMAN |  | RCFA Division -I | SOURCE AUGMENTATION OF OCP WATER BASED WATER SUPPLY SCHEME FOR KAJORA AND ITS ADJOINING AREAS TO ACCOMMODATE FHTC IN ONDAL BLOCK, DISTRICT - PASCHIM BARDHAMAN | SM/14888 | Augmentation | Acceptance cum work order for Crossing 250 mm Dia MS pipe under the canal in connection with source Augmentation of OCP based PWSS of Kajora (Ghanashampur OCP) including intake arrangement construction of Steel Truss Bridge, Guard Room, CWR Boundary wall, Laying of rising main, land Development etc. and other allied works of OCP Kajora PWSS under RCFA Division-I PHE, Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000318/2024-2025 | 2760/RCD-I | 28/11/2024 | 15/08/2025 | MRITYUNJOY MUKHERJEE & CO. | 14.7 | 0 | 0 | 100
9 | PASCHIM BARDHAMAN |  | Asansol Mechanical | SOURCE AUGMENTATION OF OCP WATER BASED WATER SUPPLY SCHEME FOR KAJORA AND ITS ADJOINING AREAS TO ACCOMMODATE FHTC IN ONDAL BLOCK, DISTRICT - PASCHIM BARDHAMAN | SM/14888 | Augmentation | Providing & fitting, fixing of lighting luminaries, electrical wiring of pump house with yard & Bridge lighting arrangement and other allied works at Kajora Pump House under Kajora Piped Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-5 | ORD/000277/2024-2025 | 1679/AMD | 04/10/2024 | 19/05/2025 | PESTCO INDIA | 23.43 | 0 | 0 | 100
10 | PASCHIM BARDHAMAN |  | RCFA Division -I | SOURCE AUGMENTATION OF OCP WATER BASED WATER SUPPLY SCHEME FOR KAJORA AND ITS ADJOINING AREAS TO ACCOMMODATE FHTC IN ONDAL BLOCK, DISTRICT - PASCHIM BARDHAMAN | SM/14888 | Augmentation | Acceptance cum work order for Additional work for laying 300 mm Dia rising main through 600 mm Dia Ms pipe by trenchless technique under railway /NH/SH FOR THE OCP base PWSS OF Kajora (Ghanashyampur OCP) of OCP Kajora PWSS under RCFA Division-I PHE, Dte | Assistant Engineer 2 | Junior Engineer | ORD/000181/2024-2025 | 2429/RCD-I | 26/09/2024 | 25/11/2024 | MRITYUNJOY MUKHERJEE & CO. | 54.06 | 0 | 0 | 100
11 | PASCHIM BARDHAMAN |  | RCFA Division -I | SOURCE AUGMENTATION OF OCP WATER BASED WATER SUPPLY SCHEME FOR KAJORA AND ITS ADJOINING AREAS TO ACCOMMODATE FHTC IN ONDAL BLOCK, DISTRICT - PASCHIM BARDHAMAN | SM/14888 | Augmentation | Acceptance cum work order for Balance work for retaining wall construction and with allied work for Augmentation of OCP Based PWSS of Kajora (Ghanashampur OCP) including intake arrangement construction of steel Truss Bridge, Guard room, CWR, Boundary wall, Laying of raising main, Land development Etc, and other allied works of OCP Kajora PWSS under RCFA Division 1 PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000097/2024-2025 | 2116/RCD-I | 27/08/2024 | 15/08/2025 | MRITYUNJOY MUKHERJEE & CO. | 46.19 | 0 | 0 | 100
12 | PASCHIM BARDHAMAN |  | RCFA Division -I | SOURCE AUGMENTATION OF OCP WATER BASED WATER SUPPLY SCHEME FOR KAJORA AND ITS ADJOINING AREAS TO ACCOMMODATE FHTC IN ONDAL BLOCK, DISTRICT - PASCHIM BARDHAMAN | SM/14888 | Augmentation | Acceptance cum Work Order for Construction of Boundary Wall at OCP Based Treatment Plant at Kajora under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000036/2024-2025 | 1591/RCD-I | 27/06/2024 | 15/08/2025 | MACHINO TECHNO | 25.99 | 0 | 0 | 100
13 | PASCHIM BARDHAMAN |  | Asansol Mechanical | SOURCE AUGMENTATION OF OCP WATER BASED WATER SUPPLY SCHEME FOR KAJORA AND ITS ADJOINING AREAS TO ACCOMMODATE FHTC IN ONDAL BLOCK, DISTRICT - PASCHIM BARDHAMAN | SM/14888 | Augmentation | Additional works Corresponding to ''Supply, delivery & installation of Electro-Mechanical equipment and other allied works at Kajora Piped Water Supply Scheme under Asansol Mechanical Division, P.H.E Dte. Block-Andal, District-Paschim Bardhaman'' | Assistant Engineer-I | Junior Engineer-5 | ORD/000072/2025-2026 | 1111/AMD | 16/06/2025 | 16/07/2025 | ORIENTAL ENGINEERING CO. | 17.15 | 0 | 0 | 100
Total | [13 empty] | 880.84 | 490.1 | 55.64