## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation of Jamuria (Rural) (Zone-I) PWSS Block- Jamuria District- Paschim Bardhaman under RCFA Division I PHE Dte. | SM/15654 | Augmentation | Quotation money for New Connection at Darbardanga |  |  | BILL/00080/2023-2024 | BP-2023-24-17 | 05/07/2023 | 05/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.48 | 0 | 0 | 0
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-I) PWSS Block- Jamuria District- Paschim Bardhaman under RCFA Division I PHE Dte. | SM/15654 | Augmentation | Acceptance cum work order Sinking of 03 (Three) Nos river bed tube wells including collecting main, Sluice Valve chamber & other allied work at Darbardanga H/W at Ajoy River under Augmentation of Jamuria Rural (Zone I & II) Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000843/2022-2023 | 1076/RCD-I | 23/03/2023 | 21/06/2023 | MAA ENTERPRISE. | 19.58 | 8.87 | 45.3 | 100
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-I) PWSS Block- Jamuria District- Paschim Bardhaman under RCFA Division I PHE Dte. | SM/15654 | Augmentation | Acceptance cum work order for Laying & Pushing of 600 mm dia RCC (NP3) Hume Pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at 03 (Three) nos. location at Lalganj Domohani Road, Kelejhora Health Centre More to Puchra Road, Puchra to Natudihi Road under Augmentation of Jamuria (Rural) (Zone-I) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000240/2023-2024 | 2217/RCD-I | 17/07/2023 | 16/08/2023 | VISUVIOUS | 30.35 | 30.36 | 100.03 | 100
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-I) PWSS Block- Jamuria District- Paschim Bardhaman under RCFA Division I PHE Dte. | SM/15654 | Augmentation | Formal work order for distribution network for augmentation of Jamuria (Rural)(Zone-I) pipe water Supply Scheme including FHTC allied work wthin Jamuria Block under RCFA Div-I PHE Dte.(Part-B) | Assistant Engineer 2 | Junior Engineer | ORD/000782/2022-2023 | 813/RCD I | 10/03/2023 | 09/04/2023 | DIP CONSTRUCTION | 151.47 | 43.68 | 28.83 | 20
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-I) PWSS Block- Jamuria District- Paschim Bardhaman under RCFA Division I PHE Dte. | SM/15654 | Augmentation | Formal work order for Distribution Network for Augmentation of Jamuri (Rural) (Zone-I) RCFA Part-II Piped Water Supply Scheme including FHTC & allied work within Jamuria Block under RCFA Division-I PHE Dte. (Part-A). | Assistant Engineer 2 | Junior Engineer | ORD/000032/2023-2024 | 1613/RCD I | 25/04/2023 | 25/05/2023 | M/S B.K. CONSTRUCTION | 132.16 | 76.95 | 58.22 | 65
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-I) PWSS Block- Jamuria District- Paschim Bardhaman under RCFA Division I PHE Dte. | SM/15654 | Augmentation | Formal work order for Constriction of OHR (Capacity 350 cum, staging Height 20 mtrs) for Augmentation of Jamuria Rural (Zone-I) Piped Water Supply Scheme under RCFA Division-I PHE Dte. Block Barabani, Dist- Paschim Bardhaman. (2nd Call) | Assistant Engineer 2 | Junior Engineer | ORD/000814/2023-2024 | 95/RCD-1 | 08/01/2024 | 08/01/2025 | M/S SINGH & KONAR CONSTRUCTION | 108 | 0 | 0 | 50
7 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-I) PWSS Block- Jamuria District- Paschim Bardhaman under RCFA Division I PHE Dte. | SM/15654 | Augmentation | Preparation of DPR & Route Survey for augumentation of Jamuria (Rural) (Zone-I) piped water supply scheme block-Jamuria, dist- Paschim Barddhaman under RCFA Division-I PHE Dte. (Sl No. 32) | Assistant Engineer 2 | Junior Engineer | ORD/000251/2022-2023 | 2247/RCD I | 15/09/2022 | 30/09/2022 | APEX ENGINEERING | 3.43 | 3.43 | 100 | 0
8 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation of Jamuria (Rural) (Zone-I) PWSS Block- Jamuria District- Paschim Bardhaman under RCFA Division I PHE Dte. | SM/15654 | Augmentation | Providing and Installation of Electro-Mechanical Equipments and allied works under Augmentation of Jamuria (Rural) Zone - I & II Water Supply Scheme, Block : Jamuria, Dist -Paschim Bardhaman. | Assistant Engineer-I | Junior Engineer-3 | ORD/000436/2022-2023 | 491/AMD | 22/02/2023 | 22/02/2025 | SUNRISE ENGINEERING CORPORATION | 145.5 | 94.72 | 65.1 | 100
Total | [13 empty] | 595.96 | 257.99 | 43.29