## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-I) PWSS Block- Jamuria District- Paschim Bardhaman under RCFA Division I PHE Dte. | SM/15654 | Augmentation | Preparation of DPR & Route Survey for augumentation of Jamuria (Rural) (Zone-I) piped water supply scheme block-Jamuria, dist- Paschim Barddhaman under RCFA Division-I PHE Dte. (Sl No. 32) | Assistant Engineer 2 | Junior Engineer | ORD/000251/2022-2023 | 2247/RCD I | 15/09/2022 | 30/09/2022 | APEX ENGINEERING | 3.43 | 3.43 | 100 | 0
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-I) PWSS Block- Jamuria District- Paschim Bardhaman under RCFA Division I PHE Dte. | SM/15654 | Augmentation | Formal work order for distribution network for augmentation of Jamuria (Rural)(Zone-I) pipe water Supply Scheme including FHTC allied work wthin Jamuria Block under RCFA Div-I PHE Dte.(Part-B) | Assistant Engineer 2 | Junior Engineer | ORD/000782/2022-2023 | 813/RCD I | 10/03/2023 | 09/04/2023 | DIP CONSTRUCTION | 151.47 | 43.68 | 28.83 | 20
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-I) PWSS Block- Jamuria District- Paschim Bardhaman under RCFA Division I PHE Dte. | SM/15654 | Augmentation | Formal work order for Distribution Network for Augmentation of Jamuri (Rural) (Zone-I) RCFA Part-II Piped Water Supply Scheme including FHTC & allied work within Jamuria Block under RCFA Division-I PHE Dte. (Part-A). | Assistant Engineer 2 | Junior Engineer | ORD/000032/2023-2024 | 1613/RCD I | 25/04/2023 | 25/05/2023 | M/S B.K. CONSTRUCTION | 132.16 | 76.95 | 58.22 | 65
4 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation of Jamuria (Rural) (Zone-I) PWSS Block- Jamuria District- Paschim Bardhaman under RCFA Division I PHE Dte. | SM/15654 | Augmentation | Providing and Installation of Electro-Mechanical Equipments and allied works under Augmentation of Jamuria (Rural) Zone - I & II Water Supply Scheme, Block : Jamuria, Dist -Paschim Bardhaman. | Assistant Engineer-I | Junior Engineer-3 | ORD/000436/2022-2023 | 491/AMD | 22/02/2023 | 22/02/2025 | SUNRISE ENGINEERING CORPORATION | 145.5 | 94.72 | 65.1 | 100
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-I) PWSS Block- Jamuria District- Paschim Bardhaman under RCFA Division I PHE Dte. | SM/15654 | Augmentation | Acceptance cum work order Sinking of 03 (Three) Nos river bed tube wells including collecting main, Sluice Valve chamber & other allied work at Darbardanga H/W at Ajoy River under Augmentation of Jamuria Rural (Zone I & II) Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000843/2022-2023 | 1076/RCD-I | 23/03/2023 | 21/06/2023 | MAA ENTERPRISE. | 19.58 | 8.87 | 45.3 | 100
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-I) PWSS Block- Jamuria District- Paschim Bardhaman under RCFA Division I PHE Dte. | SM/15654 | Augmentation | Acceptance cum work order for Laying 200 mm dia MS water pipe line with 600 mm dia MS casing pipe for Railway crossing in between KM 27/21-23 and between Barabani (BBI) and Jamuria (JMA) Station in Asansol Division under JJM under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000286/2023-2024 | 2335/RCD-I | 01/08/2023 | 16/08/2023 | M/S MONDAL ENTERPRISE | 36.29 | 34.64 | 95.45 | 100
7 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-I) PWSS Block- Jamuria District- Paschim Bardhaman under RCFA Division I PHE Dte. | SM/15654 | Augmentation | Formal Work Order for Construction of Water sample collection cum Laboratory cum ISA & DPMU activity center as well as training hall etc. in the premises of RCFA office building under Augmentation of Jamuria (Rural) (Zone-I) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000172/2023-2024 | 2008/RCD-I | 26/06/2023 | 10/01/2025 | M/S CHANDI CHARAN ROY | 241.14 | 151.22 | 62.71 | 67
8 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-I) PWSS Block- Jamuria District- Paschim Bardhaman under RCFA Division I PHE Dte. | SM/15654 | Augmentation | Acceptance cum work order for Laying & Pushing of 600 mm dia RCC (NP3) Hume Pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at 03 (Three) nos. location at Lalganj Domohani Road, Kelejhora Health Centre More to Puchra Road, Puchra to Natudihi Road under Augmentation of Jamuria (Rural) (Zone-I) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000240/2023-2024 | 2217/RCD-I | 17/07/2023 | 16/08/2023 | VISUVIOUS | 30.35 | 30.36 | 100.03 | 100
9 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-I) PWSS Block- Jamuria District- Paschim Bardhaman under RCFA Division I PHE Dte. | SM/15654 | Augmentation | Acceptence cum work order for Additional Supplying, Laying and Aligning HDPE pipe line, construction of street stand post and allied works under Ballavpur W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000403/2023-2024 | 2585/RCD-I | 07/09/2023 | 22/09/2023 | TARA CONSTRUCTION | 6.32 | 6.15 | 97.34 | 100
10 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-I) PWSS Block- Jamuria District- Paschim Bardhaman under RCFA Division I PHE Dte. | SM/15654 | Augmentation | Acceptance cum work order for Laying of 200 mm dia rising main for the proposed of Shyamla for Augmentation of Jamuria (Rural) (Zone-I) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000686/2023-2024 | 3285/RCD-1 | 08/11/2023 | 08/12/2023 | SILPO UDYOG ENGINEERING CONSTRUCTIONS | 12.63 | 11.21 | 88.77 | 85
11 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-I) PWSS Block- Jamuria District- Paschim Bardhaman under RCFA Division I PHE Dte. | SM/15654 | Augmentation | Acceptance cum work order for Construction of CWR (Clear Water Reservoir) of capacity 150 cum & allied work at Jamuria under Jamuria Rural-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000732/2023-2024 | 3656/RCD-1 | 28/12/2023 | 22/11/2024 | MD SARFARAZ ALAM | 23.33 | 20.38 | 87.36 | 70
12 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation of Jamuria (Rural) (Zone-I) PWSS Block- Jamuria District- Paschim Bardhaman under RCFA Division I PHE Dte. | SM/15654 | Augmentation | Quotation money for New Connection at Darbardanga |  |  | BILL/00080/2023-2024 | BP-2023-24-17 | 05/07/2023 | 05/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.48 | 0 | 0 | 0
13 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-I) PWSS Block- Jamuria District- Paschim Bardhaman under RCFA Division I PHE Dte. | SM/15654 | Augmentation | Formal work order for Constriction of OHR (Capacity 350 cum, staging Height 20 mtrs) for Augmentation of Jamuria Rural (Zone-I) Piped Water Supply Scheme under RCFA Division-I PHE Dte. Block Barabani, Dist- Paschim Bardhaman. (2nd Call) | Assistant Engineer 2 | Junior Engineer | ORD/000814/2023-2024 | 95/RCD-1 | 08/01/2024 | 08/01/2025 | M/S SINGH & KONAR CONSTRUCTION | 108 | 0 | 0 | 50
14 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Jamuria (Rural) (Zone-I) PWSS Block- Jamuria District- Paschim Bardhaman under RCFA Division I PHE Dte. | SM/15654 | Augmentation | Acceptance cum work order for Additional estimate for concrete conduit for water body crossing at 4 (Four) nos location including adopting trench less technology (e.g. Jack Pushing Method etc) at Three nos location including MS work, Supply of valve, hard rock cutting, valve chamber and allied works related to distribution network at Churulia, Rakhakura, Joynagar, Chinchurbil etc villages under Augmentation of Jamuria Rural (Zone-1) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000984/2023-2024 | 468/RCD-1 | 12/02/2024 | 28/03/2024 | ASHA CONSTRUCTION | 39.4 | 38.15 | 96.82 | 100
15 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation of Jamuria (Rural) (Zone-I) PWSS Block- Jamuria District- Paschim Bardhaman under RCFA Division I PHE Dte. | SM/15654 | Augmentation | Providing & fitting, fixing of lighting luminaries, electrical wiring of pump house with yard lighting arrangement and other allied works at Jamuria Pump House under Augmentation of Jamuria Rural Zone-I Piped Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-3,Junior Engineer-5 | ORD/000068/2024-2025 | 1199/AMD | 07/08/2024 | 21/09/2024 | SUNRISE ENGINEERING CORPORATION | 6.08 | 0 | 0 | 100
16 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation of Jamuria (Rural) (Zone-I) PWSS Block- Jamuria District- Paschim Bardhaman under RCFA Division I PHE Dte. | SM/15654 | Augmentation | Supply & Installation of submersible pumping machineries and other allied Works at Low Lift RBTW for Augmentation of Jamuria (Rural) Zone - I & II Water Supply Scheme, Block : Jamuria, Dist -Paschim Bardhaman. | Assistant Engineer-I | Junior Engineer-3 | ORD/000443/2024-2025 | 2101/AMD | 12/12/2024 | 11/01/2025 | SUNRISE ENGINEERING CORPORATION | 13.89 | 0 | 0 | 100
17 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation of Jamuria (Rural) (Zone-I) PWSS Block- Jamuria District- Paschim Bardhaman under RCFA Division I PHE Dte. | SM/15654 | Augmentation | Providing of lighting luminaries inconnection with yard lighting arrangement of newly constructed Pump House premises under Augmentation of Jamuria Rural (Zone-I) Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-5 | ORD/000472/2024-2025 | 2179/AMD | 26/12/2024 | 10/06/2025 | SASTIK ENTERPRISE | 12.05 | 0 | 0 | 100
18 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation of Jamuria (Rural) (Zone-I) PWSS Block- Jamuria District- Paschim Bardhaman under RCFA Division I PHE Dte. | SM/15654 | Augmentation | Additional works for making Suction Common Header and supply delivery of cubical kisok box under Augmentation of Jamuria (Rural) Zone - I and II Water Supply Scheme, Block : Jamuria, Dist -Paschim Bardhaman. | Assistant Engineer-I | Junior Engineer-3 | ORD/000029/2025-2026 | 949/AMD | 16/05/2025 | 15/06/2025 | SUNRISE ENGINEERING CORPORATION | 1.1 | 0 | 0 | 100
Total | [13 empty] | 988.18 | 519.74 | 52.6