## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Continuation work order for Laying 450 mm dia MS water pipe line with 700 mm dia MS casing pipe for Railway crossing in Salanpur at KM SLS/1136 and SLS/1138 on Bemjomary siding Railway line in Asansol Division under JJM under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000604/2023-2024 | 3297/RCD-I | 10/11/2023 | 25/11/2023 | MD AAMIR KHAN | 24.44 | 0 | 0 | 100
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Acceptance cum work order for Emergency repairing of 50 sqmm x 4 core Al Armoured damaged cable line and other allied Electrical works at Executive Engineer office building, SE office building, rest room & B type quarter under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000722/2023-2024 | 3573_RCD/1 | 12/12/2023 | 27/12/2023 | T R ENTERPRISE | 6.82 | 0 | 0 | 100
3 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Continuation order for Hiring of Diesel driven Maxi cabs for official use of the Assistant Engineer-I under Asansol Mechanical Division, P.H Engineering. Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000087/2023-2024 | 1091/AMD | 25/04/2023 | 24/04/2024 | EASTERN INDIA SALES AND SERVICE | 1.79 | 0 | 0 | 83
4 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Continuation order for Hiring of Diesel driven Maxi cabs for official use of the Assistant Engineer-II under Asansol Mechanical Division, P.H Engineering. Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000088/2023-2024 | 1092/AMD | 25/04/2023 | 24/04/2024 | EASTERN INDIA SALES AND SERVICE | 1.79 | 0 | 0 | 83
5 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Continuation order for Hiring of Diesel driven Maxi cabs for official use of the Executive Engineer under Asansol Mechanical Division, P.H Engineering. Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000089/2023-2024 | 1099/AMD | 26/04/2023 | 25/04/2024 | SUNRISE ENGINEERING CORPORATION | 1.79 | 0 | 0 | 67
6 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Providing & Installation of Electrical Equipments For Sub-Station at Mohishila Boosting Station (GLR-I & II), Searsole Boosting Station (GLR-I & II), Sankarpur Clear Water Boosting Station and Banshra Clear Water Boosting Station and Gaseous Chlorination system at different OHR sites with illumination under Augmentation of RCFA Part-II Piped Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-3 | ORD/000203/2023-2024 | 1492/AMD | 04/08/2023 | 04/08/2024 | ORIENTAL ENGINEERING CO. | 1965.22 | 0 | 0 | 71
7 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Acceptance cum work order for Laying of pipe line from Domhani Asansol main Road near BDO Office to Domohani PHC and construction of stand post at different places at Domohani Bazar under Barabani Development Block under RCFA Part-I W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000966/2023-2024 | 458/RCD-1 | 12/02/2024 | 03/03/2024 | UNITED CONSTRUCTION | 6.71 | 0 | 0 | 62
8 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Acceptance cum work order for Emergency repairing work of CI rising main (500 mm dia, 200 mm dia & 150 mm dia ) at Chotdola more, Dhasal more and new Kenda and Searsole H/W site near Pump House under RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000958/2023-2024 | 504/RCD-I | 12/02/2024 | 13/03/2024 | DAWN CONSTRUCTION | 8.84 | 0 | 0 | 0
9 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Acceptance cum Work Order for Additional for Distribution Network for Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Part-4) Block-Andal, Dist-Paschim Bardhaman under RCFA Div-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000051/2024-2025 | 1741/RCD-I | 18/07/2024 | 01/09/2024 | UNITED CONSTRUCTION | 30.14 | 0 | 0 | 85
10 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Acceptance cum work order for Supply of GI pipes to Searsole Store under Augmentation of RCFA Part-II (Zone-17) PWSS under RCFA Division-I PHE Dte. |  | Junior Engineer | ORD/000914/2023-2024 | 217/RCD-I | 29/01/2024 | 18/02/2024 | MAKALI ENGINEERING CORPORATION | 90.4 | 0 | 0 | 100
11 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Acceptance cum work order for Supply of GI pipes to Searsole Store under Augmentation of RCFA Part-II (Zone-15) PWSS under RCFA Division-I PHE Dte. |  | Junior Engineer | ORD/000912/2023-2024 | 216/RCD-I | 29/01/2024 | 18/02/2024 | INDIA PIPE FITTING CO | 89.25 | 0 | 0 | 100
12 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Laying of 110 mm dia HDPE pipeline including pushing of 600 mm dia RCC (NP3) hume pipe by adopting trench less technology at Health World Hospital, Asansol Paschim Bardhaman under RCFA Division-I PHE Dte. Extension work. | Assistant Engineer 2 | Junior Engineer | ORD/001020/2023-2024 | Camp-02_Health_World_AE-I | 21/02/2024 | 12/03/2024 | M/S CHANDI CHARAN ROY | 18.54 | 0 | 0 | 100
13 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Balance work in connection with Improvement of RCFA Part-I Water Supply Scheme within command area of Zone-V with LDS and FHTC work under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000950/2023-2024 | 455/RCD-1 | 12/02/2024 | 28/03/2024 | MRITYUNJOY MUKHERJEE & CO. | 21.29 | 0 | 0 | 100
14 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Laying 300 mm dia MS water pipe line with 600 mm dia MS cashing pipe for Railway crossing in Salanpur in between KM 231/16-18 and Salanpur (SLS) Rupnarayanpur (RNPR) Station in Asansol Diviion under JJM under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000956/2023-2024 | 456/RCD-1 | 12/02/2024 | 28/03/2024 | MRITYUNJOY MUKHERJEE & CO. | 37.06 | 0 | 0 | 100
15 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Acceptance cum work order for Adopting trench less technology (e.g. Jack Pushing Method etc.) at 3 (Three) nos location within laying distribution system of Amritnagar (Part-B) under Augmentation of Amritnagar Zone-I PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000963/2023-2024 | 457/RCD-1 | 12/02/2024 | 28/03/2024 | M/S SINGH & KONAR CONSTRUCTION | 23.02 | 0 | 0 | 100
16 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Allied work Balance Work of Road restoration in connection with formal work order Distribution network including FHTC and allied work at Ondal Block of Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000938/2023-2024 | 452/RCD-1 | 12/02/2024 | 28/03/2024 | MRITYUNJOY MUKHERJEE & CO. | 43.94 | 0 | 0 | 100
17 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Acceptance cum Work Order for Supply and erection of Information Boards (31 nos) having M.S Channel/Angle posts and 1.5 mm thick M.S synthetic enamel paint over a coat of red oxide primer including lettering complete at different places under Salanpur ,Barabani, Andal ,Pandabeswar ,Raniganj and Durgapur Faridpur Block Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer 4 | Junior Engineer | ORD/000056/2024-2025 | 1746/RCD-I | 18/07/2024 | 02/08/2024 | UTTAR DINAJPUR ANKUR GRAM UNNAYAN SOCIETY | 6.1 | 0 | 0 | 100
18 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Acceptance cum Work Order for Supply and erection of Information Boards(43 nos)having M.S Channel/Angle posts and 1.5 mm thick M.S synthetic enamel paint over a coat of red oxide primer including lettering complete at different places under Jamuria Block Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer 4 | Junior Engineer | ORD/000058/2024-2025 | 1748/RCD-I | 18/07/2024 | 02/08/2024 | UNITED CONSTRUCTION | 8.48 | 0 | 0 | 100
19 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Acceptance cum work order for construction work and Interior Decoration of Office Building in Asansol under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer 4 | Junior Engineer,Junior Engineer 10 | ORD/000209/2024-2025 | 2513/RCD-I | 04/10/2024 | 18/11/2024 | M/S KALYANI ENTERPRISE | 41.78 | 0 | 0 | 100
20 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Acceptance cum Work Order for Protecting apparatus of collecting main including other allied works under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000059/2024-2025 | 1751/RCD-I | 18/07/2024 | 07/08/2024 | INDIA PIPE FITTING CO | 93.63 | 0 | 0 | 100
21 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Acceptance cum work order for Providing of different dia of water regulating apparatus and other allied works (Part-A) under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II under RCFA Division-I PHE Dte. | Assistant Engineer 3 | Junior Engineer 7 | ORD/000196/2024-2025 | 2451/RCD-I | 30/09/2024 | 15/10/2024 | MAKALI ENGINEERING CORPORATION | 78.04 | 0 | 0 | 100
22 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Acceptance cum work order for Construction of Visiter room and driver rest room at office premises Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer 12 | ORD/000120/2024-2025 | 2155/RCD-I | 29/08/2024 | 27/11/2024 | G. CONSTRUCTION | 18.48 | 0 | 0 | 100
23 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Acceptance cum work order for Protecting apparatus of collecting main including other allied works under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000050/2024-2025 | 1750/RCD-I | 18/07/2024 | 07/08/2024 | MAKALI ENGINEERING CORPORATION | 94.91 | 0 | 0 | 100
24 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000001/2024-2025 | 1178/RCD-I | 03/04/2024 | 03/04/2024 | Resource Division | 337.92 | 0 | 0 | 0
25 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Quotation for Earnest Money Deposit at Sankarpur Boosting Station, Chhora under Augmentation of RCFA II WS Scheme. |  |  | BILL/00694/2023-2024 | BP-2023-24-63 | 28/12/2023 | 28/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.05 | 0 | 0 | 0
26 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-67 dt 09.02.2024 under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) under RCFA Division-I PHE Dte. |  |  | BILL/01361/2023-2024 | 560/23-24 | 20/02/2024 | 20/02/2024 | EASTERN RAILWAY | 10.41 | 0 | 0 | 0
27 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-71 dt 09.02.2024 under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) under RCFA Division-I PHE Dte. |  |  | BILL/01363/2023-2024 | 562/23-24 | 20/02/2024 | 20/02/2024 | EASTERN RAILWAY | 7.84 | 0 | 0 | 0
28 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-65 dt 09.02.2024 under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) under RCFA Division-I PHE Dte. |  |  | BILL/01364/2023-2024 | 563/23-24 | 20/02/2024 | 20/02/2024 | EASTERN RAILWAY | 17.21 | 0 | 0 | 0
29 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Fuel Bill for Diesel Driven Maxi Cab for Official Use of The AE-II, under AMD, PHE Dte for the month of April, 2024. |  |  | BILL/00461/2024-2025 | BP-2024-25-33/3 | 23/08/2024 | 23/08/2024 | RANAJIT AUTO | 0.15 | 0 | 0 | 0
30 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Earnest Money Deposit for Bulk Power Supply at Intake sub-station Sarkuri Salanpur under Augmentation of RCFA Part II WS Scheme. |  |  | BILL/00697/2023-2024 | BP-2023-24-66 | 02/01/2024 | 02/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.05 | 0 | 0 | 0
31 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Quotation for Earnest Money Deposit at Bansra Boosting Station, Kunustoria under Augmentation of RCFA II WS Scheme. |  |  | BILL/00692/2023-2024 | BP-2023-24-61 | 28/12/2023 | 28/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.05 | 0 | 0 | 0
32 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-69 dt 09.02.2024 under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) under RCFA Division-I PHE Dte. |  |  | BILL/01362/2023-2024 | 561/23-24 | 20/02/2024 | 20/02/2024 | EASTERN RAILWAY | 6.97 | 0 | 0 | 0
33 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-68 dt 09.02.2024 under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) under RCFA Division-I PHE Dte. |  |  | BILL/01366/2023-2024 | 565/23-24 | 20/02/2024 | 20/02/2024 | EASTERN RAILWAY | 6.97 | 0 | 0 | 0
34 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-66 dt 09.02.2024 under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) under RCFA Division-I PHE Dte. |  |  | BILL/01359/2023-2024 | 559/23-24 | 20/02/2024 | 20/02/2024 | EASTERN RAILWAY | 16.52 | 0 | 0 | 0
35 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Shifting of overhead line inside the premises of benali boosting station |  |  | BILL/00075/2024-2025 | BP-2024-25-14 | 17/05/2024 | 17/05/2024 | INDIA POWER CORPN. LTD. | 2.84 | 0 | 0 | 0
36 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-91 dt 07.03.2024 under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) under RCFA Division-I PHE Dte. |  |  | BILL/01539/2023-2024 | 624/23-24 | 14/03/2024 | 14/03/2024 | EASTERN RAILWAY | 0.09 | 0 | 0 | 0
37 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Fuel Charges for the Cab of AE-I under AMD, PHE Dte. for the month of JANUARY, 2024 |  |  | BILL/00310/2024-2025 | BP-2024-25-30 | 06/08/2024 | 06/08/2024 | RANAJIT AUTO | 0.26 | 0 | 0 | 0
38 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Fuel Bill for the Cab of The Executive Engineer, under AMD, PHE Dte., for the month of March,2024. |  |  | BILL/00471/2024-2025 | BP-2024-25-34/5 | 23/08/2024 | 23/08/2024 | RANAJIT AUTO | 0.25 | 0 | 0 | 0
39 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Fuel Charges for the Cab of AE-II under AMD, PHE Dte. for the month of NOVEMBER, 2023. |  |  | BILL/00313/2024-2025 | BP-2024-25-27 | 30/07/2024 | 30/07/2024 | RANAJIT AUTO | 0.2 | 0 | 0 | 0
40 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Fuel Charges for the Cab of AE-II under AMD, PHE Dte. for the month of FEBRUARY, 2024 |  |  | BILL/00319/2024-2025 | BP-2024-25-30/3 | 06/08/2024 | 06/08/2024 | RANAJIT AUTO | 0.23 | 0 | 0 | 0
41 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Fuel Charges for the Cab of AE-II under AMD, PHE Dte. for the month of JANUARY, 2024 |  |  | BILL/00317/2024-2025 | BP-2024-25-30/2 | 06/08/2024 | 06/08/2024 | RANAJIT AUTO | 0.25 | 0 | 0 | 0
42 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Earnest Money Deposit for Bulk Power Supply at Mohishila Boosting Station under Augmentation of RCFA Part II WS Scheme. |  |  | BILL/00696/2023-2024 | BP-2023-24-65 | 02/01/2024 | 02/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.05 | 0 | 0 | 0
43 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-90 dt 07.03.2024 under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) under RCFA Division-I PHE Dte. |  |  | BILL/01541/2023-2024 | 626/23-24 | 14/03/2024 | 14/03/2024 | EASTERN RAILWAY | 0.09 | 0 | 0 | 0
44 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | DIVERSION OF 33KV S/C PHE FEEDER INSIDE THE PREMISES OF THE PHE DUE TO PROPOSED WTP,KALYNESWARI FOR M/S PHE DIRECTORATE,ASANSOL |  |  | BILL/00022/2024-2025 | BP-2024-25-4 | 23/04/2024 | 23/04/2024 | CHIEF ACCOUNTS OFFICER, DAMODAR VALLEY CORPORATION | 2.8 | 0 | 0 | 0
45 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Fuel Bill for Diesel Driven Maxi Cab for Official Use of The AE-I, under AMD, PHE Dte for the month of April, 2024. |  |  | BILL/00465/2024-2025 | BP-2024-25-33/7 | 23/08/2024 | 23/08/2024 | RANAJIT AUTO | 0.22 | 0 | 0 | 0
46 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Fuel Bill for the Cab of The Executive Engineer, under AMD, PHE Dte., for the month of Jan, 2024. |  |  | BILL/00467/2024-2025 | BP-2024-25-34/1 | 23/08/2024 | 23/08/2024 | RANAJIT AUTO | 0.25 | 0 | 0 | 0
47 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Fuel Charges for the Cab of AE - I under AMD, PHE Dte. for the month of DECEMBER, 2023 |  |  | BILL/00320/2024-2025 | BP-2024-25-27/3 | 30/07/2024 | 30/07/2024 | RANAJIT AUTO | 0.26 | 0 | 0 | 0
48 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-70 dt 09.02.2024 under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) under RCFA Division-I PHE Dte. |  |  | BILL/01365/2023-2024 | 564/23-24 | 20/02/2024 | 20/02/2024 | EASTERN RAILWAY | 7.84 | 0 | 0 | 0
49 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Bulk Power Supply at Mohishila Boosting Station under Augmentation of RCFA Part II. |  |  | BILL/00912/2023-2024 | BP-2023-24-77 | 21/02/2024 | 21/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 22.75 | 0 | 0 | 0
50 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-72 dt 09.02.2024 under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) under RCFA Division-I PHE Dte. |  |  | BILL/01367/2023-2024 | 566/23-24 | 20/02/2024 | 20/02/2024 | EASTERN RAILWAY | 6.97 | 0 | 0 | 0
51 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Fuel Charges for the Cab of AE-I under AMD, PHE Dte. for the month of FEBRUARY, 2024. |  |  | BILL/00312/2024-2025 | BP-2024-25-30/1 | 06/08/2024 | 06/08/2024 | RANAJIT AUTO | 0.27 | 0 | 0 | 0
52 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Fuel Charges for the Cab of AE-II under AMD, PHE Dte. for the month of DECEMBER, 2023 |  |  | BILL/00315/2024-2025 | BP-2024-25-27/1 | 30/07/2024 | 30/07/2024 | RANAJIT AUTO | 0.24 | 0 | 0 | 0
53 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Fuel Bill for the Cab of The Executive Engineer, under AMD, PHE Dte., for the month of Feb, 2024. |  |  | BILL/00469/2024-2025 | BP-2024-25-34/3 | 23/08/2024 | 23/08/2024 | RANAJIT AUTO | 0.22 | 0 | 0 | 0
54 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-08 dt 07.03.2024 under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) under RCFA Division-I PHE Dte. |  |  | BILL/01540/2023-2024 | 625/23-24 | 14/03/2024 | 14/03/2024 | EASTERN RAILWAY | 0.08 | 0 | 0 | 0
55 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-92 dt 07.03.2024 under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) under RCFA Division-I PHE Dte. |  |  | BILL/01542/2023-2024 | 627/23-24 | 14/03/2024 | 14/03/2024 | EASTERN RAILWAY | 0.28 | 0 | 0 | 0
56 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Installation Charge and Security Deposit for Bulk Power Supply at Intake Sub-Station Sarkuri Salanpur Under Augmentation of RCFA Part-II |  |  | BILL/00003/2024-2025 | BP-2024-25-2 | 15/04/2024 | 15/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 54.89 | 0 | 0 | 0
57 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Fuel Charges for the Cab of AE-I under AMD, PHE Dte. for the month of NOVEMBER, 2023 |  |  | BILL/00307/2024-2025 | BP-2024-25-27/2 | 30/07/2024 | 30/07/2024 | RANAJIT AUTO | 0.22 | 0 | 0 | 0
58 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | License Fees for five (05) years for 6-lanning of Barwa Adda - Panagarh section of NH-2 from km 398.240 to km 521.120 including Panagarh Bypass in the state of Jharkhand & West Bengal under NHDP Phase -V on BOT (Toll) on DBFOT pattern - Permission for laying of water pipeline along NH-2 from Kalla more (km 462+080) to Harishpur (km+918) and 7 nos crossing across NH-2 in the state of West Bengal under Augmentatin of RCFA Pt II Volume -II under RCFA Division-I PHE Dte. |  |  | BILL/00522/2024-2025 | 282/24-25 | 09/09/2024 | 09/09/2024 | NATIONAL HIGHWAY AUTHORITY OF INDIA | 164.48 | 0 | 0 | 0
59 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Quotation for Earnest Money Deposit at Searsole Boosting Station, Ranisayer under Augmentation of RCFA II WS Scheme. |  |  | BILL/00693/2023-2024 | BP-2023-24-62 | 28/12/2023 | 28/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.05 | 0 | 0 | 0
60 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Bulk Power Supply at Searsole Boosting Station under Augmentation of RCFA Part II. |  |  | BILL/00911/2023-2024 | BP-2023-24-76 | 21/02/2024 | 21/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 93.38 | 0 | 0 | 0
61 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-93 dt 07.03.2024 under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) under RCFA Division-I PHE Dte. |  |  | BILL/01538/2023-2024 | 623/23-24 | 14/03/2024 | 14/03/2024 | EASTERN RAILWAY | 0.08 | 0 | 0 | 0
62 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Fuel Bill for Diesel Driven Maxi Cab for Official Use of The AE-I, under AMD, PHE Dte for the month of March, 2024. |  |  | BILL/00463/2024-2025 | BP-2024-25-33/5 | 23/08/2024 | 23/08/2024 | RANAJIT AUTO | 0.25 | 0 | 0 | 0
63 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Payment of Security Deposite & Remaining Earnest Money for Bansra Boosting Station (Consumer ID- 950085633) under Asansol Mechanical Division, P.H.E. Dte. |  |  | BILL/00398/2024-2025 | BP-2024-25-24 | 29/07/2024 | 29/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 24.84 | 0 | 0 | 0
64 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Quotation Money for Earnest Money Deposition for Bulk Power supply at Kalyaneswari under Augmentation of RCFA Part II WS Scheme. |  |  | BILL/00777/2023-2024 | BP-2023-24-69 | 11/01/2024 | 11/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.2 | 0 | 0 | 0
65 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-95 dt 07.03.2024 under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) under RCFA Division-I PHE Dte. |  |  | BILL/01543/2023-2024 | 628/23-24 | 14/03/2024 | 14/03/2024 | EASTERN RAILWAY | 0.08 | 0 | 0 | 0
66 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Fuel Bill for Diesel Driven Maxi Cab for Official Use of The AE-II, under AMD, PHE Dte for the month of March, 2024. |  |  | BILL/00459/2024-2025 | BP-2024-25-33/1 | 23/08/2024 | 23/08/2024 | RANAJIT AUTO | 0.23 | 0 | 0 | 0
67 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Fuel Charges for the Cab of EE under AMD, PHE Dte. for the month of NOV, 2023. |  |  | BILL/00303/2024-2025 | BP-2024-25-27/4 | 30/07/2024 | 30/07/2024 | RANAJIT AUTO | 0.09 | 0 | 0 | 0
68 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Fuel Charges for the Cab of EE under AMD, PHE Dte. for the month of DECEMBER, 2023. |  |  | BILL/00305/2024-2025 | BP-2024-25-27/5 | 30/07/2024 | 30/07/2024 | RANAJIT AUTO | 0.23 | 0 | 0 | 0
69 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | PAYMENT OF SECURITY DEPOSIT & EARNEST MONEY FOR BULK POWER SUPPLY AT SHANKARPUR BOOSTING STATION. |  |  | BILL/00589/2024-2025 | BP-2024-25-63 | 28/10/2024 | 28/10/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 22.9 | 0 | 0 | 0
70 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Fuel Bill for the Cab of The Executive Engineer, under AMD, PHE Dte., for the month of April, 2024. |  |  | BILL/00473/2024-2025 | BP-2024-25-62 | 28/10/2024 | 28/10/2024 | RANAJIT AUTO | 0.22 | 0 | 0 | 0
71 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Formal Work Order for Laying of different dia HDPE pipe line and allied works at Raghunathchak, Raniganj Chati, Baliapur and adjacent area under Zone-IX for Improvement of RCFA Part-I Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000305/2023-2024 | 2383/RCD-I | 07/08/2023 | 05/11/2023 | DAWN CONSTRUCTION | 105.48 | 0 | 0 | 100
72 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Acceptance cum work order for Renovation work at Kalyaneswari Inspection Bungalow & WTP under RCFA Part-I W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer 4 | Junior Engineer | ORD/000721/2023-2024 | 3610/RCD-1 | 20/12/2023 | 12/06/2025 | M/S KALYANI ENTERPRISE | 81.82 | 0 | 0 | 100
73 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Acceptance cum work order for Operation and regulatiing of different dia S/V of Distribution system and rising main for FHTC work for Mdira, Dighalpahari, Chotkara and Kanskuli villages under administrative contingency of JJM under RCFA Division -I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000820/2023-2024 | 101/RCD-1 | 09/01/2024 | 04/09/2024 | SRI KRISHNA ENTERPRISE | 2.91 | 0 | 0 | 100
74 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) Under RCFA Division-I PHE Dte. | SM/18468 | Augmentation | Acceptance cum Work Order for Realtime Water Quality Monitoring including 1 year maintenance for the OHR as hereunder RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer 4 | Junior Engineer | ORD/000079/2024-2025 | 2033/RCD-I | 21/08/2024 | 19/11/2025 | MAXBRIDGE SOLUTIONS LLP | 33.46 | 0 | 0 | 55
Total | [13 empty] | 3748.85 | 0 | 0