## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Acceptance cum work order for Sinking of 4 (Four) nos 200 mm dia river bed tube wells in the river Ajoy at Baidyanathpur for Baidyanathpur Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000287/2023-2024 | 2336/RCD-I | 01/08/2023 | 12/01/2025 | MD AAMIR KHAN | 43.86 | 21.67 | 49.4 | 50
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Acceptance cum work order for Sinking of 6 (Six) nos 200 mm dia river bed tube wells in the river Ajoy at Kendra Khottamdihi for Kendra Khottamdihi Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000288/2023-2024 | 2337/RCD-I | 01/08/2023 | 31/08/2023 | M/S MONI TRADERS | 42.45 | 41.38 | 97.48 | 55
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Acceptance cum Work Order for Sinking of 4 (Four) nos river bed tube wells including collecting main and other allied works at Damodar river under (Part-II) Unionpara Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer,Junior Engineer 10 | ORD/000974/2023-2024 | 492/RCD-I | 12/02/2024 | 13/03/2024 | TARA MA ENTERPRISE | 13.02 | 2.87 | 22.03 | 100
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Emergent sinking of one no 200 x 165 mm dia rig bore tube well at ESI Hospital near staff quarter Kali Mandir, Paschim Bardhaman under RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000001/2024-2025 | Camp_02_ESI_Hospital_AE_I | 16/04/2024 | 23/04/2024 | M/S CHANDI CHARAN ROY | 8.1 | 0 | 0 | 100
5 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Lowering of submersible pumping machineries in Newly sunk RBTW No-14 at Baidyanathpur Pump house under Ukhra Water Supply Scheme. | Assistant Engineer-II | Junior Engineer-5 | ORD/000037/2024-2025 | 1039/AMD | 16/07/2024 | 03/05/2025 | EASTERN INDIA SALES AND SERVICE | 8.15 | 0 | 0 | 100
6 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Providing and Installation of Submersible pumping Machineries at newly sunk River Bed Tube Well no-9 and 10 at Narayankuri Pump House under Source Augmentation of RCFA Part-II Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-5 | ORD/000438/2024-2025 | 2096/AMD | 12/12/2024 | 11/01/2025 | PREMNATH MITRA | 9.89 | 0 | 0 | 0
7 | PASCHIM BARDHAMAN |  | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Acceptance cum Work Order for Sinking of 6 (Six) nos 200 mm dia river bed tube well in the river Damodar at Madanpur Head Works Site for Madanpur Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000937/2023-2024 | 477/RCD-I | 12/02/2024 | 13/03/2024 | NIYATI CONSTRUCTION | 29.98 | 23.43 | 78.16 | 100
8 | PASCHIM BARDHAMAN |  | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Continuation work order for Sinking of 6 (Six) nos 200 mm dia river bed tube well including collecting main in the river of Damodar at Surjanagar under Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000994/2023-2024 | 295/A/RCD-I | 06/02/2024 | 07/03/2024 | MAK CONSTRUCTION CO | 22.57 | 17.67 | 78.32 | 100
9 | PASCHIM BARDHAMAN |  | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Acceptance cum Work Order for Sinking of 5 (Five) nos 200 mm dia river bed tube well including collecting main in the river Damodar at Surjanagar H/W site for ASTA Source Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Part-A) | Assistant Engineer 2 | Junior Engineer 12 | ORD/000953/2023-2024 | 479/RCD-I | 12/02/2024 | 13/03/2024 | M/S MONDAL ENTERPRISE | 15.54 | 8.02 | 51.59 | 100
10 | PASCHIM BARDHAMAN |  | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Acceptance cum Work Order for Sinking of 5 (Five) nos 200 mm dia river bed tube well including collecting main in the river Damodar at Surjanagar H/W site for ASTA of Source Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Part-B) | Assistant Engineer 2 | Junior Engineer 12 | ORD/000954/2023-2024 | 480/RCD-I | 12/02/2024 | 13/03/2024 | MD. JAWED KHAN | 15.82 | 8.15 | 51.54 | 100
11 | PASCHIM BARDHAMAN |  | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Acceptance cum Work Order for Sinking of 3 (Three) nos river bed tube wells including collecting main manifold sluice valve chamber reinforcement and other allied works at Damalia H/W under RCFA Part-II at Damodar river under Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. (Part-A) | Assistant Engineer 2 | Junior Engineer 12 | ORD/000969/2023-2024 | 485/RCD-I | 12/02/2024 | 08/03/2024 | SOMNATH SAMANTA | 19.46 | 19.45 | 99.94 | 100
12 | PASCHIM BARDHAMAN |  | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Acceptance cum Work Order for Sinking of 2 (Two) nos river bed tube wells including collecting main & other allied works at Damodar river under Tirat Colliery Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer 12 | ORD/001106/2023-2024 | 895/RCD-I | 15/03/2024 | 30/03/2024 | MAA ENTERPRISE | 4.51 | 4.42 | 98.12 | 100
13 | PASCHIM BARDHAMAN |  | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Acceptance cum Work Order for Sinking of 1 (One) no river bed tube wells including collecting main & other allied works at Damalia Damodar river under Amritnagar Zone-II Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer 12 | ORD/001105/2023-2024 | 894/RCD-I | 15/03/2024 | 30/03/2024 | MAA ENTERPRISE | 3.05 | 2.99 | 98.05 | 100
14 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Lowering of submersible pumping machineries in Newly sunk RBTW No-5 at Tirat Colliery Lowlift Pump House under Tirat Colliery Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-5 | ORD/000035/2024-2025 | 1037/AMD | 16/07/2024 | 30/08/2024 | PESTCO INDIA | 8.93 | 8.87 | 99.35 | 100
15 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Lowering of Submersible Pumping Machineries in the Newly sunk RBTWs Amkula-5 to Tirat Mouza Pump House under Tirat Mouza Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-5 | ORD/000036/2024-2025 | 1038/AMD | 16/07/2024 | 12/01/2025 | SUNRISE ENGINEERING CORPORATION | 8.47 | 0 | 0 | 100
16 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Lowering of Submersible Pumping Machineries for Newly Sunk RBTW No-03 for CWR at Ajoy Ghat Pumping Station under Churulia Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-5 | ORD/000038/2024-2025 | 1040/AMD | 16/07/2024 | 09/12/2025 | PREMNATH MITRA | 10.27 | 0 | 0 | 100
17 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Providing and Installation of Submersible Pumping machineries in the Newly sunk RBTWs from 01-06 at Surjanagar Lowlift Pump House under ASTA W/S Scheme. | Assistant Engineer-II | Junior Engineer-5 | ORD/000039/2024-2025 | 1041/AMD | 16/07/2024 | 30/08/2024 | BENGAL CONSTRUCTION | 10.6 | 0 | 0 | 100
18 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Lowering of submersible pumping machineries in Newly sunk RBTW No-7 at Tirat Colliery Lowlift Pump House under Tirat Colliery Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-5 | ORD/000047/2024-2025 | 1133/AMD | 30/07/2024 | 28/09/2024 | PESTCO INDIA | 8.93 | 8.87 | 99.35 | 100
19 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Providing and installation of submersible pumping machineries at newly sunk river bed tube well No-31 & 32 and other allied works at Kalajharia Water Works under source Augmentation of RCFA-II Water Supply Scheme. | Assistant Engineer-II | Junior Engineer-5 | ORD/000442/2024-2025 | 2100/AMD | 12/12/2024 | 11/01/2025 | EASTERN INDIA SALES AND SERVICE | 28.6 | 0 | 0 | 100
20 | PASCHIM BARDHAMAN |  | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Acceptance cum work order for Hydro-Geological study of Sub-Surface Water Flow with Sinking of Tube Well in Damodar & Ajay River bed and Bank Position of Source Augmentation of RCFA Part-II Water Supply Scheme by installing River bed tube well under RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 10 | ORD/000178/2024-2025 | 2435/RCD-I | 26/09/2024 | 11/10/2024 | ENVIROTECH SOLUTIONS | 95 | 25.16 | 26.48 | 100
21 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Lowering of submersible pumping machineries in Newly sunk RBTW No-6 at Tirat Colliery Low lift Pump House under Tirat Colliery Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-5 | ORD/000071/2024-2025 | 1202/AMD | 07/08/2024 | 21/09/2024 | PESTCO INDIA | 4.97 | 4.92 | 98.83 | 100
22 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Lowering of submersible pumping machineries in Newly sunk RBTW No-15 at Baidyanathpur Pump house under Ukhra Water Supply Scheme. | Assistant Engineer-II | Junior Engineer-5 | ORD/000075/2024-2025 | 1206/AMD | 07/08/2024 | 22/05/2025 | INDUSTRIAL ELECTRICAL CORPORATION | 8.18 | 0 | 0 | 100
23 | PASCHIM BARDHAMAN |  | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Acceptance cum work order for Sinking of 6 (Six) nos. 200 mm dia river bed tube well including 3 nos. collecting main in the river Ajoy at Runakuraghat H/W site for Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000103/2024-2025 | 2123/RCD-I | 27/08/2024 | 21/09/2024 | MAA ENTERPRISE | 13.24 | 12.75 | 96.33 | 100
24 | PASCHIM BARDHAMAN |  | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Acceptance cum Work Order for Additional work of Emergent laying of Collecting Main for sinking of 4 nos river bed tube well and making of manifold with in addition of connecting of 10 nos tube well in River Ajoy at Bhaburia Head Works Site under RBT Type Sarpi, Jamgora Jagannathpur and Gourbazar-Ichapur Water Supply Scheme for Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | Assistant Engineer 3 | Junior Engineer 7 | ORD/000371/2024-2025 | 3099/RCD-I | 13/12/2024 | 27/01/2025 | MD AAMIR KHAN | 46.32 | 0 | 0 | 100
25 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Providing and Installation of Submersible pumping Machineries at newly sunk River Bed Tube Well No-8 at Union Para Low Lift under Ballavpur Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-5 | ORD/000046/2024-2025 | 1132/AMD | 30/07/2024 | 03/08/2025 | HINDUSTHAN CONSULTANT FIRM | 4.84 | 0 | 0 | 100
26 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Lowering of Submersible Pumping Machineries in the Newly sunk RBTWs Harvanga-13 & 14 to Tirat Mouza Pump House under Tirat Mouza Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-5 | ORD/000048/2024-2025 | 1134/AMD | 30/07/2024 | 28/09/2024 | M/S. SOMA ENTERPRISE | 8.55 | 6.95 | 81.27 | 100
27 | PASCHIM BARDHAMAN |  | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Acceptance cum work order for Balanced work Sinking of 03 (Three) nos. 200 mm dia river bed tube well in the river of Ajoy (Pandabeswar H/W Site) for Source Augmentation of RCFA Part-II W/S Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000083/2024-2025 | 2108/RCD-I | 27/08/2024 | 01/06/2025 | B.T.M. CONCERN | 23.41 | 11.92 | 50.91 | 70
28 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Lowering of Submersible Pumping Machineries in Newly sunk RBTW No- 8 for CWR at Ajoyghat Pumping Station under source Augmentation of RCFA part-II Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-5 | ORD/000439/2024-2025 | 2097/AMD | 12/12/2024 | 11/01/2025 | M/S. SOMA ENTERPRISE | 5.6 | 0 | 0 | 100
29 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Providing and Installation of Submersible Pumping machineries in the Newly sunk RBTWs from 07-11 at Surjanagar Low lift Pump House under ASTA W/S Scheme. | Assistant Engineer-II | Junior Engineer-5 | ORD/000070/2024-2025 | 1201/AMD | 07/08/2024 | 21/09/2024 | M/S JIT ENTERPRISE | 8.85 | 8.83 | 99.7 | 100
30 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Providing and Installation of Submersible pumping Machineries at newly sunk River Bed Tube Well no- 7 & 8 at Narayankuri Pump House under Narayankuri Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-5 | ORD/000318/2024-2025 | 1812/AMD | 29/10/2024 | 02/06/2025 | HINDUSTHAN CONSULTANT FIRM | 11.21 | 0 | 0 | 100
31 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Providing and Installation of Submersible pumping Machineries at newly sunk River Bed Tube Well No-7 at Union Para Low Lift under Ballavpur Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-5 | ORD/000319/2024-2025 | 1813/AMD | 29/10/2024 | 31/08/2025 | M/S S.G.ENTERPRISE | 5.28 | 0 | 0 | 100
32 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Supply & Installation of submersible pumping machineries at Newly sunk 8 Nos Low Lift RBTWs at Madanpur Lowlift under Source Augmentation of RCFA Part-II Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-5 | ORD/000024/2025-2026 | 944/AMD | 16/05/2025 | 15/06/2025 | BENGAL CONSTRUCTION | 24.61 | 0 | 0 | 0
33 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Installation of transformer(315 KVA), Supply, delivery and installation S/M, Pump-Motor set, and other allied works at Madanpur Head Works Site under RCFA Part-II Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-5 | ORD/000069/2025-2026 | 1108/AMD | 16/06/2025 | 16/07/2025 | M/S SAJAHAN CHOWDHURY | 37.68 | 0 | 0 | 0
34 | PASCHIM BARDHAMAN |  | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Acceptance cum work order for Protecting and regulating apparatus for distribution system and rising main of Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000333/2025-2026 | 1616/RCD-I | 29/05/2025 | 18/06/2025 | MAKALI ENGINEERING CORPORATION | 50.69 | 0 | 0 | 100
35 | PASCHIM BARDHAMAN |  | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Acceptance cum Work Order for Flow control of Rising main and different dia distribution system by different regulating apparatus of Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000602/2024-2025 | 267/RCD-I | 04/02/2025 | 06/03/2025 | MAKALI ENGINEERING CORPORATION | 87.75 | 0 | 0 | 100
36 | PASCHIM BARDHAMAN |  | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Acceptance cum work order for Allied work of collecting main of river bed tube well in Ajay river for Gourbazar-Ichapur Piped Water Supply Scheme from river bed manifold to Bhaburia Old CWR under JJM at Durgapur-Faridpur Block of Augmentation of Gourbazar-Ichapur W/S Scheme of Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | Assistant Engineer 3 | Junior Engineer,Junior Engineer 7 | ORD/000704/2024-2025 | 451/RCD-I | 12/03/2025 | 26/04/2025 | MAK CONSTRUCTION CO | 24 | 0 | 0 | 100
37 | PASCHIM BARDHAMAN |  | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Acceptance cum Work Order for Flow control of Rising main and different dia distribution system by different regulating apparatus Source of Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000601/2024-2025 | 266/RCD-I | 04/02/2025 | 06/03/2025 | MAKALI ENGINEERING CORPORATION | 78.96 | 39.09 | 49.51 | 100
38 | PASCHIM BARDHAMAN |  | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Acceptance cum work order for Supply and laying 240 sqmm 3.5 core cable at Kalajharia complex for searching of infiltration gallery of Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer 12 | ORD/000284/2025-2026 | 1388/RCD-I | 15/05/2025 | 25/05/2025 | MRITYUNJOY MUKHERJEE & CO. | 27.6 | 0 | 0 | 100
39 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Electric quotation for Narayankuri PWSS under Source augmentation of RCFA Part-II by installing RBTW under RCFA Division-I PHe Dte |  |  | BILL/00342/2025-2026 |  | 19/06/2025 | 19/06/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.06 | 0 | 0 | 0
40 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Narayankuri pump house under Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. [SM/18891] |  |  | BILL/00506/2026-2027 |  | 06/08/2026 | 06/08/2026 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.03 | 0 | 0 | 0
Total | [13 empty] | 887.03 | 277.4 | 31.27