## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Emergent sinking of one no 200 x 165 mm dia rig bore tube well at ESI Hospital near staff quarter Kali Mandir, Paschim Bardhaman under RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000001/2024-2025 | Camp_02_ESI_Hospital_AE_I | 16/04/2024 | 23/04/2024 | M/S CHANDI CHARAN ROY | 8.1 | 0 | 0 | 100
2 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Providing and Installation of Submersible Pumping machineries in the Newly sunk RBTWs no-13 at Surjanagar Low lift Pump House under ASTA W/S Scheme. | Assistant Engineer-II | Junior Engineer-5 | ORD/000049/2024-2025 | 1135/AMD | 30/07/2024 | 28/09/2024 | M/S S.G.ENTERPRISE | 9.75 | 0 | 0 | 0
3 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Providing and Installation of Submersible pumping Machineries at newly sunk River Bed Tube Well no-9 and 10 at Narayankuri Pump House under Source Augmentation of RCFA Part-II Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-5 | ORD/000438/2024-2025 | 2096/AMD | 12/12/2024 | 11/01/2025 | PREMNATH MITRA | 9.89 | 0 | 0 | 0
4 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Lowering of submersible pumping machineries in Newly sunk RBTW No-7 at Tirat Colliery Lowlift Pump House under Tirat Colliery Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-5 | ORD/000047/2024-2025 | 1133/AMD | 30/07/2024 | 28/09/2024 | PESTCO INDIA | 8.93 | 0 | 0 | 100
5 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Lowering of submersible pumping machineries in Newly sunk RBTW No-6 at Tirat Colliery Low lift Pump House under Tirat Colliery Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-5 | ORD/000071/2024-2025 | 1202/AMD | 07/08/2024 | 21/09/2024 | PESTCO INDIA | 4.97 | 0 | 0 | 100
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Continuation work order for Sinking of 6 (Six) nos 200 mm dia river bed tube well including collecting main in the river of Damodar at Surjanagar under Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000994/2023-2024 | 295/A/RCD-I | 06/02/2024 | 07/03/2024 | MAK CONSTRUCTION CO | 22.57 | 0 | 0 | 100
7 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Lowering of submersible pumping machineries in Newly sunk RBTW No-5 at Tirat Colliery Lowlift Pump House under Tirat Colliery Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-5 | ORD/000035/2024-2025 | 1037/AMD | 16/07/2024 | 30/08/2024 | PESTCO INDIA | 8.93 | 0 | 0 | 100
8 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Lowering of Submersible Pumping Machineries in the Newly sunk RBTWs Harvanga-13 & 14 to Tirat Mouza Pump House under Tirat Mouza Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-5 | ORD/000048/2024-2025 | 1134/AMD | 30/07/2024 | 28/09/2024 | M/S. SOMA ENTERPRISE | 8.55 | 0 | 0 | 100
9 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Providing and Installation of Submersible Pumping machineries in the Newly sunk RBTWs from 07-11 at Surjanagar Low lift Pump House under ASTA W/S Scheme. | Assistant Engineer-II | Junior Engineer-5 | ORD/000070/2024-2025 | 1201/AMD | 07/08/2024 | 21/09/2024 | M/S JIT ENTERPRISE | 8.85 | 0 | 0 | 100
10 | PASCHIM BARDHAMAN |  | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Acceptance cum Work Order for Sinking of 4 (Four) nos river bed tube wells including collecting main and other allied works at Damodar river under (Part-II) Unionpara Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer,Junior Engineer 10 | ORD/000974/2023-2024 | 492/RCD-I | 12/02/2024 | 13/03/2024 | TARA MA ENTERPRISE | 13.02 | 0 | 0 | 100
11 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Supply & Installation of submersible pumping machineries at Newly sunk 8 Nos Low Lift RBTWs at Madanpur Lowlift under Source Augmentation of RCFA Part-II Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-5 | ORD/000024/2025-2026 | 944/AMD | 16/05/2025 | 15/06/2025 | BENGAL CONSTRUCTION | 24.61 | 0 | 0 | 0
12 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Installation of transformer(315 KVA), Supply, delivery and installation S/M, Pump-Motor set, and other allied works at Madanpur Head Works Site under RCFA Part-II Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-5 | ORD/000069/2025-2026 | 1108/AMD | 16/06/2025 | 16/07/2025 | M/S SAJAHAN CHOWDHURY | 37.68 | 0 | 0 | 0
13 | PASCHIM BARDHAMAN |  | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Acceptance cum work order for Sinking of 4 (Four) nos 200 mm dia river bed tube wells in the river Ajoy at Baidyanathpur for Baidyanathpur Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000287/2023-2024 | 2336/RCD-I | 01/08/2023 | 12/01/2025 | MD AAMIR KHAN | 43.86 | 0 | 0 | 50
14 | PASCHIM BARDHAMAN |  | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Acceptance cum work order for Sinking of 6 (Six) nos 200 mm dia river bed tube wells in the river Ajoy at Kendra Khottamdihi for Kendra Khottamdihi Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000288/2023-2024 | 2337/RCD-I | 01/08/2023 | 31/08/2023 | M/S MONI TRADERS | 42.45 | 0 | 0 | 55
15 | PASCHIM BARDHAMAN |  | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Acceptance cum Work Order for Sinking of 5 (Five) nos 200 mm dia river bed tube well including collecting main in the river Damodar at Surjanagar H/W site for ASTA of Source Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Part-B) | Assistant Engineer 2 | Junior Engineer 12 | ORD/000954/2023-2024 | 480/RCD-I | 12/02/2024 | 13/03/2024 | MD. JAWED KHAN | 15.82 | 0 | 0 | 100
16 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Providing and installation of submersible pumping machineries at newly sunk river bed tube well No-31 & 32 and other allied works at Kalajharia Water Works under source Augmentation of RCFA-II Water Supply Scheme. | Assistant Engineer-II | Junior Engineer-5 | ORD/000442/2024-2025 | 2100/AMD | 12/12/2024 | 11/01/2025 | EASTERN INDIA SALES AND SERVICE | 28.6 | 0 | 0 | 100
17 | PASCHIM BARDHAMAN |  | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Acceptance cum work order for Hydro-Geological study of Sub-Surface Water Flow with Sinking of Tube Well in Damodar & Ajay River bed and Bank Position of Source Augmentation of RCFA Part-II Water Supply Scheme by installing River bed tube well under RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 10 | ORD/000178/2024-2025 | 2435/RCD-I | 26/09/2024 | 11/10/2024 | ENVIROTECH SOLUTIONS | 95 | 0 | 0 | 100
18 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Providing and Installation of Submersible Pumping machineries in the Newly sunk RBTWs from 01-06 at Surjanagar Lowlift Pump House under ASTA W/S Scheme. | Assistant Engineer-II | Junior Engineer-5 | ORD/000039/2024-2025 | 1041/AMD | 16/07/2024 | 30/08/2024 | BENGAL CONSTRUCTION | 10.6 | 0 | 0 | 100
19 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Lowering of submersible pumping machineries in Newly sunk RBTW No-15 at Baidyanathpur Pump house under Ukhra Water Supply Scheme. | Assistant Engineer-II | Junior Engineer-5 | ORD/000075/2024-2025 | 1206/AMD | 07/08/2024 | 22/05/2025 | INDUSTRIAL ELECTRICAL CORPORATION | 8.18 | 0 | 0 | 100
20 | PASCHIM BARDHAMAN |  | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Acceptance cum work order for Sinking of 6 (Six) nos. 200 mm dia river bed tube well including 3 nos. collecting main in the river Ajoy at Runakuraghat H/W site for Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000103/2024-2025 | 2123/RCD-I | 27/08/2024 | 21/09/2024 | MAA ENTERPRISE | 13.24 | 0 | 0 | 100
21 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Lowering of Submersible Pumping Machineries in the Newly sunk RBTWs Amkula-5 to Tirat Mouza Pump House under Tirat Mouza Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-5 | ORD/000036/2024-2025 | 1038/AMD | 16/07/2024 | 12/01/2025 | SUNRISE ENGINEERING CORPORATION | 8.47 | 0 | 0 | 100
22 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Lowering of Submersible Pumping Machineries for Newly Sunk RBTW No-03 for CWR at Ajoy Ghat Pumping Station under Churulia Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-5 | ORD/000038/2024-2025 | 1040/AMD | 16/07/2024 | 09/12/2025 | PREMNATH MITRA | 10.27 | 0 | 0 | 100
23 | PASCHIM BARDHAMAN |  | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Acceptance cum Work Order for Sinking of 6 (Six) nos 200 mm dia river bed tube well in the river Damodar at Madanpur Head Works Site for Madanpur Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000937/2023-2024 | 477/RCD-I | 12/02/2024 | 13/03/2024 | NIYATI CONSTRUCTION | 29.98 | 0 | 0 | 100
24 | PASCHIM BARDHAMAN |  | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Acceptance cum Work Order for Sinking of 5 (Five) nos 200 mm dia river bed tube well including collecting main in the river Damodar at Surjanagar H/W site for ASTA Source Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Part-A) | Assistant Engineer 2 | Junior Engineer 12 | ORD/000953/2023-2024 | 479/RCD-I | 12/02/2024 | 13/03/2024 | M/S MONDAL ENTERPRISE | 15.54 | 0 | 0 | 100
25 | PASCHIM BARDHAMAN |  | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Acceptance cum Work Order for Sinking of 3 (Three) nos river bed tube wells including collecting main manifold sluice valve chamber reinforcement and other allied works at Damalia H/W under RCFA Part-II at Damodar river under Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. (Part-A) | Assistant Engineer 2 | Junior Engineer 12 | ORD/000969/2023-2024 | 485/RCD-I | 12/02/2024 | 08/03/2024 | SOMNATH SAMANTA | 19.46 | 0 | 0 | 100
26 | PASCHIM BARDHAMAN |  | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Acceptance cum Work Order for Sinking of 2 (Two) nos river bed tube wells including collecting main & other allied works at Damodar river under Tirat Colliery Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer 12 | ORD/001106/2023-2024 | 895/RCD-I | 15/03/2024 | 30/03/2024 | MAA ENTERPRISE | 4.51 | 0 | 0 | 100
27 | PASCHIM BARDHAMAN |  | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Acceptance cum Work Order for Sinking of 1 (One) no river bed tube wells including collecting main & other allied works at Damalia Damodar river under Amritnagar Zone-II Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer 12 | ORD/001105/2023-2024 | 894/RCD-I | 15/03/2024 | 30/03/2024 | MAA ENTERPRISE | 3.05 | 0 | 0 | 100
Total | [13 empty] | 514.88 | 0 | 0