## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Acceptance cum work order for Sinking of 4 (Four) nos 200 mm dia river bed tube wells in the river Ajoy at Baidyanathpur for Baidyanathpur Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000287/2023-2024 | 2336/RCD-I | 01/08/2023 | 31/08/2023 | MD AAMIR KHAN | 44.62 | 10.83 | 24.28 | 50
2 | PASCHIM BARDHAMAN |  | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Emergent sinking of one no 200 x 165 mm dia rig bore tube well at ESI Hospital near staff quarter Kali Mandir, Paschim Bardhaman under RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000001/2024-2025 | Camp_02_ESI_Hospital_AE_I | 16/04/2024 | 23/04/2024 | M/S CHANDI CHARAN ROY | 8.1 | 0 | 0 | 100
3 | PASCHIM BARDHAMAN |  | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Acceptance cum Work Order for Sinking of 5 (Five) nos 200 mm dia river bed tube well including collecting main in the river Damodar at Surjanagar H/W site for ASTA of Source Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Part-B) | Assistant Engineer 2 | Junior Engineer 12 | ORD/000954/2023-2024 | 480/RCD-I | 12/02/2024 | 13/03/2024 | MD. JAWED KHAN | 15.82 | 4.08 | 25.77 | 100
4 | PASCHIM BARDHAMAN |  | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Acceptance cum Work Order for Sinking of 1 (One) no river bed tube wells including collecting main & other allied works at Damalia Damodar river under Amritnagar Zone-II Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer 12 | ORD/001105/2023-2024 | 894/RCD-I | 15/03/2024 | 30/03/2024 | MAA ENTERPRISE | 3.05 | 1.5 | 49.02 | 100
5 | PASCHIM BARDHAMAN |  | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Acceptance cum Work Order for Sinking of 5 (Five) nos 200 mm dia river bed tube well including collecting main in the river Damodar at Surjanagar H/W site for ASTA Source Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Part-A) | Assistant Engineer 2 | Junior Engineer 12 | ORD/000953/2023-2024 | 479/RCD-I | 12/02/2024 | 13/03/2024 | M/S MONDAL ENTERPRISE | 15.54 | 4.01 | 25.79 | 100
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Acceptance cum Work Order for Sinking of 2 (Two) nos river bed tube wells including collecting main & other allied works at Damodar river under Tirat Colliery Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer 12 | ORD/001106/2023-2024 | 895/RCD-I | 15/03/2024 | 30/03/2024 | MAA ENTERPRISE | 4.51 | 2.21 | 49.06 | 100
7 | PASCHIM BARDHAMAN |  | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Acceptance cum work order for Sinking of 6 (Six) nos 200 mm dia river bed tube wells in the river Ajoy at Kendra Khottamdihi for Kendra Khottamdihi Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000288/2023-2024 | 2337/RCD-I | 01/08/2023 | 31/08/2023 | M/S MONI TRADERS | 42.45 | 20.69 | 48.74 | 55
8 | PASCHIM BARDHAMAN |  | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Acceptance cum Work Order for Sinking of 6 (Six) nos 200 mm dia river bed tube well in the river Damodar at Madanpur Head Works Site for Madanpur Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000937/2023-2024 | 477/RCD-I | 12/02/2024 | 13/03/2024 | NIYATI CONSTRUCTION | 29.98 | 9 | 30.04 | 100
9 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Providing and Installation of Submersible Pumping machineries in the Newly sunk RBTWs from 01-06 at Surjanagar Lowlift Pump House under ASTA W/S Scheme. | Assistant Engineer-II | Junior Engineer-5 | ORD/000039/2024-2025 | 1041/AMD | 16/07/2024 | 30/08/2024 | BENGAL CONSTRUCTION | 10.6 | 0 | 0 | 0
10 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Lowering of Submersible Pumping Machineries in the Newly sunk RBTWs Amkula-5 to Tirat Mouza Pump House under Tirat Mouza Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-5 | ORD/000036/2024-2025 | 1038/AMD | 16/07/2024 | 30/08/2024 | SUNRISE ENGINEERING CORPORATION | 8.47 | 0 | 0 | 0
11 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Lowering of Submersible Pumping Machineries for Newly Sunk RBTW No-03 for CWR at Ajoy Ghat Pumping Station under Churulia Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-5 | ORD/000038/2024-2025 | 1040/AMD | 16/07/2024 | 30/08/2024 | PREMNATH MITRA | 10.27 | 0 | 0 | 0
12 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Lowering of submersible pumping machineries in Newly sunk RBTW No-14 at Baidyanathpur Pump house under Ukhra Water Supply Scheme. | Assistant Engineer-II | Junior Engineer-5 | ORD/000037/2024-2025 | 1039/AMD | 16/07/2024 | 30/08/2024 | EASTERN INDIA SALES AND SERVICE | 8.15 | 0 | 0 | 0
13 | PASCHIM BARDHAMAN |  | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Acceptance cum Work Order for Sinking of 4 (Four) nos river bed tube wells including collecting main and other allied works at Damodar river under (Part-II) Unionpara Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer 10 | ORD/000974/2023-2024 | 492/RCD-I | 12/02/2024 | 13/03/2024 | TARA MA ENTERPRISE | 13.02 | 1.43 | 11.01 | 25
14 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Providing and Installation of Submersible pumping Machineries at newly sunk River Bed Tube Well No-8 at Union Para Low Lift under Ballavpur Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-5 | ORD/000046/2024-2025 | 1132/AMD | 30/07/2024 | 28/09/2024 | HINDUSTHAN CONSULTANT FIRM | 4.84 | 0 | 0 | 0
15 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Providing and Installation of Submersible Pumping machineries in the Newly sunk RBTWs no-13 at Surjanagar Low lift Pump House under ASTA W/S Scheme. | Assistant Engineer-II | Junior Engineer-5 | ORD/000049/2024-2025 | 1135/AMD | 30/07/2024 | 28/09/2024 | M/S S.G.ENTERPRISE | 9.75 | 0 | 0 | 0
16 | PASCHIM BARDHAMAN |  | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Continuation work order for Sinking of 6 (Six) nos 200 mm dia river bed tube well including collecting main in the river of Damodar at Surjanagar under Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000994/2023-2024 | 295/A/RCD-I | 06/02/2024 | 07/03/2024 | MAK CONSTRUCTION CO | 22.57 | 7.07 | 31.33 | 100
17 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Lowering of submersible pumping machineries in Newly sunk RBTW No-15 at Baidyanathpur Pump house under Ukhra Water Supply Scheme. | Assistant Engineer-II | Junior Engineer-5 | ORD/000075/2024-2025 | 1206/AMD | 07/08/2024 | 21/09/2024 | INDUSTRIAL ELECTRICAL CORPORATION | 8.18 | 0 | 0 | 0
18 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Providing and Installation of Submersible Pumping machineries in the Newly sunk RBTWs from 07-11 at Surjanagar Low lift Pump House under ASTA W/S Scheme. | Assistant Engineer-II | Junior Engineer-5 | ORD/000070/2024-2025 | 1201/AMD | 07/08/2024 | 21/09/2024 | M/S JIT ENTERPRISE | 8.85 | 0 | 0 | 100
19 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Lowering of submersible pumping machineries in Newly sunk RBTW No-7 at Tirat Colliery Lowlift Pump House under Tirat Colliery Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-5 | ORD/000047/2024-2025 | 1133/AMD | 30/07/2024 | 28/09/2024 | PESTCO INDIA | 8.93 | 0 | 0 | 100
20 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Lowering of submersible pumping machineries in Newly sunk RBTW No-6 at Tirat Colliery Low lift Pump House under Tirat Colliery Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-5 | ORD/000071/2024-2025 | 1202/AMD | 07/08/2024 | 21/09/2024 | PESTCO INDIA | 4.97 | 0 | 0 | 100
21 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Lowering of submersible pumping machineries in Newly sunk RBTW No-5 at Tirat Colliery Lowlift Pump House under Tirat Colliery Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-5 | ORD/000035/2024-2025 | 1037/AMD | 16/07/2024 | 30/08/2024 | PESTCO INDIA | 8.93 | 0 | 0 | 100
22 | PASCHIM BARDHAMAN |  | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Acceptance cum Work Order for Sinking of 3 (Three) nos river bed tube wells including collecting main manifold sluice valve chamber reinforcement and other allied works at Damalia H/W under RCFA Part-II at Damodar river under Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. (Part-A) | Assistant Engineer 2 | Junior Engineer 12 | ORD/000969/2023-2024 | 485/RCD-I | 12/02/2024 | 08/03/2024 | SOMNATH SAMANTA | 19.46 | 9.72 | 49.97 | 100
23 | PASCHIM BARDHAMAN |  | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Acceptance cum work order for Additional work for Providing FHTC within command area of Zone - VII under RCFA Division-I PHE Dte. (Part-F) | Assistant Engineer 2 |  | ORD/000109/2024-2025 | 2131/RCD-I | 27/08/2024 | 26/09/2024 | GITA CONSTRUCTION | 54.9 | 0 | 0 | 0
24 | PASCHIM BARDHAMAN |  | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Acceptance cum work order for Balance work of Laying & Pushing of 600 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at Pathan Dahwra of Murgasole Mouza under Augmentation for Sub Surface Water Based Piped Water Supply Scheme under RCFA, Division-1, P.H.E. Dte. | Assistant Engineer 2 |  | ORD/000106/2024-2025 | 2126/RCD-I | 27/08/2024 | 21/09/2024 | DAS & CHAKRABORTY | 7.38 | 0 | 0 | 0
25 | PASCHIM BARDHAMAN |  | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Acceptance cum work order for Additional work for Making interconnection construction of drain, approach road and allied works at Panuria OHR site within Part-I of Augmentation of Panuria W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000105/2024-2025 | 2125/RCD-I | 27/08/2024 | 26/09/2024 | A CONSTRUCTION CO | 17.8 | 0 | 0 | 0
26 | PASCHIM BARDHAMAN |  | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Acceptance cum work order for Laying of 150 mm MS water pipe with 600 mm casing pipe for underground Railway track crossing by Jack Pushing method between Andal and Kajora gram Station at KM 01/33-01/35 and other allied works under (Zone-5) of Andal Block under RCFA Div-I,PHE Dte | Assistant Engineer 2 |  | ORD/000088/2024-2025 | 2113/RCD-I | 27/08/2024 | 26/09/2024 | M/S UNIT CONSTRUCTION | 76.77 | 0 | 0 | 0
27 | PASCHIM BARDHAMAN |  | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Acceptance cum work order for Additional supplying laying and aligning of distribution system including FHTC for Shyamla W/S Scheme in Chatrisganda Mouza, Block Jamuria Paschim Bardhaman under Shyamla W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000114/2024-2025 | 2137/RCD-I | 27/08/2024 | 11/10/2024 | DAWN CONSTRUCTION | 38 | 0 | 0 | 0
28 | PASCHIM BARDHAMAN |  | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Acceptance cum work order for Balanced work Sinking of 03 (Three) nos. 200 mm dia river bed tube well in the river of Ajoy (Pandabeswar H/W Site) for Source Augmentation of RCFA Part-II W/S Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000083/2024-2025 | 2108/RCD-I | 27/08/2024 | 26/09/2024 | B.T.M. CONCERN | 23.41 | 5.96 | 25.45 | 70
29 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Lowering of Submersible Pumping Machineries in the Newly sunk RBTWs Harvanga-13 & 14 to Tirat Mouza Pump House under Tirat Mouza Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-5 | ORD/000048/2024-2025 | 1134/AMD | 30/07/2024 | 28/09/2024 | M/S. SOMA ENTERPRISE | 8.55 | 0 | 0 | 90
30 | PASCHIM BARDHAMAN |  | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Acceptance cum work order for Balance work of laying distribution system by providing HDPE pipe in place of DI pipe and allied works like concrete cutting, rock cutting, bituminous road cutting at Murgathol of Augmentation of Amritnagar Zone-I PWSS under RCFA Division-I PHE Dte | Assistant Engineer 2 |  | ORD/000143/2024-2025 | 2244/RCD-1 | 11/09/2024 | 10/11/2024 | DAS & CHAKRABORTY | 62.2 | 0 | 0 | 0
Total | [13 empty] | 600.07 | 76.51 | 12.75