## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Emergent sinking of one no 200 x 165 mm dia rig bore tube well at ESI Hospital near staff quarter Kali Mandir, Paschim Bardhaman under RCFA Division-I PHE Dte. | Assistant Engineer 4 | Junior Engineer 12 | ORD/000001/2024-2025 | Camp_02_ESI_Hospital_AE_I | 16/04/2024 | 23/04/2024 | M/S CHANDI CHARAN ROY | 8.1 | 0 | 0 | 100
2 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Providing and Installation of Submersible Pumping machineries in the Newly sunk RBTWs no-13 at Surjanagar Low lift Pump House under ASTA W/S Scheme. | Assistant Engineer-II | Junior Engineer-5 | ORD/000049/2024-2025 | 1135/AMD | 30/07/2024 | 28/09/2024 | M/S S.G.ENTERPRISE | 9.75 | 0 | 0 | 0
3 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Providing and Installation of Submersible pumping Machineries at newly sunk River Bed Tube Well no-9 and 10 at Narayankuri Pump House under Source Augmentation of RCFA Part-II Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-5 | ORD/000438/2024-2025 | 2096/AMD | 12/12/2024 | 11/01/2025 | PREMNATH MITRA | 9.89 | 0 | 0 | 0
4 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Lowering of submersible pumping machineries in Newly sunk RBTW No-7 at Tirat Colliery Lowlift Pump House under Tirat Colliery Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-5 | ORD/000047/2024-2025 | 1133/AMD | 30/07/2024 | 28/09/2024 | PESTCO INDIA | 8.93 | 8.87 | 99.35 | 100
5 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Lowering of submersible pumping machineries in Newly sunk RBTW No-6 at Tirat Colliery Low lift Pump House under Tirat Colliery Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-5 | ORD/000071/2024-2025 | 1202/AMD | 07/08/2024 | 21/09/2024 | PESTCO INDIA | 4.97 | 4.92 | 98.83 | 100
6 | PASCHIM BARDHAMAN |  | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Continuation work order for Sinking of 6 (Six) nos 200 mm dia river bed tube well including collecting main in the river of Damodar at Surjanagar under Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000994/2023-2024 | 295/A/RCD-I | 06/02/2024 | 07/03/2024 | MAK CONSTRUCTION CO | 22.57 | 17.67 | 78.32 | 100
7 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Lowering of submersible pumping machineries in Newly sunk RBTW No-5 at Tirat Colliery Lowlift Pump House under Tirat Colliery Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-5 | ORD/000035/2024-2025 | 1037/AMD | 16/07/2024 | 30/08/2024 | PESTCO INDIA | 8.93 | 8.87 | 99.35 | 100
8 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Lowering of Submersible Pumping Machineries in the Newly sunk RBTWs Harvanga-13 & 14 to Tirat Mouza Pump House under Tirat Mouza Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-5 | ORD/000048/2024-2025 | 1134/AMD | 30/07/2024 | 28/09/2024 | M/S. SOMA ENTERPRISE | 8.55 | 6.95 | 81.27 | 100
9 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Providing and Installation of Submersible Pumping machineries in the Newly sunk RBTWs from 07-11 at Surjanagar Low lift Pump House under ASTA W/S Scheme. | Assistant Engineer-II | Junior Engineer-5 | ORD/000070/2024-2025 | 1201/AMD | 07/08/2024 | 21/09/2024 | M/S JIT ENTERPRISE | 8.85 | 8.83 | 99.7 | 100
10 | PASCHIM BARDHAMAN |  | RCFA Division -I | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Acceptance cum Work Order for Sinking of 4 (Four) nos river bed tube wells including collecting main and other allied works at Damodar river under (Part-II) Unionpara Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer,Junior Engineer 10 | ORD/000974/2023-2024 | 492/RCD-I | 12/02/2024 | 13/03/2024 | TARA MA ENTERPRISE | 13.02 | 2.87 | 22.03 | 100
11 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Lowering of Submersible Pumping Machineries for Newly Sunk RBTW No-03 for CWR at Ajoy Ghat Pumping Station under Churulia Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-5 | ORD/000038/2024-2025 | 1040/AMD | 16/07/2024 | 09/12/2025 | PREMNATH MITRA | 10.27 | 0 | 0 | 100
12 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Supply & Installation of submersible pumping machineries at Newly sunk 8 Nos Low Lift RBTWs at Madanpur Lowlift under Source Augmentation of RCFA Part-II Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-5 | ORD/000024/2025-2026 | 944/AMD | 16/05/2025 | 15/06/2025 | BENGAL CONSTRUCTION | 24.61 | 0 | 0 | 0
13 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | SM/18891 | Augmentation | Installation of transformer(315 KVA), Supply, delivery and installation S/M, Pump-Motor set, and other allied works at Madanpur Head Works Site under RCFA Part-II Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-5 | ORD/000069/2025-2026 | 1108/AMD | 16/06/2025 | 16/07/2025 | M/S SAJAHAN CHOWDHURY | 37.68 | 0 | 0 | 0
Total | [13 empty] | 176.13 | 58.97 | 33.48