## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Continuation order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Domra mouza (JL-68) under command area of Tilakchandrapur piped W/S Scheme at Kanksa Block under Durgapur W/S Division, PHE Dte |  |  | ORD/000306/2021-2022 | 1663/DWSD | 25/11/2021 | 05/12/2021 | AMARANJALI CONSTRUCTION | 4.97 | 0 | 0 | 0
2 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Formal order for the work of Providing additional number of FHTC and laying of branch pipe line from existing pipe line in connection with JJM for Basuhda Mouza (JL_35) under command area of Basudha W/s Scheme at Kanksa block under DWSD ,PHE Dte (SL-06) |  |  | ORD/000117/2021-2022 | 1376/DWSD | 17/09/2021 | 16/11/2021 | M/S S. CHOUDHURY | 38.92 | 40.02 | 102.82 | 0
3 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Formal order for the work of Supplying and laying of 140 mm dia UPVC pipe line from Hetedoba OHR to Jhajra more for water supply of Sarpi more ,Jhanjra gram and Adibasipara of Jamgora under Jamgora-Jagannathpur piped W/s Scheme.(SL-07) |  |  | ORD/000118/2021-2022 | 1371/DWSD | 17/09/2021 | 07/10/2021 | MD AAMIR KHAN | 23.48 | 0 | 0 | 0
4 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal order for the work of Extension of pipe line from existing pipe line and replace old damaged AC pipe line with HDPE pipe of Kanksa Zone-I W/s Scheme to combat draught like situation in Kanksa block to providing FHTC at Shilampur Gosh Para Mouza JL-89 under DWSD ,PHE Dte (SL-10) |  |  | ORD/000137/2021-2022 | 1320/DWSD | 14/09/2021 | 29/09/2021 | MAK CONSTRUCTION CO. | 4.91 | 9.83 | 200 | 0
5 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal order for the work of Supplying ,fitting and fixing of CI special ,valve construction of Sluice valve chamber & others allied work for distribution system of entire command area of Gourbazar OHR site under Gourbazar-Ichhapur piped W/S Scheme under DWSD,PHE Dte (SL-16) |  |  | ORD/000138/2021-2022 | 1177/DWSD | 02/08/2021 | 17/08/2021 | JOY GURU ENTERPRISE | 4.36 | 0 | 0 | 0
6 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal order for the work of Supply fitting fixing and installation of sluice valve for O & Mtc of Kanksa (Zone-II (Ph-II) W/s Scheme command area of Panagarh ,Prayagpur Mouza under DWSD ,PHE Dte. (SL-13) |  |  | ORD/000141/2021-2022 | 1322/DWSD | 14/09/2021 | 29/09/2021 | TARA CONSTRUCTION | 4.93 | 0 | 0 | 0
7 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal order for the work of Emergent supply fitting ,fixing of sluice valve for repairing and maintenance of pipe line under command area of Jamgora-Jagannathpur W/s Scheme under DWSD, PHE Dte(SL-30). |  |  | ORD/000146/2021-2022 | 1184/DWSD | 06/08/2021 | 26/08/2021 | TARA CONSTRUCTION | 3.86 | 0 | 0 | 0
8 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal order for the work of Emegent supply ,fitting -fixing of Sluice valve for repairing and maintenance of pipe line under command area from Sarpi village,Amlouka,Patseura,Arati,Jabuna areas of Gourbazar-Ichhapur piped W/s Scheme under DWSD ,PHE Dte (SL-01) |  |  | ORD/000167/2021-2022 | 1338/DWSD | 14/09/2021 | 29/09/2021 | MD AAMIR KHAN | 4.56 | 0 | 0 | 0
9 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal order for the Work of Emergent supplying, fitting fixing of Sluice valve for repairing and maintenance of ppe line under command are a of Ichhapur areas of Gourbazar-Ichhapur piped W/s Scheme under DWSD ,PHE Dte (SL-02) |  |  | ORD/000168/2021-2022 | 1339/DWSD | 14/09/2021 | 04/10/2021 | MD AAMIR KHAN | 4.42 | 0 | 0 | 0
10 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal order for the work of Cleaning the chokage of AC Pipe line of 80 /100/150 mm dia for providing water supply to Arrah Mouza & other allied works for providing FHTC of Roopgnaj W/s Scheme under DWSD ,PHE Dte (SL-34) |  |  | ORD/000165/2021-2022 | 1336/DWSD | 14/09/2021 | 24/09/2021 | M/S KALYANI ENTERPRISE | 4.14 | 0 | 0 | 0
11 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal order for the work of Extension of pipe line from existing pipe line of Jamgora-Jagannathpur W/s Scheme to combat draught like situation in Durgapur-Faridpur block to provide FHTC at Banerjeepara,Mukherjee para ,Bouri Para ,Harimandir ,Durgamandir of Nachan Gram from Nachan bypass of Nachan Mouza (JL-39) (Part-B) under DWSD, PHE Dte(SL-18) |  |  | ORD/000157/2021-2022 | 1326/DWSD | 14/09/2021 | 29/09/2021 | BABA LOKENATH ENTERPRISE | 4.5 | 0 | 0 | 0
12 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Continuation order for the work of Additional work for providing FHTC in connection with JJM at Jamgora (JL-23) block-Durgapur-Faridpur,Pachim Bardhaman under Jamgora-Jagannathpur piped W/s Scheme under DWD, PHE Dte (Part-A) |  |  | ORD/000178/2021-2022 | 1273/DWSD | 02/09/2021 | 17/09/2021 | RANJIB GHATAK | 4.21 | 0 | 0 | 0
13 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Continuation for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Sarpi mouza (JL-35) (Pt-A) under command area of Gourbazar-Ichhapur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte.(SL-29) |  |  | ORD/000122/2021-2022 | 1225/DWSD | 19/08/2021 | 29/08/2021 | KIRON ENTERPRISE | 1.22 | 2.27 | 186.49 | 0
14 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Continuation order for the work of Continuation for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Sarpi mouza (JL-35) (Pt-A) under command area of Gourbazar-Ichhapur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte.(SL-29) |  |  | ORD/000123/2021-2022 | 1214/DWSD | 17/08/2021 | 01/09/2021 | KIRON ENTERPRISE | 4.84 | 9.72 | 200.65 | 0
15 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Formal order for the work of Additional functional house hod tap connection FHTC in connection with JJM at Nachan mouza (JL-39) under command area of Jamgora-Jagannathpur piped W/s Scheme block -Durgapur-Faridpur under DWSD, PHE Dte (SL-03) |  |  | ORD/000202/2021-2022 | 1634/DWSD | 22/11/2021 | 22/12/2021 | BABA LOKENATH ENTERPRISE | 11.05 | 11.1 | 100.42 | 0
16 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal order for the work of Emergency repairing and restoration of distribution system of Nachan ,Bansia, Dhabani Labnapara for providing sufficient water to every house hold of Gourbazar -Ichhapur piped W/s Scheme under DWSD ,PHE Dte(SL-01) |  |  | ORD/000131/2021-2022 | 1162/DWSD | 02/08/2021 | 17/08/2021 | M/S MONDAL ENTERPRISE | 4.75 | 0 | 0 | 0
17 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Formal for the work of Additional FHTC in connection with JJM at Hetedoba Mouza under command area of Gourbazar-Ichhapur piped W/S Scheme of Durgapur-Faridpur block under DWSD PHE Dte . |  |  | ORD/000297/2021-2022 | 1779/DWSD | 21/12/2021 | 15/01/2022 | RANAJOY ENTERPRISE | 9.62 | 8.76 | 91.06 | 0
18 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Formal order for the work of Providing additional number of FHTC in connection with JJM for Roopganj mouza(JL-91) with extension of branch pipe line at Roopganj and Arrah under command are a of Roopganj W/S Scheme at Kanksa block under DWSD ,PHE Dte |  |  | ORD/000295/2021-2022 | 1783/DWSD | 21/12/2021 | 20/01/2022 | M/S KALYANI ENTERPRISE | 17.08 | 17.39 | 101.83 | 0
19 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal order for the work of Water supply arrangement at different places to combat water crisis at Bonsal,Hetedoba,Jabber Pally & Hetedoba, block - Durgapur-Faridpur of Ichhapur GP under DWSD, PHE Dte . (SL-28) |  |  | ORD/000145/2021-2022 | 1183/DWSD | 06/08/2021 | 21/08/2021 | JOY GURU ENTERPRISE | 3.21 | 0 | 0 | 0
20 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal order for the work of Bypass connection from existing R/M at Gopalpur OHR site and jungle cutting at head work site Pump house Site -II and III of Gopalpur W/s Scheme under DWSD,PHE Dte .(SL-29) |  |  | ORD/000163/2021-2022 | 1333/DWSD | 14/09/2021 | 29/09/2021 | QUICK PAL SUPPLIERS | 4.94 | 0 | 0 | 0
21 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Formal order for the work of sinking 1 No. 250 mm X 150 mm dia tube well 90 mtr deep by DR method using PVC pipe and fiber glass reinforced epoxy resin slotted at Krishnapur H/W site (OHR) under Krishnapur W/s Scheme under Durgapur W/s Division, PHE Dte |  |  | ORD/000327/2020-2021 | 41/DWSD | 13/01/2021 | 23/01/2021 | AMARANJALI CONSTRUCTION | 7.02 | 0 | 0 | 0
22 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal order for the work of Laying of additional distribution pipe line with necessary allied works at Matwangini more to Bhabandapur village road of Gourbazar-Ichhapur piped W/S Scheme under DWSD,PHE Dte |  |  | ORD/000357/2021-2022 | 74/DWSD | 21/01/2022 | 10/02/2022 | R.K.ENTERPRISE | 4.99 | 0 | 0 | 0
23 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Formal order for the work of Emergency repairing and restoration of distribution system from command are a of Jagannathpur OHR (Gopendanga ,Kalinagar,Jagannathpur,Kailashpur part) Jamgora-Jagannathpur piped W/s Scheme under DWSD, PHE Dte. |  |  | ORD/000296/2021-2022 | 1778/DWSD | 20/12/2021 | 09/01/2022 | M/S BADAL GHOSH | 5.54 | 0 | 0 | 0
24 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Continuation order for the work of Additional work for providing FHTC in connection with JJM at Jamgora (JL-23) block-Durgapur-Faridpur,Pachim Bardhaman under Jamgora-Jagannathpur piped W/s Scheme under DWD, PHE Dte (Part-C) |  |  | ORD/000179/2021-2022 | 1290/DWSD | 07/09/2021 | 22/09/2021 | RANJIB GHATAK | 3.75 | 3.75 | 99.97 | 0
25 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal order for the work of Emergency repairing and restoration of distribution system from command area of Gourbazar OHR (Gourbazar-Srikrishanapur,Kailashpur(Part) for providing sufficient Water to every house holds under Gourbazar-Ichhapur piped W/s Scheme under DWSD ,PHE Dte (Part-B) (SL-03) |  |  | ORD/000133/2021-2022 | 1164/DWSD | 02/08/2021 | 17/08/2021 | JOY GURU ENTERPRISE | 3.49 | 0 | 0 | 0
26 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Continuation order for the work of Additional work for providing FHTC in connection with JJM at Jamgora (JL-23) block-Durgapur-Faridpur,Pachim Bardhaman under Jamgora-Jagannathpur piped W/s Scheme under DWD, PHE Dte (part-B) |  |  | ORD/000177/2021-2022 | 1283/DWSD | 06/09/2021 | 21/09/2021 | RANJIB GHATAK | 4.12 | 3.86 | 93.62 | 0
27 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal order for the work of Laying of additional distribution pipe line with necessary allied works at Bansal Kamala Park, DMC area of Vivekananda Nagar under retrofitting's of Gourbazar -Ichhapur piped W/S scheme under DWSD ,PHE Dte (Part-C) (SL No-06) |  |  | ORD/000319/2021-2022 | 1792/DWSD | 23/12/2021 | 07/01/2022 | JOY GURU ENTERPRISE | 4.96 | 4.93 | 99.45 | 0
28 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal order for the work of Laying of additional distribution pipe line with necessary allied works at Protapur mouza (JL-40) under Jamgora-Jagannathpur Piped W/s Scheme under DWSD,PHE Dte (SL-07) |  |  | ORD/000320/2021-2022 | 1793/DWSD | 23/12/2021 | 07/01/2022 | JAYANTA DATTA | 4.56 | 4.54 | 99.66 | 0
29 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Formal order for the work of Additional work for providing FHTC in connection with JJM for Radhamohanpur Mouza(JL-36) under command area of Basudha piped W/S Scheme ,Block-Kanksa under DWSD,PHE Dte (SL-04) |  |  | ORD/000259/2021-2022 | 1706/DWSD | 08/12/2021 | 07/01/2022 | MD AAMIR KHAN | 24.05 | 24.6 | 102.32 | 0
30 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal order for the work of Laying of additional distribution pipe line with necessary allied works at Bansal Kamala Park ,Majhipara and Bouri Para under retrofitting's of Gourbazar -Ichhapur piped W/S scheme under DWSD ,PHE Dte (Part-B)(SL-05) |  |  | ORD/000318/2021-2022 | 1791/DWSD | 23/12/2021 | 07/01/2022 | JOY GURU ENTERPRISE | 4.93 | 4.92 | 99.87 | 0
31 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Formal order for the work of Additional work for providing FHTC in connection with JJM for Shilampur Mouza(JL-90) under command area of Kanksa (Zone-I) piped W/S Scheme ,Block-Kanksa under DWSD,PHE Dte |  |  | ORD/000260/2021-2022 | 1707/DWSD | 08/12/2021 | 07/01/2022 | MD AAMIR KHAN | 42.05 | 43.15 | 102.61 | 0
32 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal order for the work of additional laying of pipe line and repairing of damage road with concrete work at Sarpi (Mouza-35) under command area of retrofitting of improvement of Gourbazar-Ichhapur W/s Scheme under DWSD ,PHE Dte (SL-02) |  |  | ORD/000273/2021-2022 | 1553/DWSD | 27/10/2021 | 16/11/2021 | K.M. ENTERPRISE | 2.3 | 0 | 0 | 0
33 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal order for the work of repairing of existing distribution pipe line with 110 mm UPVC line and necessary allied works at Nakrakonda village under RCFA Pt-III W/s Scheme under DWSD, PHE Dte (SL-12) |  |  | ORD/000367/2021-2022 | 98/DWSD | 28/01/2022 | 12/02/2022 | RANAJOY ENTERPRISE | 1.25 | 0 | 0 | 0
34 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal order for the work of Laying of additional distribution pipe line with necessary allied works at Jabber Pally ,Bansal Vadupara under retrofitting's of Gourbazar -Ichhapur piped W/S scheme under DWSD ,PHE Dte (Part-A)(SL-04) |  |  | ORD/000317/2021-2022 | 1790/DWSD | 23/12/2021 | 07/01/2022 | JOY GURU ENTERPRISE | 5 | 5 | 99.97 | 0
35 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal order for the work of Supplying and laying of laying 75 mm dia HDPE pipe line at Prayagpur canal per in Kanksa block to providing FHTC at Prayagpur mouza (JL-88) (Part-A) under DWSD ,PHE Dte (SL-10) |  |  | ORD/000323/2021-2022 | 1796/DWSD | 24/12/2021 | 08/01/2022 | CHATTERJEE CONSTRUCTION | 4.98 | 5.01 | 100.49 | 0
36 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum Formal work-Order for the work of ---Replacement of damage existing distribution pipe line with 75 mm UPVC line and necessary allied works at Loudoha village Palpara,Ghosh Para & Banerjee para under RCFA Pt-III W/s Scheme under DWSD ,PHE Dte (SL-3) |  |  | ORD/000283/2021-2022 | 1575/DWSD | 27/10/2021 | 11/11/2021 | D. S. ENTERPRISE | 4.67 | 0 | 0 | 0
37 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Formal for the work of Emergency provision of AC phtovoltaic submersible solar pump set within bore well tube well along with 2400 peak watt capacity soalr photovoltaic array on Ms structure with sinking of 150 mm dia tube well 90 mtr deep by DR ring method using PVC pipe and fiber glass reinforced epoxy resin slotted to meet up water demand during summer season at Kalinagar under GP-Pratabpur Block-Durgapur-Faridpur under DWSD, PHE Dte |  |  | ORD/000313/2021-2022 | 1776/DWSD | 20/12/2021 | 19/01/2022 | M/S BADAL GHOSH | 11.69 | 0 | 0 | 0
38 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal order for the work of Water supply arrangement at Maheshpur village within Durgapur-Faridpur Block to combat waters crisis and protection of RCC Columns within Tumuni river near Jagannathpur village under DWSD, PHE Dte(SL-5) |  |  | ORD/000281/2021-2022 | 1572/DWSD | 27/10/2021 | 11/11/2021 | M/S BADAL GHOSH | 1.98 | 0 | 0 | 0
39 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Continuation order for the work of Balance work for Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Gopendanga mouza (JL-94) under command area of Jamgora-Jagannathpur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte. |  |  | ORD/000307/2021-2022 | 1662/DWSD | 25/11/2021 | 05/12/2021 | BADAL GHOSH | 1.91 | 1.91 | 99.91 | 0
40 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Continuation order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Mahespur mouza (JL-12) under command area of Jamgora-Jagannathpur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte. |  |  | ORD/000308/2021-2022 | 1746/DWSD | 15/12/2021 | 25/12/2021 | BADAL GHOSH | 3.96 | 3.96 | 99.89 | 0
41 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Continuation for the work of providing functional household tap connection (FHTC) in connection with JJM at Srikrishnapur mouza (JL No-09),Baidayanathpur and Kailashpur(JL No-09/20/22) under Retrofitting of Gourbazar-Ichhapur piped W/s Scheme under DWSD,PHE Dte. |  |  | ORD/000415/2021-2022 | 266/DWSD | 04/03/2022 | 19/03/2022 | JOY GURU ENTERPRISE | 3.6 | 3.58 | 99.22 | 0
42 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal order for the work of Extension of laying 75 mm dia HDPE pipe line at Prayagpur canal Par in Kanksa block to providing FHTC at Prayagpur mouza (JL-88) (Part-B) under DWSD ,PHE Dte (SL-09) |  |  | ORD/000322/2021-2022 | 1795/DWSD | 24/12/2021 | 08/01/2022 | CHATTERJEE CONSTRUCTION | 3.26 | 3.33 | 102.03 | 0
43 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal order for the work of Additional distribution pipe line with necessary allied works for FHTC purpose at Jagannathpur gram,Jagganathpur Dangal para to Kailashpur upper para ,Kalinagar main road to upper para ,Gopendanga main road to Bagdi para under Improvement of Jamgora-Jagannathpur Piped W/s Scheme under DWSD,PHE Dte |  |  | ORD/000328/2021-2022 | 1802/DWSD | 27/12/2021 | 16/01/2022 | M/S BADAL GHOSH | 3.99 | 3.99 | 99.94 | 0
44 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Banguri mouza (JL-52) under command area of Gourbazar-Ichhapur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte.(SL-01) |  |  | ORD/000370/2020-2021 | 142/DWSD | 28/01/2021 | 27/02/2021 | SUBHADEEP DAS | 7.7 | 6.82 | 88.59 | 0
45 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Formal order for the work of Supplying laying of 90 mm dia UPVC pipe bypass connection for Amlouka gram from Banguri more of Improvement of Jamgora-Jagannathpur W/s Scheme under DWSD ,PHE Dte (SL-02) |  |  | ORD/000346/2021-2022 | 135/DWSD | 02/02/2022 | 17/02/2022 | MD JAWED KHAN | 6.6 | 0 | 0 | 50
46 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Formal work- order for the work of ----Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Basudebpur mouza (JL-5)under command area of Kanchanpur W/s Scheme Kanksa Block under Durgapur W/S Division, PHE Dte.(SL-03) |  |  | ORD/000075/2020-2021 | 930/DWSD | 22/09/2020 | 06/11/2020 | MACHINO TECHNO | 15.79 | 26.46 | 167.58 | 0
47 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Arrah mouza (JL-91) (Pt-B) under command area of Roopganj W/S Scheme at Kanksa Block under Durgapur W/S Division, PHE Dte |  |  | ORD/000373/2020-2021 | 145/DWSD | 28/01/2021 | 19/03/2021 | M/S KALYANI ENTERPRISE | 36.43 | 32.48 | 89.15 | 0
48 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Debipur mouza (JL-87) (Pt-B) under command area of Kanksa Zone-II (Ph-II) W/S Scheme at Kanksa Block under Durgapur W/S Division, PHE Dte (SL-08) |  |  | ORD/000311/2020-2021 | 1437/DWSD | 28/12/2020 | 26/02/2021 | M/S. D. PALIT & CO. | 42.74 | 57.64 | 134.88 | 0
49 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal work order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Satkahania mouza (JL-34) under command area of Basudha W/S Scheme at Kanksa Block under Durgapur W/S Division, PHE Dte (SL-12) |  |  | ORD/000315/2020-2021 | 1440/DWSD | 28/12/2020 | 22/01/2021 | SUBHADEEP DAS | 8.66 | 15.2 | 175.54 | 0
50 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum Formal work-Order for the work of ---Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Dubrajpur,Sashipur,Benodpur,Sundipur,Talbahari,Srirampur Mouzas (JL-9,8,6,4,3,1)under command area of Kanchanpur W/S Scheme at Kanksa Block under Durgapur W/S Division, PHE Dte |  |  | ORD/000318/2020-2021 | 1443/DWSD | 28/12/2020 | 27/01/2021 | MACHINO TECHNO | 27.32 | 45.74 | 167.39 | 0
51 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum Formal work-Order for the work of ---Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JJM) at Panagarh mouza (JL-85) (Part-B) under command area of Kanksa Zone-II(Ph-II) piped W/s Scheme of of Kanksa Block under Durgapur W/S Division, PHE Dte |  |  | ORD/000319/2020-2021 | 1445/DWSD | 28/12/2020 | 22/01/2021 | GITA CONSTRUCTION | 17.07 | 27.86 | 163.23 | 0
52 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Kanksa (CT) mouza (JL-86) (Pt-E) under command area of Kanksa Zone-II (Ph-I) W/S Scheme at Kanksa Block under Durgapur W/S Division, PHE Dte (SL-01) |  |  | ORD/000305/2020-2021 | 1431/DWSD | 28/12/2020 | 26/02/2021 | SWATI CORPARATION | 42.78 | 87.48 | 204.5 | 0
53 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal workorder for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Kanksa (CT) mouza (JL-86) (Pt-F) under command area of Kanksa Zone-II (Ph-I) W/S Scheme at Kanksa Block under Durgapur W/S Division, PHE Dte (SL-05) |  |  | ORD/000308/2020-2021 | 1434/DWSD | 28/12/2020 | 11/02/2021 | TARA CONSTRUCTION | 27.72 | 56.89 | 205.19 | 0
54 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Shyamsundarpur mouza (JL-07) (Pt-B) under command area of Gourbazar-Ichhapur W/s Scheme of Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte .(SL-02) |  |  | ORD/000379/2020-2021 | 171/DWSD | 03/02/2021 | 28/02/2021 | PRAVAT SARKAR | 37.43 | 63.5 | 169.64 | 0
55 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JJM) at Kanchanpur mouza (JL-02) under command area of Kanchanpur piped W/s Scheme of Kanksa Block under Durgapur W/S Division, PHE Dte.(SL-15) |  |  | ORD/000259/2020-2021 | 1318/DWSD | 09/12/2020 | 23/01/2021 | MRITYUNJOY MUKHERJEE AND CO | 17.56 | 29.42 | 167.51 | 0
56 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JJM) at Ayma Biswanathpur & Gangbil mouza (JL-82 & 83) under command area of Kanksa Zone-I piped W/s Scheme of of Kanksa Block under Durgapur W/S Division, PHE Dte (SL-22) |  |  | ORD/000267/2020-2021 | 1363/DWSD | 10/12/2020 | 24/01/2021 | MD AAMIR KHAN | 41.61 | 83.23 | 199.99 | 0
57 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal work order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JJM) at Basudha mouza (JL-35) under command area of Basudha piped W/s Scheme of of Kanksa Block under Durgapur W/S Division, PHE Dte (SL-18) |  |  | ORD/000263/2020-2021 | 1321/DWSD | 09/12/2020 | 23/01/2021 | M/S S. CHOUDHURY | 42.77 | 82.12 | 191.99 | 0
58 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JJM) at Pryagpur mouza (JL-88) under command area of Kanksa Zone-II(Ph-II) (Pt-A) piped W/s Scheme of of Kanksa Block under Durgapur W/S Division, PHE Dte.(Sl-19) |  |  | ORD/000264/2020-2021 | 1322/DWSD | 09/12/2020 | 23/01/2021 | DAS & CHAKRABORTY | 43.55 | 87.22 | 200.3 | 0
59 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JJM) at Debipur mouza (JL-87) under command areaof Kanksa Zone-II(Ph-II) piped W/s Scheme of of Kanksa Block under Durgapur W/S Division, PHE Dte.(SL-21) |  |  | ORD/000265/2020-2021 | 1313/DWSD | 09/12/2020 | 23/01/2021 | M/S. D. PALIT & CO. | 43.64 | 82.83 | 189.79 | 0
60 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum Formal work-Order for the work of ---Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Kanksa (CT) mouza (JL-86) (Pt-A) under command area of Kanksa Zone-II (Ph-I) W/S Scheme at Kanksa Block under Durgapur W/S Division, PHE Dte (SL-18) |  |  | ORD/000321/2020-2021 | 1448/DWSD | 28/12/2020 | 26/02/2021 | GITA CONSTRUCTION | 42.61 | 76.74 | 180.09 | 0
61 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal work order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Prayagpur mouza (JL-88) (Pt-B) under command area of Kanksa Zone-II (Ph-I) W/S Scheme at Kanksa Block under Durgapur W/S Division, PHE Dte |  |  | ORD/000314/2020-2021 | 1439/DWSD | 28/12/2020 | 22/01/2021 | DAS & CHAKRABORTY | 7.24 | 7.33 | 101.19 | 0
62 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum Formal work-Order for the work of ---Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Basudha mouza (JL-35) (Pt-B)under command area of Basudha W/S Scheme at Kanksa Block under Durgapur W/S Division, PHE Dte |  |  | ORD/000317/2020-2021 | 1442/DWSD | 28/12/2020 | 22/01/2021 | SAIKAT RAY | 17.42 | 33.88 | 194.56 | 0
63 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal order for the work of Extension of pipe line from existing pipe line of Kanksa (Zone-II) Ph-II W/s Scheme to combat draught like situation in Kanksa block to providing FHTC at Prayagpur Mouza(JL-88)(Part-C) under DWSD,PHE Dte |  |  | ORD/000462/2020-2021 | 317/DWSD | 26/02/2021 | 28/03/2021 | B. T. M. CONCERN | 4.98 | 4.98 | 100 | 0
64 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Formal order for the work of Laying of additional distribution pipe line with necessary allied works at Domra and Piariganj mouza distribution zone under Tilakchandrapur W/s Scheme under DWSD ,PHE Dte (SL-05) |  |  | ORD/000062/2021-2022 | 990/DWSD | 05/07/2021 | 25/07/2021 | AMARANJALI CONSTRUCTION | 11.94 | 23.82 | 199.49 | 0
65 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Formal order for the work of Extension of existing pipe line of Kanchanpur to combat drought like situation in Kanksa block to providng FHTC at Kanchanpur,Sashipu,Benodpur,Dubrajpur,Basudebpur,Talbahari mouzas repiring of leakage bursting 160 to 90 mm dia at different places ,restoration of drain village road supply of hume pipe at pump house No-II and others allied works of cmmand area under Kanchanpur piped W/s Scheme (SL-02) |  |  | ORD/000116/2021-2022 | 1291/DWSD | 07/09/2021 | 27/09/2021 | MRITYUNJOY MUKHERJEE AND CO | 12.82 | 12.7 | 99.1 | 0
66 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Formal order for the work of Additional work for providing functional houehold tap connection (FHTC) in connection with JJM at Bonsol Mouza(JL_49) ,Block-Durgapur-Faridpur ,Dist-Paschim Bardhaman under Gourbazar-Ichhapur W/s Scheme of Durgapur W/s Division, PHE Dte.(SL-01) |  |  | ORD/000101/2021-2022 | 1272/DWSD | 02/09/2021 | 01/11/2021 | JOY GURU ENTERPRISE | 22.47 | 22.45 | 99.93 | 0
67 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Formal for the work of Providing functional household tap connection (FHTC) in connection with JJM at Shyamsundarpur Mouza(JL_07) ,Block-Durgapur-Faridpur ,Dist-Paschim Bardhaman under Gourbazar-Ichhapur W/s Scheme of Durgapur W/s Division, PHE Dte.(Part-C) (SL-03) |  |  | ORD/000102/2021-2022 | 1254/DWSD | 27/08/2021 | 26/10/2021 | PRAVAT SARKAR | 27.33 | 27.3 | 99.89 | 0
68 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Formal order for the work of Additional work for providing functional household tap connection (FHTC) in connection with JJM at Bhadrapur Mouza & Basgora Mouza ,Block-Durgapur-Faridpur ,Dist-Paschim Bardhaman under Gourbazar-Ichhapur W/s Scheme of Durgapur W/s Division, PHE Dte. |  |  | ORD/000107/2021-2022 | 1253/DWSD | 27/08/2021 | 26/10/2021 | SILPO UDYOG ENGINEERING CONSTRUCTIONS | 6.7 | 6.66 | 99.42 | 0
69 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Formal order for the work of Additional work for provding FHTC in connection with JJM and Jal Swapna at Ijjatganj mouza (JL_71) under command area of kanksa (Zone-II) W/s Scheme of block-Durgapur-Fardipur under DWSD ,PHE Dte (SL-08) |  |  | ORD/000114/2021-2022 | 1375/DWSD | 17/09/2021 | 01/11/2021 | RANJIB GHATAK | 33.78 | 34.4 | 101.84 | 0
70 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal order for the work of Emergency repairing kanksa Zone-I(Ijjatganj) Phase-I W/s Scheme pipe line of entire command area for providing sufficient water to every house hold to Kanksa mouza, Ijjatganj and Prayagpur mouza under DWSD,PHE Dte(SL-02) |  |  | ORD/000183/2021-2022 | 1404/DWSD | 23/09/2021 | 13/10/2021 | DAS & CHAKRABORTY | 4.91 | 4.59 | 93.53 | 0
71 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Formal order for the work of Additional work for providing functional house hold tap connection (FHTC) in connection with JJM at Tilakchandrapur Mouza(JL_63) & Sundiara(JL-67),Block-Kanksa ,Dist.-Paschim Bardhaman under Tilakchandrapur W/s Scheme of Durgapur W/s Division, PHE Dte.(SL-05) |  |  | ORD/000103/2021-2022 | 1229/DWSD | 23/08/2021 | 07/10/2021 | S K ALIM | 15.03 | 15.01 | 99.87 | 0
72 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal order for the work of Connection provide to different Govt offices ,Schools,(Kanksa Thana,Kanksa Girls high Schools,Kanksa GP,TC Pur GP & 6 Nos ICDS at Kanksa mouza under DWSD,PHE Dte (SL-01) |  |  | ORD/000182/2021-2022 | 1403/DWSD | 23/09/2021 | 08/10/2021 | SWATI CORPORATION | 3.03 | 0 | 0 | 0
73 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal order for the work of Dismantling and reconcreting of PCC road at Prayagpur mouza for laying of branch line under command area of Kanksa Zone-II W/s Scheme for providing of FHTC under DWSD ,PHE Dte (SL-03) |  |  | ORD/000184/2021-2022 | 1405/DWSD | 23/09/2021 | 08/10/2021 | B. T. M. CONCERN | 4.55 | 1.63 | 35.92 | 0
74 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal order for the work of Additional work for providing FHTC in connection with JJM at Dhabani(JL-43) Block-Durgapur-Faridpur ,Dist-Paschim Bardhaman under Jamgora-Jagannathpur piped W/s Scheme under DWSD,PHE Dte (SL-01) |  |  | ORD/000081/2021-2022 | 1093/DWSD | 30/07/2021 | 14/08/2021 | RANJIB GHATAK | 4.44 | 8.87 | 199.9 | 0
75 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Formal order for the work of Emergency provision of AC photovoltaic submersible solar pum set within bore well /tube well along with 2400 peak watt capacity solar photovoltaic array on MS structure with sinking of 150 mm dia Tube well 150 mtr deep by DR ring method using PVC pipe and fiber glass reinforced epoxy resin slotted to meet up water demand during summer season at near DVC School Para under Pandebaswar Block under DWSD ,PHE Dte (SL-12) |  |  | ORD/000207/2021-2022 | 1596/DWSD | 08/11/2021 | 08/12/2021 | RANJIB GHATAK | 13.56 | 0 | 0 | 0
76 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal order for the work of 2 Nos trial bore by direct rotary method drilling using rig machine at Roopganj H/W Site ,Tube well No-I &II of Augmentation of Roopganj piped W/s Scheme under DWSD ,PHE Dte(SL-16) |  |  | ORD/000329/2021-2022 | 1803/DWSD | 28/12/2021 | 07/01/2022 | M/S KALYANI ENTERPRISE | 2.32 | 0 | 0 | 0
77 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Formal order for the work of Extension of pipe line from the existing pipe line from command area of Gourbazar-Ichhapur piped W/s Scheme of Ichhapur area for providing of FHTC at Ichhapur mouza(JL-50) under DWSD,PHE Dte (SL-05) |  |  | ORD/000347/2021-2022 | 140/DWSD | 03/02/2022 | 10/02/2022 | SHWET BARANI | 13.62 | 0 | 0 | 0
78 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Continuation order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Shyamsundarpur mouza (JL-07) under command area of Gourbazar-Ichhapur W/s Scheme of Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte (Part-C). |  |  | ORD/000305/2021-2022 | 1735/DWSD | 13/12/2021 | 23/12/2021 | PRAVAT SARKAR | 4.97 | 0 | 0 | 0
79 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Formal order for the work of Additional work for providing FHTC in connection with JJM for Kanksa mouzza (JL-89) under command area of Kanksa (Zone-II) Ph-II W/s Scheme at Kanksa block under DWSD ,PHE Dte (SL-03) |  |  | ORD/000348/2021-2022 | 199/DWSD | 16/02/2022 | 03/03/2022 | GITA CONSTRUCTION | 9.72 | 0 | 0 | 0
80 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal order for the work Providing FHTC in connection with JJM at Shayamsundarpur mouza(JL-07) ,Block-Durgapur-Fardipur Block ,Dist-Paschim Bardhman under Gourbazar-Ichhapur piped W/s Scheme PHE Dte (P-C) |  |  | ORD/000390/2021-2022 | 10/DWSD | 04/01/2022 | 19/01/2022 | PRAVAT SARKAR | 4.84 | 0 | 0 | 0
81 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Constinuation order for the work of Providing functional houe hold tap connection (FHTC) in connection with JJM at Shyamsundarpur mouza(JL-07) block-Durgapur-Faridpur , Dist Paschim Bardhaman under Gourbazar-Ichhapur piped W/s Scheme under DWSD,PHE Dte |  |  | ORD/000277/2021-2022 | 1643/DWSD | 23/11/2021 | 03/12/2021 | PRAVAT SARKAR | 4.96 | 1.32 | 26.56 | 0
82 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Continuation for the work of balance work for providing functional household tap connection (FHTC) in connection with JJM at Jagannathpur mouza (JL-26) under command area of Jamgora -Jagannathpur piped W/s Scheme under Durgapur-Faridpur block of DWSD,PHE Dte |  |  | ORD/000412/2021-2022 | 244/DWSD | 22/02/2022 | 19/03/2022 | M/S BADAL GHOSH | 2.09 | 0 | 0 | 0
83 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal order for the work of Supplying and laying of additional 90 mm /75 mm dia HDPE pipe line with concrete works and necessary works at Gangbill and Ayma Biswanathpur near Itvata More of Ayma Biswanathpur Mouza(JL-82 & 83) under Kanksa (Zone-I) W/s Scheme Block-Kanksa under DWSD,PHE Dte (Part-A)(SL-25) |  |  | ORD/000161/2021-2022 | 1330/DWSD | 14/09/2021 | 04/10/2021 | MAK CONSTRUCTION CO. | 4.91 | 9.76 | 198.82 | 0
84 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal work order for the work providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Bankati mouza (JL-33)under command area of Basudha W/s Scheme Kanksa Block under Durgapur W/S Division, PHE Dte(SL-18) |  |  | ORD/000222/2020-2021 | 1159/DWSD | 28/10/2020 | 12/12/2020 | BISHAL ENTERPRISE | 14.6 | 26.56 | 181.91 | 0
85 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal order for the work of Laying of additional 90 mm dia HDPE pipe line with necessary allied works at Ayma Biswanathpur Mouza (JL-82) Balighat towards Ketan of Ayama Biswanthpur under Kanksa (Zone-I) W/s Scheme Block-Kanksa under DWSD,PHE Dte.(SL-26) |  |  | ORD/000162/2021-2022 | 1331/DWSD | 14/09/2021 | 04/10/2021 | MAK CONSTRUCTION CO. | 4.85 | 9.65 | 199.1 | 0
86 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal order for the work of Emergency repairing and restoration of distribution system of Protapur ,Kalikapur and Jamgora village under command area of Nachan OHR of Jamgora-Jagannathpur piped W/s Scheme under DWSD, PHE Dte (SL-02) |  |  | ORD/000132/2021-2022 | 1163/DWSD | 02/08/2021 | 22/08/2021 | RANJIB GHATAK | 4.85 | 0 | 0 | 100
87 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Laying of UPVC pipe line and other allied works at Kanksa under Pass to Molla para under Kanksa W/s Scheme under DWSD,PHE Dte.(SL-26) |  |  | ORD/000165/2020-2021 | 1044/DWSD | 09/10/2020 | 24/10/2020 | M/S KALYANI ENTERPRISE | 4.94 | 9.84 | 199.26 | 0
88 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | FORMAL WORK ORDER FOR the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Rajkusum mouza (JL-72) under command area of Rajkusum W/s Scheme Kanksa Block under Durgapur W/S Division, PHE Dte.(SL-01) |  |  | ORD/000081/2020-2021 | 875/DWSD | 15/09/2020 | 30/10/2020 | RANJIB GHATAK | 31.99 | 15.07 | 47.12 | 0
89 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal work-order for the work of replacement of AC pipe line with UPVC pipe line at Mollapara More to Kansa Gangulipara under Kanksa W/S Scheme under DWSD, PHE Dte (SL-07) |  |  | ORD/000093/2020-2021 | 918/DWSD | 22/09/2020 | 12/10/2020 | RANJIB GHATAK | 4.85 | 9.86 | 203.08 | 0
90 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Formal order for the work of --Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for RUPGANGANJ mouza (JL-54)under command area of Rupganj W/s Scheme Kanksa Block under Durgapur W/S Division, PHE Dte.(Sl-02) |  |  | ORD/000074/2020-2021 | 1355/DWSD | 09/12/2020 | 23/01/2021 | M/S KALYANI ENTERPRISE | 13.97 | 28.47 | 203.84 | 0
91 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Formal work-order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Srikrishnapur mouza (JL No-09) under command area of Gourbazar-Ichhapur W/s Scheme Durgapur-Faridpur Block, Paschim Bardhaman under Durgapur W/S Division, PHE Dte. |  |  | ORD/000080/2020-2021 | 897/DWSD | 22/09/2020 | 06/11/2020 | JOY GURU ENTERPRISE | 19.09 | 37.94 | 198.72 | 0
92 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Formal work-order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Kajladihi mouza (JL-26) under command area of Krishnapur W/s Scheme Kanksa Block under Durgapur W/S Division, PHE Dte.(SL-01) |  |  | ORD/000073/2020-2021 | 902/DWSD | 22/09/2020 | 06/11/2020 | THE STAR & CO | 16.5 | 32.83 | 199 | 0
93 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Formal order for the work of --Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Shilampur mouza (JL-90)under command area of Kanksa Zone-I W/s Scheme Kanksa Block under Durgapur W/S Division, PHE Dte.(SL-06) |  |  | ORD/000076/2020-2021 | 932/DWSD | 25/09/2020 | 09/11/2020 | MD AAMIR KHAN | 43.86 | 90.26 | 205.77 | 0
94 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Bansol mouza (JL-49) under command area of Gourbazar-Ichhapru piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte.(SL-28) |  |  | ORD/000273/2020-2021 | 1329/DWSD | 09/12/2020 | 23/01/2021 | JOY GURU ENTERPRISE | 29.98 | 59.92 | 199.85 | 0
95 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal work order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Shyamsundarpur mouza (JL-07) (Pt-A) under command area of Gourbazar-Ichhapur W/s Scheme of Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte (SL-30) |  |  | ORD/000275/2020-2021 | 1331/DWSD | 09/12/2020 | 23/01/2021 | PRAVAT SARKAR | 33.89 | 67.46 | 199.06 | 0
96 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Arati mouza (JL-54) under command area of Gourbazar-Ichhapur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte.(SL-09) |  |  | ORD/000253/2020-2021 | 1310/DWSD | 09/12/2020 | 23/01/2021 | BISHAL ENTERPRISE | 26.15 | 52.59 | 201.14 | 0
97 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Pratappur mouza (JL-40) under command area of Jamgora-Jagannathpur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte.(SL-25) |  |  | ORD/000270/2020-2021 | 1325/DWSD | 09/12/2020 | 23/01/2021 | JAYANTA DATTA | 18.89 | 37.73 | 199.8 | 0
98 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Kendua mouza (JL-36) & Chapabandhi (JL-37) under command area of Gourbazar-Ichhapru piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte (SL-27) |  |  | ORD/000272/2020-2021 | 1328/DWSD | 09/12/2020 | 23/01/2021 | CHANDAN HAZRA | 11.53 | 19.43 | 168.45 | 0
99 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal work order for the work of cutting of concrete road with supplying ,laying of 160 mm dia OD HDPE pipe from Pump house to pond providing water to Roopganj and Arrah mouza and others allied works for providing FHTC of roopganj W/s Scheme under DWSD ,PHE Dte (SL-18) |  |  | ORD/000285/2020-2021 | 1350/DWSD | 09/12/2020 | 24/12/2020 | M/S KALYANI ENTERPRISE | 3.09 | 6.16 | 199.48 | 0
100 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal work-order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Jamgora mouza (JL-23) under command area of Jamgora-Jagannathpur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte.(SL-01) |  |  | ORD/000246/2020-2021 | 1332/DWSD | 09/12/2020 | 23/01/2021 | RANJIB GHATAK | 24.63 | 49.21 | 199.82 | 0
101 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal work order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Radhamohanpur mouza (JL-36) under command area of Basudha W/S Scheme at Kanksa Block under Durgapur W/S Division, PHE Dte |  |  | ORD/000316/2020-2021 | 1441/DWSD | 28/12/2020 | 22/01/2021 | MD AAMIR KHAN | 13.53 | 27.39 | 202.42 | 0
102 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Arrah mouza (JL-91) (Pt-C) under command area of Roopganj W/S Scheme at Kanksa Block under Durgapur W/S Division, PHE Dte |  |  | ORD/000374/2020-2021 | 146/DWSD | 28/01/2021 | 14/03/2021 | DARPAN DAS & CO. | 24.19 | 48.27 | 199.52 | 0
103 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Domra mouza (JL-68) under command area of Trilakchandrapur piped W/S Scheme at Kanksa Block under Durgapur W/S Division, PHE Dte (SL-06) |  |  | ORD/000375/2020-2021 | 155/DWSD | 28/01/2021 | 14/03/2021 | AMARANJALI CONSTRUCTION | 21.66 | 43.26 | 199.75 | 0
104 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Patsaora mouza (JL-53) under command area of Gourbazar-Ichhapur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte.(SL-13) |  |  | ORD/000257/2020-2021 | 1316/DWSD | 09/12/2020 | 23/01/2021 | SHWET BARANI | 19.08 | 30.69 | 160.88 | 50
105 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal work order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Ijjatganj mouza (JL-71) (Pt-B) under command area of Kanksa Zone-II (Ph-I) W/S Scheme at Kanksa Block under Durgapur W/S Division, PHE Dte (SL-06) |  |  | ORD/000310/2020-2021 | 1436/DWSD | 28/12/2020 | 22/01/2021 | QUICK PAL SUPPLIERS | 5.93 | 11.78 | 198.75 | 0
106 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JJM) at Panagarh mouza (JL-85) under command area of Kanksa Zone-II(Ph-II) piped W/s Scheme of of Kanksa Block under Durgapur W/S Division, PHE Dte.(SL-20) |  |  | ORD/000266/2020-2021 | 1314/DWSD | 09/12/2020 | 23/01/2021 | UMWELT ENGINEER PVT LTD | 43.6 | 89.47 | 205.2 | 0
107 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal order for the work of Additional pipe line work with concrete cutting at Shilampur mouza for providing FHTC in connection with Jal Jeevan mission for Shilampur Mouza(JL-90) under command area of Kanksa (Zone-I) W/s Scheme at Kanksa block under DWSD, PHE Dte (SL-18) |  |  | ORD/000354/2020-2021 | 72/DWSD | 13/01/2021 | 07/02/2021 | MAK CONSTRUCTION CO. | 4.98 | 10.04 | 201.53 | 0
108 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal work order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Sibpur mouza (JL-20) under command area of within Bidbhar GP, Kanksa Block of Krishnapur piped W/s Scheme under Durgapur W/S Division, PHE Dte.(SL-10) |  |  | ORD/000254/2020-2021 | 1311/DWSD | 09/12/2020 | 23/01/2021 | RANJIB GHATAK | 21.43 | 41.64 | 194.34 | 0
109 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal work-order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Jotbalaram & Amdohi mouza (JL-08 & 25) under command area of Gourbazar-Ichhapur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte.(SL-14) |  |  | ORD/000258/2020-2021 | 1317/DWSD | 09/12/2020 | 23/01/2021 | JOY GURU ENTERPRISE | 25.99 | 44.23 | 170.23 | 0
110 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Bhadrapur(JL-34) & Banshgara mouza (JL-38) under command area of Gourbazar-Ichhapur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte.(SL-26) |  |  | ORD/000271/2020-2021 | 1326/DWSD | 09/12/2020 | 23/01/2021 | GHOSH ENTERPRISE | 12.83 | 25.55 | 199.08 | 0
111 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Sarpi mouza (JL-35) (Pt-A) under command area of Gourbazar-Ichhapru piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte. (SL-29) |  |  | ORD/000274/2020-2021 | 1330/DWSD | 09/12/2020 | 23/01/2021 | KIRON ENTERPRISE | 29.51 | 58.92 | 199.62 | 0
112 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal work-order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Hetedoba mouza (JL-48) under command area of Gourbazar-Ichhapur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte.(SL-06) |  |  | ORD/000251/2020-2021 | 1308/DWSD | 09/12/2020 | 23/01/2021 | AMARANJALI CONSTRUCTION | 12.32 | 24.45 | 198.48 | 0
113 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Jabuna mouza (JL-55) under command area of Gourbazar-Ichhapur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte.(SL-11) |  |  | ORD/000255/2020-2021 | 1312/DWSD | 09/12/2020 | 23/01/2021 | D. S. ENTERPRISE | 11.37 | 22.72 | 199.83 | 0
114 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JJM) at Sundiara mouza (JL-67) under command area of Trilockchandrapur piped W/s Scheme of of Kanksa Block under Durgapur W/S Division, PHE Dte. under Durgapur W/S Division, PHE Dte.(SL-15) |  |  | ORD/000261/2020-2021 | 1319/DWSD | 09/12/2020 | 23/01/2021 | S K ALIM | 14.52 | 28.98 | 199.62 | 0
115 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Ichhapur mouza (JL-50) under command area of Gourbazar-Ichhapur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte.(SL-12) |  |  | ORD/000256/2020-2021 | 1315/DWSD | 09/12/2020 | 23/01/2021 | SHWET BARANI | 25.79 | 45.26 | 175.51 | 0
116 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JJM) at Ijjatganj mouza (JL-71) under command area of Kanksa Zone-II(Ph-I) piped W/s Scheme of of Kanksa Block under Durgapur W/S Division, PHE Dte. (SL-17) |  |  | ORD/000262/2020-2021 | 1320/DWSD | 09/12/2020 | 23/01/2021 | RANJIB GHATAK | 42.68 | 85.03 | 199.21 | 0
117 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal work-order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Banshia mouza (JL-31) under command area of Jamgora-Jagannathpur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte.(SL-03) |  |  | ORD/000248/2020-2021 | 1305/DWSD | 09/12/2020 | 23/01/2021 | BABA LOKNATH ENTERPRISE | 17.74 | 36.51 | 205.78 | 0
118 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Gopendanga mouza (JL-94) under command area of Jamgora-Jagannathpur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte.(SL-06) |  |  | ORD/000250/2020-2021 | 1307/DWSD | 09/12/2020 | 23/01/2021 | M/S BADAL GHOSH | 6.63 | 11.82 | 178.36 | 0
119 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum Formal work-Order for the work of ---Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Krishnapur mouza (JL-23) within Bidbahar GP under command area of Krishnapur W/S Scheme at Kanksa Block under Durgapur W/S Division, PHE Dte |  |  | ORD/000320/2020-2021 | 1447/DWSD | 28/12/2020 | 17/01/2021 | THE STAR & CO | 5.63 | 11.17 | 198.56 | 0
120 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum Formal work-Order for the work of ---Balance work for Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Jagannathpur mouza (JL-26) under command area of Jamgora-Jagannathpur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte. |  |  | ORD/000322/2020-2021 | 1449/DWSD | 28/12/2020 | 22/01/2021 | M/S BADAL GHOSH | 14.76 | 26.44 | 179.09 | 0
121 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Nabagram mouza (JL-22) having habitations Nabagram and Jambon within Bidbahar GP under command area of Krishnapur W/S Scheme at Kanksa Block under Durgapur W/S Division, PHE Dte |  |  | ORD/000371/2020-2021 | 143/DWSD | 28/01/2021 | 27/02/2021 | RANJIB GHATAK | 13.2 | 12.03 | 91.17 | 0
122 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Jagannathpur mouza (JL-26) under command area of Jamgora-Jagannathpur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte.(SL-14) |  |  | ORD/000219/2020-2021 | 1156/DWSD | 28/10/2020 | 12/12/2020 | M/S BADAL GHOSH | 10.15 | 18.01 | 177.51 | 0
123 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Tilakchandrapur mouza (JL-63)under command area of Tilakchandrapur W/s Scheme Kanksa Block under Durgapur W/S Division, PHE Dte.(SL-15) |  |  | ORD/000220/2020-2021 | 1157/DWSD | 28/10/2020 | 12/12/2020 | S K ALIM | 22.47 | 44.88 | 199.77 | 0
124 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Rautdihi mouza (JL-25) under command area of Bidbahar GP Krishnapur piped W/s Scheme Kanksa Block under Durgapur W/S Division, PHE Dte.(sl-17) |  |  | ORD/000221/2020-2021 | 1158/DWSD | 28/10/2020 | 12/12/2020 | THE STAR & CO | 5.59 | 11.08 | 198.2 | 0
125 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Sarpi mouza (JL-35) (Pt-B) under command area of Gourbazar-Ichhapur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte.(SL-01) |  |  | ORD/000378/2020-2021 | 170/DWSD | 03/02/2021 | 20/03/2021 | RANJIB GHATAK | 26.91 | 48.03 | 178.52 | 0
126 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal order for the work of Extension of pipe line from existing pipe line of Kanksa zone -II Ph-II W/s Scheme to combat draught like situation in Kaksa Block to providing FHTC at Debipur Mouza (JL-87)(Part-D) under DWSD,PHE Dte (SL-56) |  |  | ORD/000447/2020-2021 | 301/DWSD | 26/02/2021 | 28/03/2021 | MANAS KUMAR SAHA | 4.31 | 8.62 | 200 | 0
127 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal order for the work Extension of pipe line from existing pipe line of Kanksa zone -II Ph-II W/s Scheme to combat draught like situation in Kaksa Block to providing FHTC at Debipur Mouza (JL-87)(Part-E) under DWSD,PHE Dte(SL-57) |  |  | ORD/000448/2020-2021 | 302/DWSD | 26/02/2021 | 28/03/2021 | MANAS KUMAR SAHA | 4.98 | 9.96 | 200 | 0
128 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal order for the work of Supplying of extra UPVC pipe line at different places of Kendua Hazra para ,Bouri para and Chapabandhi in connection of FHTC under Gourbazar-Ichhapur piped W/s Scheme of DWSD,PHE Dte.(SL-06) |  |  | ORD/000419/2020-2021 | 275/DWSD | 26/02/2021 | 18/03/2021 | CHANDAN HAZRA | 2.89 | 5.08 | 175.82 | 0
129 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal order for the work of Extension of pipe line from existing pipe line for providing FHTC in connection with JJM for Basudha mouza(JL-35(Part-B) under command area of Basudha W/s Scheme at Kanksa Block under DWSD, PHE Dte (SL-06) |  |  | ORD/000001/2021-2022 | 715/DWSD | 29/04/2021 | 19/05/2021 | S.S.CONSTRUCTION | 4.98 | 9.97 | 200.13 | 0
130 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal order for the work of Extension of pipe line from existing pipe line of Roopganj W/S Scheme to combat draught like situation in Kanksa block to providing FHTC at Roopganj mouza (JL-54) under DWSD, PHE Dte (SL-07) |  |  | ORD/000002/2021-2022 | 716/DWSD | 29/04/2021 | 24/05/2021 | M/S KALYANI ENTERPRISE | 4.96 | 9.91 | 199.99 | 0
131 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal order for the work of Extension of pipe line from existing pipe line for providing FHTC in connection with JJM for Basudha mouza(JL-35(Part-A) under command area of Basudha W/s Scheme at Kanksa Block under DWSD, PHE Dte(Sl-05) |  |  | ORD/000005/2021-2022 | 718/DWSD | 29/04/2021 | 24/05/2021 | M/S S. CHOUDHURY | 4.85 | 9.72 | 200.21 | 0
132 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal order for the work of laying of PVC pipe line at Kailashpur village within Jagannathpur Mouza in connection with FHTC under Jamgora-Jagannathpur W/s Scheme under DWSD, PHE Dte(SL-07) |  |  | ORD/000420/2020-2021 | 276/DWSD | 26/02/2021 | 08/03/2021 | M/S BADAL GHOSH | 2.07 | 4.13 | 199.94 | 0
133 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal order for the work of Laying of PVC pipe line at Shibpur Mouza (JL-20) and Nabagram Mouza (JL 22) in connection with FHTC under Krishnapur W/s Scheme under DWSD, PHE Dte.(SL-02) |  |  | ORD/000415/2020-2021 | 271/DWSD | 26/02/2021 | 08/03/2021 | RANJIB GHATAK | 2.23 | 4.47 | 199.99 | 0
134 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Formal order for the work of Balance work for providing FHTC in connection with JJM for Bansia mouza(JL-31) under command area of Jamgora-Jagannathpur W/s Scheme at Durgapur Faridpur Block under DWSD, PHE Dte (SL-05) |  |  | ORD/000023/2021-2022 | 796/DWSD | 12/05/2021 | 27/05/2021 | BABA LOKENATH ENTERPRISE | 12.9 | 25.24 | 195.64 | 0
135 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Formal order for the work of Additional work for providing functional house hold Tap connection (FHTC) in connection with JJM for Kalikapur mouza(JL-30) under command area of Jamgora-Jagannathpur W/S Scheme under DWSD, PHE Dte (SL-06) |  |  | ORD/000024/2021-2022 | 794/DWSD | 12/05/2021 | 27/05/2021 | M/S MONDAL ENTERPRISE | 11.05 | 22.53 | 203.92 | 0
136 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal order for the work of additional pipe line work with concrete cutting at Bansia mouza for providing functional house hold tap connection (FHTC) in connection with JJM for Bansia mouza (JL-31) under command area of Jamgora-Jaggannathpur W/s Scheme at Durgapur-Faridpur block under DWSD, PHE Dte. (SL-04) |  |  | ORD/000006/2021-2022 | 719/DWSD | 29/04/2021 | 24/05/2021 | BABA LOKENATH ENTERPRISE | 4.99 | 9.94 | 199.06 | 0
137 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Formal order for the work of Laying of additional distribution pipe line with necessary allied works at Sarpi Adibasipara,Dhibarpara ,Bouripara,Ruidaspara, Mondalpara,Karmakarpara under Gourbazar-Ichhapur piped W/S Scheme under DWSD,PHE Dte (SL-01) |  |  | ORD/000059/2021-2022 | 1055/DWSD | 22/07/2021 | 06/08/2021 | RANJIB GHATAK | 8.27 | 16.49 | 199.35 | 0
138 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal order for the work of Additional work for providing FHTC in connection with JJM at Jabuna (JL-55) Block-Durgapur-Faridpur ,Dist-Paschim Bardhaman under Gourbazar-Ichhapur piped W/s Scheme of DWSD,PHE Dte (SL-06) |  |  | ORD/000086/2021-2022 | 1098/DWSD | 30/07/2021 | 09/08/2021 | D. S. ENTERPRISE | 0.63 | 1.26 | 198.9 | 0
139 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal order for the work of Extension of pipe line from existing pipe line Kanksa zone -II (Ph-II) W/s Scheme with concrete cutting and re-concreting to combat draught like situation in Kaksa block to providing FHTC at Debipur mouza(JL-87)(Part-D) under DWSD,PHE Dte(SL-10) |  |  | ORD/000090/2021-2022 | 1102/DWSD | 30/07/2021 | 14/08/2021 | MANAS KUMAR SAHA | 3.97 | 7.83 | 197.21 | 0
140 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance order for the work of Additional work for providing functional household tap connection (FHTC) in connection with JJM at Ichhapur Mouza ,Block-Durgapur-Faridpur ,Dist-Paschim Bardhaman under Gourbazar-Ichhapur W/s Scheme of Durgapur W/s Division, PHE Dte.(SL-08) |  |  | ORD/000106/2021-2022 | 1195/DWSD | 11/08/2021 | 10/10/2021 | SHWET BARANI | 22.71 | 22.74 | 100.1 | 0
141 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal order for the work of Extension of pipe line from existing pipe line Kanksa zone -II (Ph-II) W/s Scheme to combat draught like situation in Kaksa block to providing FHTC at Debipur mouza(JL-87)(Part-F) under DWSD,PHE Dte (SL-11). |  |  | ORD/000091/2021-2022 | 1103/DWSD | 30/07/2021 | 14/08/2021 | MANAS KUMAR SAHA | 4.85 | 9.7 | 200 | 0
142 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal work order for the work of Additional work for providing FHTC in connection with JJM at Pratappur(JL-40) Block-Durgapur-Faridpur ,Dist-Paschim Bardhaman under Gourbazar-Ichhapur piped W/s Scheme under DWSD,PHE Dte (SL-03) |  |  | ORD/000083/2021-2022 | 1095/DWSD | 30/07/2021 | 14/08/2021 | JAYANTA DATTA | 4.2 | 8.07 | 191.9 | 0
143 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Formal order for the work of Repairing ,extension as well as replace of damaged pipe line and allied works at Sarpi mouza (JL-35) under command area of Gourbazar-Ichhapur W/s Scheme under DWSD ,PHE Dte (SL-09) |  |  | ORD/000113/2021-2022 | 1300/DWSD | 09/09/2021 | 29/09/2021 | KIRON ENTERPRISE | 6.59 | 13.15 | 199.54 | 0
144 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal order for the work of Extension of pipe line from exisitn pipe line Kanksa (Zone-II (Ph-II) W/s Scheme to combat draught like situation in Kanksa block to providing FHTC at Kanksa mouza (JL_89) under DWSD ,PHE Dte at Poral para,Khadra para under DWSD,PHE Dte (SL-19) |  |  | ORD/000099/2021-2022 | 1111/DWSD | 30/07/2021 | 14/08/2021 | SWATI CORPARATION | 4.95 | 10.06 | 203.1 | 0
145 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal order for the work of Additional pipe line work with concrete cutting at Nachan mouza for provding FHTC in connection with JJM for Nachan mouza(JL-39) (Part-A) under command are aof Jamgora-Jagannathpur W/s Scheme at Durgapur-Faridpur block under DWSD,PHE Dte (SL-24) |  |  | ORD/000111/2021-2022 | 1116/DWSD | 30/07/2021 | 14/08/2021 | BABA LOKENATH ENTERPRISE | 4.59 | 9.39 | 204.72 | 0
146 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal work-order for the work providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) at Kalikapur mouza (JL-30) under command area of Jamgora-Jagannathpur piped W/s Scheme Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte (SL-02) |  |  | ORD/000247/2020-2021 | 1304/DWSD | 09/12/2020 | 23/01/2021 | M/S MONDAL ENTERPRISE | 11.59 | 23.85 | 205.72 | 0
147 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Formal work-order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Piariganj mouza (JL-93) under command area of Tilakchandrapur piped W/s Scheme Kanksa Block under Durgapur W/S Division, PHE Dte. (SL-11) |  |  | ORD/000077/2020-2021 | 1356/DWSD | 09/12/2020 | 23/01/2021 | AMARANJALI CONSTRUCTION | 13.52 | 26.96 | 199.36 | 0
148 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Formal order for the work of Replace of damaged AC pipe line with HDPE pipe from Kanksa under pass towards Kanksa PS of Kanksa (Zone-II & Ph-II) W/S Scheme under DWSD,PHE Dte (SL-06) |  |  | ORD/000104/2021-2022 | 1374/DWSD | 17/09/2021 | 07/10/2021 | SWATI CORPARATION | 9.71 | 19.78 | 203.75 | 0
149 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal work order for the work of providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JJM) at Kalinagar mouza (JL-27) under command area Durgapur-Faridpur Block of Jamgora-Jagnnathpur piped W/s Scheme of under Durgapur W/S Division, PHE Dte (SL-23) |  |  | ORD/000268/2020-2021 | 1323/DWSD | 09/12/2020 | 23/01/2021 | M/S BADAL GHOSH | 5.52 | 10.49 | 190.04 | 0
150 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of 10 Nos. PWSS for providing FHTC under Durgapur W/S Division. | SM/07391 | Retrofitting | Acceptance cum formal work order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Radhanagar mouza (JL-24) within Bidbahar GP under command area of Krishnapur W/S Scheme at Kanksa Block under Durgapur W/S Division, PHE Dte (SL-09) |  |  | ORD/000312/2020-2021 | 1338/DWSD | 28/12/2020 | 17/01/2021 | THE STAR & CO | 5.48 | 10.92 | 199.19 | 0
Total | [13 empty] | 1988.62 | 3012.86 | 151.51