## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of ARRAH Mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07518 | Retrofitting | Formal order for the work of Supplying laying of 90 mm dia UPVC pipe bypass connection for Amlouka gram from Banguri more of Improvement of Jamgora-Jagannathpur W/s Scheme under DWSD ,PHE Dte (SL-02) |  |  | ORD/000346/2021-2022 | 135/DWSD | 02/02/2022 | 17/02/2022 | MD JAWED KHAN | 6.6 | 0 | 0 | 50
2 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of ARRAH Mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07518 | Retrofitting | Continuation order for the work of Providing functional house hold tap connection in connection with JJM at Shyamsundarpur Mouza(JL-07) ,block-Durgapur-Faridpur ,Dist-Paschim Bardhaman under Gourbazar-Ichhapur piped W/s Scheme under DWSD,PHE Dte. |  |  | ORD/000424/2021-2022 | 245/DWSD | 28/02/2022 | 15/03/2022 | PRAVAT SARKAR | 4.97 | 0 | 0 | 50
3 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of ARRAH Mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07518 | Retrofitting | Acceptance cum formal order for the work of Water supply arrangement at Hazra para ICDS Centre of Akandara for having no Electricity power supply to provide solar power connection (For 350 Nos Students), Kanksa Block under Retrofitting of Arraha piped W/s Scheme under DWSD ,PHE Dte |  |  | ORD/000460/2022-2023 | 312/DWSD | 20/02/2023 | 07/03/2023 | GHOSH ENTERPRISE | 6.92 | 6.92 | 100 | 0
4 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of ARRAH Mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07518 | Retrofitting | Acceptance cum formal order for the work of water supply arrangement at Muslim Para ICDS Centre of Akandara for having no Electricity power supply to provide solar power connection (For 350 Nos Students),Kanksa Block under Retrofitting of Arraha piped W/s Scheme under DWSD ,PHE Dte |  |  | ORD/000461/2022-2023 | 313/DWSD | 20/02/2023 | 07/03/2023 | RUBY CONSTRUCTION | 6.96 | 6.96 | 100 | 0
5 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of ARRAH Mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07518 | Retrofitting | Acceptance cum formal order for the work of Water supply arrangement at Akandara Adibasipara ICDS Centre of Akandara for having no Electricity power supply to provide solar power connection (For 350 Nos Students), Kanksa Block under Retrofitting of Arraha piped W/s Scheme under DWSD ,PHE Dte |  |  | ORD/000462/2022-2023 | 314/DWSD | 20/02/2023 | 07/03/2023 | JUBILEE CONSTRUCTION | 6.95 | 6.95 | 100 | 0
6 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of ARRAH Mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07518 | Retrofitting | Acceptance cum formal order for the work of Water supply arrangement 1(One) No ICDS Centre at Shyambazar for having no Electricity power supply to provide solar power connection (For 350 Nos Students), Kanksa Block under Retrofitting of Arraha piped W/s Scheme under DWSD ,PHE Dte |  |  | ORD/000463/2022-2023 | 315/DWSD | 20/02/2023 | 07/03/2023 | KIRON ENTERPRISE | 12.15 | 11.92 | 98.13 | 0
7 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of ARRAH Mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07518 | Retrofitting | Acceptance cum formal order for the work of water supply arrangement at Jatgoria Junior High School ICDS Centre having no Electricity power supply to provide solar power connection (For 350 Nos Students),Kanksa Block under Retrofitting of Arraha piped W/s Scheme under DWSD ,PHE Dte |  |  | ORD/000464/2022-2023 | 316/DWSD | 20/02/2023 | 07/03/2023 | BASANTI TRADERS | 6.95 | 6.95 | 100 | 0
8 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of ARRAH Mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07518 | Retrofitting | Formal order for the work of Laying of branch pipe line at Basudevpur ,Binodpur and Sashipur mouza with its adjoining area UPVC pipe of Kanchanpur W/s Scheme under DWSD, PHE Dte (SL-08) |  |  | ORD/000027/2021-2022 | 834/DWSD | 24/05/2021 | 08/06/2021 | T.M.CONCRETE CREATION PVT LTD | 10.76 | 0 | 0 | 0
9 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of ARRAH Mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07518 | Retrofitting | Acceptance cum formal order for the work of Dismantling and reconcreting of PCC road at Madhammath Subashpally sher para of Kanksa mouza Zone-II Ph-II W/s Scheme under DWSD ,PHE Dte (SL-05) |  |  | ORD/000186/2021-2022 | 1407/DWSD | 29/09/2021 | 14/10/2021 | SWATI CORPORATION | 4.56 | 0 | 0 | 0
10 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of ARRAH Mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07518 | Retrofitting | Acceptance cum formal order for the work of Connection provide to different Govt offices ,Schools,(Kanksa Thana,Kanksa Girls high Schools,Kanksa GP,TC Pur GP & 6 Nos ICDS at Kanksa mouza under DWSD,PHE Dte (SL-01) |  |  | ORD/000182/2021-2022 | 1403/DWSD | 23/09/2021 | 08/10/2021 | SWATI CORPORATION | 3.03 | 0 | 0 | 0
11 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of ARRAH Mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07518 | Retrofitting | Acceptance cum formal order for the work of Dismantling of concre road and reconcreting the same at poral para,Khadrapara ,near Kanksa Police Station under pass to towards kanksa PS and Sher para under command areaof Kanksa zone-II W/s Scheme for providing of FHTC under DWSD,PHE Dte (SL-04) |  |  | ORD/000185/2021-2022 | 1406/DWSD | 23/09/2021 | 08/10/2021 | SWATI CORPORATION | 4.56 | 0 | 0 | 0
12 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of ARRAH Mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07518 | Retrofitting | Acceptance cum formal order for the work of Water supply arrangement at Ruidas para ICDS Centre of Akandara for having no Electricity power supply to provide solar power connection (For 350 Nos Students), Kanksa Block under Retrofitting of Arraha piped W/s Scheme under DWSD ,PHE Dte |  |  | ORD/000457/2022-2023 | 310/DWSD | 20/02/2023 | 07/03/2023 | QUICK PAL SUPPLIERS | 6.96 | 6.96 | 100 | 100
13 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of ARRAH Mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07518 | Retrofitting | Acceptance cum formal order for the work of Water supply arrangement at Akandara Bouri para ICDS Centre of Akandara for having no Electricity power supply to provide solar power connection (For 350 Nos Students), Kanksa Block under Retrofitting of Arraha piped W/s Scheme under DWSD ,PHE Dte |  |  | ORD/000458/2022-2023 | 311/DWSD | 20/02/2023 | 07/03/2023 | M/S MONDAL ENTERPRISE | 6.94 | 6.87 | 98.94 | 0
14 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of ARRAH Mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07518 | Retrofitting | Acceptance cum formal order for the work of Water supply arrangement at Borobigha Adibasi para ICDS Centre of Domra Bagdipara ICDS, Domra Bagdipara,Satkahania billpara for having no Electricity power supply to provide solar power connection (For 350 Nos Students), Kanksa Block under Retrofitting of Arraha piped W/s Scheme under DWSD ,PHE Dte |  |  | ORD/000467/2022-2023 | 263/DWSD | 15/02/2023 | 12/03/2023 | BISHAL ENTERPRISE | 21.24 | 21.24 | 100 | 0
15 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of ARRAH Mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07518 | Retrofitting | Additional concreting of exiting dismantled road after extension of pipe line and retrofitting of existing pipe distribution system of kanksa block at Basudevpur village, Kanchanpur (N),Talbahari under Augmentation of Kanchanpur piped W/s Scheme (Part- A) |  |  | ORD/000165/2023-2024 | 1296/DWSD | 07/08/2023 | 22/08/2023 | M/S MANDAL ENTERPRISE | 5.87 | 5.87 | 99.99 | 100
16 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of ARRAH Mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07518 | Retrofitting | Additional concreting of exiting dismantled road after extension of pipe line and retrofitting of existing pipe distribution system of kanksa block at Kanchanpur under Augmentation of Kanchanpur piped W/s Scheme (Part- B) |  |  | ORD/000166/2023-2024 | 1298/DWSD | 07/08/2023 | 22/08/2023 | M/S BANERJEE CONSTRUCTION | 7.05 | 7.05 | 99.95 | 100
17 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of ARRAH Mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07518 | Retrofitting | Continuation order for Additional concreting of exiting dismantled road after extension of pipe line and retrofitting of existing pipe distribution system of kanksa block at Basudevpur village, Kanchanpur (N),Talbahari under Retrofitting of ARRAH piped W/s Scheme (Part- A) |  |  | ORD/000173/2023-2024 | 1376/DWSD | 14/08/2023 | 21/08/2023 | M/S MANDAL ENTERPRISE | 1.72 | 1.72 | 100 | 100
18 | PASCHIM BARDHAMAN |  | RCFA Division -I | Retrofitting of ARRAH Mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07518 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000012/2025-2026 | 2540/RCD-I | 01/09/2025 | 01/09/2025 | Resource Division | 6.92 | 0 | 0 | 0
Total | [13 empty] | 131.1 | 89.4 | 68.19