## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of Jamgara,Jagannathpur,Kalinagar,Kendula,Kalikapur & Banshia mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07524 | Retrofitting | Formal order for the work of Balance work for providing FHTC in connection with JJM for Bansia mouza(JL-31) under command area of Jamgora-Jagannathpur W/s Scheme at Durgapur Faridpur Block under DWSD, PHE Dte (SL-05) |  |  | ORD/000023/2021-2022 | 796/DWSD | 12/05/2021 | 27/05/2021 | BABA LOKENATH ENTERPRISE | 12.9 | 0 | 0 | 0
2 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of Jamgara,Jagannathpur,Kalinagar,Kendula,Kalikapur & Banshia mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07524 | Retrofitting | Formal order for the work of Repairing ,extension as well as replace of damage AC pipe line and allied works at Colony Bouri para ,Upper Bagdi para ,Adibasi para under Jamgora(Mouza-23) under command area of Jamgora-Jagannathpur W/s Scheme for combat upcoming drought like situation under DWSD, PHE Dte (SL-07) |  |  | ORD/000025/2021-2022 | 829/DWSD | 24/05/2021 | 03/06/2021 | RANJIB GHATAK | 7.26 | 0 | 0 | 0
3 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of Jamgara,Jagannathpur,Kalinagar,Kendula,Kalikapur & Banshia mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07524 | Retrofitting | Acceptance cum formal order for the work of additional pipe line work with concrete cutting at Bansia mouza for providing functional house hold tap connection (FHTC) in connection with JJM for Bansia mouza (JL-31) under command area of Jamgora-Jaggannathpur W/s Scheme at Durgapur-Faridpur block under DWSD, PHE Dte. (SL-04) |  |  | ORD/000006/2021-2022 | 719/DWSD | 29/04/2021 | 24/05/2021 | BABA LOKENATH ENTERPRISE | 4.99 | 0 | 0 | 0
4 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of Jamgara,Jagannathpur,Kalinagar,Kendula,Kalikapur & Banshia mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07524 | Retrofitting | Acceptance cum formal order for the work of Extension of pipe line of different dia UPVC pipe at Kalikapur mouza to combat draught like situation in Durgapur-Faridpur block to providing FHTC at Kalikapur mouza(JL-30) under Jamgora-Jagannathpur W/s Scheme under DWSD, PHE Dte (SL-08) |  |  | ORD/000009/2021-2022 | 722/DWSD | 29/04/2021 | 29/05/2021 | M/S MONDAL ENTERPRISE | 4.99 | 0 | 0 | 0
5 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of Jamgara,Jagannathpur,Kalinagar,Kendula,Kalikapur & Banshia mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07524 | Retrofitting | Acceptance cum formal order for the work of Emergency repairing and restoration of distributing system from Nachan OHR to Jamgora ,Nachan more to jamgora samshan distribution main road crossing at Nachan with Hume pipe ,Bansia pratabpur and extension of pipe at different places of Pratabpur gram of Jamgora-Jagannathpur piped W/s Scheme under DWSD ,PHE Dte |  |  | ORD/000120/2022-2023 | 781/DWSD | 18/05/2022 | 02/06/2022 | M/S MONDAL ENTERPRISE | 4.56 | 0 | 0 | 0
6 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of Jamgara,Jagannathpur,Kalinagar,Kendula,Kalikapur & Banshia mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07524 | Retrofitting | Acceptance cum formal order for the work of Emergency repairing restoration and chokage cleaning of distribution system of Hetedoba OHR from Hetedoba OHR to Sarpi more of Gourbazar-Ichhapur piped W.S Scheme under DWSD,PHE Dte |  |  | ORD/000374/2021-2022 | 112/DWSD | 01/02/2022 | 21/02/2022 | PAYAL CONSTRUCTION | 3.24 | 0 | 0 | 0
7 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of Jamgara,Jagannathpur,Kalinagar,Kendula,Kalikapur & Banshia mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07524 | Retrofitting | Continuation order for the work of Providing functional house hold tap connection in connection with JJM at Shyamsundarpur Mouza(JL-07) ,block-Durgapur-Faridpur ,Dist-Paschim Bardhaman under Gourbazar-Ichhapur piped W/s Scheme under DWSD,PHE Dte. |  |  | ORD/000425/2021-2022 | 239/DWSD | 25/02/2022 | 12/03/2022 | PRAVAT SARKAR | 4.92 | 0 | 0 | 0
8 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of Jamgara,Jagannathpur,Kalinagar,Kendula,Kalikapur & Banshia mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07524 | Retrofitting | Acceptance cum formal order for the work of Making interconnection of Over flow line and laying of additonal distribution pipe line with necessary allied works for FHTC purpose at Jagnnathpur gram under Jamgora-Jagannathpur W/S Scheme under DWSD PHE Dte (SL-06) |  |  | ORD/000442/2021-2022 | 421/DWSD | 30/03/2022 | 09/04/2022 | M/S BADAL GHOSH | 3.69 | 0 | 0 | 0
9 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of Jamgara,Jagannathpur,Kalinagar,Kendula,Kalikapur & Banshia mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07524 | Retrofitting | Acceptance cum formal order for the work of Laying of distribution pipe line for (FHTC) in connection with JJM and additional work of Solar Tube well site and necessary allied work at Huchukdanga village ,Paschim Bardhaman under DWSD, PHE Dte (SL-10) |  |  | ORD/000446/2021-2022 | 425/DWSD | 30/03/2022 | 09/04/2022 | RANJIB GHATAK | 3.81 | 0 | 0 | 0
10 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of Jamgara,Jagannathpur,Kalinagar,Kendula,Kalikapur & Banshia mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07524 | Retrofitting | Formal order for the work of Emegency repairng and restoration of distribution system from command area of Gourbazar OHR {(Srikrishnapur, Kailashpur (Part)} under Gourbazar-Ichhapur piped W/s Scheme under DWSD, PHE Dte (SL-11) |  |  | ORD/000115/2021-2022 | 1780/DWSD | 20/12/2021 | 30/12/2021 | JOY GURU ENTERPRISE | 5.6 | 0 | 0 | 0
11 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of Jamgara,Jagannathpur,Kalinagar,Kendula,Kalikapur & Banshia mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07524 | Retrofitting | Acceptance cum formal order for the work of Laying of collecting main necessary repairing works in river Ajoy at Bhaburia H/w Site under Jamgora-Jagannathpur and Gourbazar-Ichhapur W/s Scheme for combat flood damaged under DWSD, PHE Dte |  |  | ORD/000366/2021-2022 | 97/DWSD | 28/01/2022 | 12/02/2022 | RANAJOY ENTERPRISE | 3.29 | 0 | 0 | 50
12 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of Jamgara,Jagannathpur,Kalinagar,Kendula,Kalikapur & Banshia mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07524 | Retrofitting | Acceptance cum formal order for the work of Surging of 5 Nos tube well including withdrawing pumping machinery setting the same correcting cable line and other allied works due to flood damaged at Bhaburia H/W site under Jamgora-Jagannathpur & Gourbazar-Ichhapur piped W/s Scheme.(Part-B) |  |  | ORD/000369/2021-2022 | 101/DWSD | 31/01/2022 | 20/02/2022 | RANAJOY ENTERPRISE | 1.8 | 0 | 0 | 50
13 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of Jamgara,Jagannathpur,Kalinagar,Kendula,Kalikapur & Banshia mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07524 | Retrofitting | Continuation order for the work of Providing functional house hold tap connection in connection with JJM at Shyamsundarpur Mouza(JL-07) ,block-Durgapur-Faridpur ,Dist-Paschim Bardhaman under Gourbazar-Ichhapur piped W/s Scheme under DWSD,PHE Dte. |  |  | ORD/000424/2021-2022 | 245/DWSD | 28/02/2022 | 15/03/2022 | PRAVAT SARKAR | 4.97 | 0 | 0 | 50
14 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of Jamgara,Jagannathpur,Kalinagar,Kendula,Kalikapur & Banshia mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07524 | Retrofitting | Formal order for the work of Supplying and laying of 110 mm and 90 mm dia UPVC pipe at Bansgora (Main road to Akhrapara) for providing FHTC of Bansgora Mouza JL-38 of Jamgora-Jagannathpur W/s Scheme under DWSD PHE Dte |  |  | ORD/000298/2021-2022 | 1775/DWSD | 20/12/2021 | 14/01/2022 | SILPO UDYOG ENGINEERING CONSTRUCTIONS | 7.57 | 0 | 0 | 0
15 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of Jamgara,Jagannathpur,Kalinagar,Kendula,Kalikapur & Banshia mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07524 | Retrofitting | Continuation order for the work of the work of Providing functional house hold tap connection (FHTC ) in connection with JJM for Huchuk Danga Jamgora-Jagannathpur piped W/S Scheme Mouza-Dannaya /Jamgora(JL-23) block-Durgapur-Faridpur ,Paschim Bardhaman under DWSD,PHE Dte |  |  | ORD/000337/2021-2022 | 25/DWSD | 06/01/2022 | 21/01/2022 | RANJIB GHATAK | 3.49 | 0 | 0 | 0
16 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of Jamgara,Jagannathpur,Kalinagar,Kendula,Kalikapur & Banshia mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07524 | Retrofitting | Formal order for the work of Extension of pipe line from the existing pipe line from command area of Gourbazar-Ichhapur piped W/s Scheme of Ichhapur area for providing of FHTC at Ichhapur mouza(JL-50) under DWSD,PHE Dte (SL-05) |  |  | ORD/000347/2021-2022 | 140/DWSD | 03/02/2022 | 10/02/2022 | SHWET BARANI | 13.62 | 0 | 0 | 0
17 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of Jamgara,Jagannathpur,Kalinagar,Kendula,Kalikapur & Banshia mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07524 | Retrofitting | Continuation order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Shyamsundarpur mouza (JL-07) under command area of Gourbazar-Ichhapur W/s Scheme of Durgapur-Faridpur Block under Durgapur W/S Division, PHE Dte (Part-C). |  |  | ORD/000305/2021-2022 | 1735/DWSD | 13/12/2021 | 23/12/2021 | PRAVAT SARKAR | 4.97 | 0 | 0 | 0
18 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of Jamgara,Jagannathpur,Kalinagar,Kendula,Kalikapur & Banshia mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07524 | Retrofitting | Acceptance cum formal order for the work of Laying of collection main necessary repairing works in river Ajoy at Bhaburia H/W site under Jamgora -Jagannathpur piped W/s Scheme and Gourbazar-Ichhapur piped W/s Scheme.(Part-A) |  |  | ORD/000360/2021-2022 | 79/DWSD | 24/01/2022 | 08/02/2022 | RANAJOY ENTERPRISE | 3.85 | 0 | 0 | 0
19 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of Jamgara,Jagannathpur,Kalinagar,Kendula,Kalikapur & Banshia mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07524 | Retrofitting | Acceptance cum formal order for the work of Laying of distribution pipe line with necessary allied works for FHTC purpose at Maheshpur village Muchipara,Chasa para Moheshpur Mouza(JL-12),Durgapur-Faridpur block under DWSD PHE Dte |  |  | ORD/000364/2021-2022 | 88/DWSD | 27/01/2022 | 11/02/2022 | M/S BADAL GHOSH | 4.87 | 0 | 0 | 0
20 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of Jamgara,Jagannathpur,Kalinagar,Kendula,Kalikapur & Banshia mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07524 | Retrofitting | Acceptance cum formal order for the work Providing FHTC in connection with JJM at Shayamsundarpur mouza(JL-07) ,Block-Durgapur-Fardipur Block ,Dist-Paschim Bardhman under Gourbazar-Ichhapur piped W/s Scheme PHE Dte (P-C) |  |  | ORD/000390/2021-2022 | 10/DWSD | 04/01/2022 | 19/01/2022 | PRAVAT SARKAR | 4.84 | 0 | 0 | 0
21 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of Jamgara,Jagannathpur,Kalinagar,Kendula,Kalikapur & Banshia mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07524 | Retrofitting | Acceptance cum formal order for the work of Surging of 12 Nos tube well including withdrawing pumping machinery setting the same correcting cable line and other allied works due to flood damaged at Bhaburia H/W site under Jamgora-Jagannathpur & Gourbazar-Ichhapur piped W/s Scheme.(Part-A) |  |  | ORD/000375/2021-2022 | 113/DWSD | 01/02/2022 | 21/02/2022 | RANAJOY ENTERPRISE | 4.31 | 0 | 0 | 0
22 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of Jamgara,Jagannathpur,Kalinagar,Kendula,Kalikapur & Banshia mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07524 | Retrofitting | Constinuation order for the work of Providing functional houe hold tap connection (FHTC) in connection with JJM at Shyamsundarpur mouza(JL-07) block-Durgapur-Faridpur , Dist Paschim Bardhaman under Gourbazar-Ichhapur piped W/s Scheme under DWSD,PHE Dte |  |  | ORD/000277/2021-2022 | 1643/DWSD | 23/11/2021 | 03/12/2021 | PRAVAT SARKAR | 4.96 | 0 | 0 | 0
23 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of Jamgara,Jagannathpur,Kalinagar,Kendula,Kalikapur & Banshia mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07524 | Retrofitting | Continuation for the work of balance work for providing functional household tap connection (FHTC) in connection with JJM at Jagannathpur mouza (JL-26) under command area of Jamgora -Jagannathpur piped W/s Scheme under Durgapur-Faridpur block of DWSD,PHE Dte |  |  | ORD/000412/2021-2022 | 244/DWSD | 22/02/2022 | 19/03/2022 | M/S BADAL GHOSH | 2.09 | 0 | 0 | 0
24 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of Jamgara,Jagannathpur,Kalinagar,Kendula,Kalikapur & Banshia mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07524 | Retrofitting | Acceptance cum formal order for the work of Supplying and laying of 200 mm dia UPVC pipe line from Hetedoba OHR to Zero point towards SARPI more road of Improvement of Jamgora-Jagannathpur piped W/s Scheme under DWSD, PHE Dte (SL-06) |  |  | ORD/000091/2022-2023 | 723/DWSD | 06/05/2022 | 21/05/2022 | BABA LOKENATH ENTERPRISE | 30.27 | 0 | 0 | 0
25 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Retrofitting of Jamgara,Jagannathpur,Kalinagar,Kendula,Kalikapur & Banshia mouzas for providing FHTC under Durgapur W/s Division, PHE Dte. | SM/07524 | Retrofitting | Formal order for the work of Laying of additional distribution pipe line with necessary allied works at Patsaora mouza under Gourbazar-Ichhapur piped W/S Scheme for FHT C work under DWSD, PHE Dte.(SL-03) |  |  | ORD/000172/2022-2023 | 1146/DWSD | 28/07/2022 | 17/08/2022 | SHWET BARANI | 5.69 | 0 | 0 | 0
Total | [13 empty] | 156.55 | 0 | 0