## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. | SM/08877 | New | Acceptance cum formal order for the work of Construction of Pump house cum chlorine room and switch room at Molandighi (Tube well no ¿III) sites under Bistupur piped W/S scheme under DWSD,PHE Dte (SL-21) |  |  | ORD/000334/2021-2022 | 1810/DWSD | 29/12/2021 | 12/02/2022 | DARPAN DAS & CO. | 4.67 | 3.59 | 76.91 | 0
2 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. | SM/08877 | New | Formal order for the work of Sinking of 1 No (300X200 mm) dia tube well 120 mtr deep by DR rig method using PVC pipe and fiber glass reinforced epoxy resin slotted at Tube well no 3 site of Bistupur piped W/s Scheme under Durgapur W/s Division, PHE Dte (SL-02) |  |  | ORD/000257/2021-2022 | 1679/DWSD | 01/12/2021 | 26/12/2021 | SK. ALIM | 9.32 | 6.7 | 71.96 | 0
3 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. | SM/08877 | New | Fomal order for the work of Supplying laying and alinging of UPVC distribution pipe line (distribution system Part-B) and allied works including FHTC and connecrtion provided to Kuldiha,Pathardihi,Keshabpur moluzas under command area of Bistupur piped W/s Scheme under Durgapur W/s Division, PHE Dte |  |  | ORD/000353/2021-2022 | 148/DWSD | 07/02/2022 | 09/03/2022 | TARA CONSTRUCTION | 147.47 | 139.68 | 94.72 | 0
4 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. | SM/08877 | New | Acceptance cum formal order for the work of Construction of Pump house cum chlorine room and switch room at Molandighi (Tube well no ¿II) sites under Bistupur piped W/S scheme under DWSD,PHE Dte |  |  | ORD/000332/2021-2022 | 1808/DWSD | 29/12/2021 | 12/02/2022 | CHATTERJEE CONSTRUCTION | 4.67 | 3.59 | 76.9 | 0
5 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. | SM/08877 | New | Formal order for the work of Laying and aligning of DI K9 Rising main pipe line supplying of DI Specials and valves and other allied works under Command area of Bistupur piped W/s Scheme under DWSD PHE Dte (SL-12) |  |  | ORD/000109/2022-2023 | 749/DWSD | 10/05/2022 | 30/05/2022 | MAK CONSTRUCTION CO. | 17.52 | 14.97 | 85.47 | 0
6 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. | SM/08877 | New | Acceptance cum formal order for the work of Supplying laying and aligning of UPVC distributing pipe line and allied works including FHTC and connection providing Kuldiha(JL-53),Pathardiha(JL-52) ,Keshbpur(JL-66) Mouzas under command area of Bistupur distribution system (Part-B) of Bistupur piped W/S Scheme under DWSD,PHE Dte. (SL-03) |  |  | ORD/000128/2022-2023 | 815/DWSD | 21/05/2022 | 15/06/2022 | TARA CONSTRUCTION | 54.66 | 42.36 | 77.49 | 0
7 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. | SM/08877 | New | Acceptance cum formal order for the work of Sanitary arrangement and plumbing works at Molandighi H/W site Pump house No-3 Tube well No-03 for Bistupur pipe W/S Scheme under DWSD,PHE Dte (SL-06) |  |  | ORD/000199/2022-2023 | 1061/DWSD | 08/07/2022 | 02/08/2022 | DARPAN DAS & CO. | 4.82 | 3.02 | 62.62 | 0
8 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. | SM/08877 | New | Acceptance cum formal order for the work of supplying and laying of 150 mm dia MS water carrying pipe with making necessary bend and others allied works at node point -414,323 and 540 near Kuldiha boys club ,Kuldiha More bus stand and Kuldiha bordoba More, Kanksa Block under Bistupur piped W/S Scheme under DWSD,PHE Dte. (SL-04) |  |  | ORD/000260/2022-2023 | 1577/DWSD | 02/11/2022 | 17/11/2022 | TARA CONSTRUCTION | 37.4 | 33.92 | 90.68 | 0
9 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. | SM/08877 | New | Acceptance cum formal order for the work of Construction of Pump house cum chlorine room and switch room at Bistupur Head work sites (Tube well no ¿I) under Bistupur piped W/S scheme under DWSD,PHE Dte (SL-18) |  |  | ORD/000331/2021-2022 | 1805/DWSD | 28/12/2021 | 11/02/2022 | BABA LOKENATH ENTERPRISE | 4.87 | 4.2 | 86.06 | 0
10 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. | SM/08877 | New | Continuation order for the work of soil investigation for determining the safe bearing capacity and other relevant parameters of soil for the work of construction of RCC Elevated At Molandighi Reservoir site of Bistupur W/s Scheme under DWSD,PHE Dte |  |  | ORD/000467/2021-2022 | 303/DWSD | 10/03/2022 | 04/04/2022 | MABCO CONSULTANT | 1.2 | 1.2 | 100 | 0
11 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. | SM/08877 | New | Acceptance cum formal order for the work of Additional work for laying and aligning of DI K9 rising main pipe line and supplying DI specials ,valves & allied works under command area of Bistupur piped W/S Scheme under DWSD ,PHE Dte (Sl-06) |  |  | ORD/000133/2022-2023 | 820/DWSD | 23/05/2022 | 07/06/2022 | MAK CONSTRUCTION CO. | 39.46 | 39.53 | 100.18 | 0
12 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. | SM/08877 | New | Acceptance cum formal order for the work of Additional work for supplying laying and aligning of UPVC distribution pipe line and allied works including FHTC and connection providing to Akandara (JL-47) ,Molandighi (JL-48),Kandarakona (JL-51),Rakhitpur (JL-42) ,Chua(JL-43),Bhagaabanpur (JL-45),Hariki(JL-50) Mouzas under command area of Bistupur distributin system (Part-A) of Bistupur piped W/s Scheme under DWSD,PHE Dte (SL-02) |  |  | ORD/000127/2022-2023 | 814/DWSD | 21/05/2022 | 15/06/2022 | MRITYUNJOY MUKHERJEE AND CO | 71.11 | 44.6 | 62.72 | 0
13 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. | SM/08877 | New | Acceptance cum formal order for the work of Construction of temporary approach road at Molandighi H/W site of Bistupur piped W/s Scheme under DWSD ,PHE Dte (SL-05) |  |  | ORD/000141/2022-2023 | 962/DWSD | 17/06/2022 | 27/06/2022 | MACHINO TECHNO | 4.11 | 4.09 | 99.74 | 0
14 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. | SM/08877 | New | Acceptance cum formal order for the work of Land development at Molandighi H/W site & back filling of Bistupur H/W site of Bistupur piped W/s Scheme under DWSD ,PHE Dte (SL-06) |  |  | ORD/000142/2022-2023 | 963/DWSD | 17/06/2022 | 27/06/2022 | MRITYUNJOY MUKHERJEE AND CO | 4.15 | 4.17 | 100.55 | 0
15 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. | SM/08877 | New | Formal order for the work of 2 Nos road crossing of distribution pipe line under Bistupur distribution main (Part-C) by modern trenchless technology through Jack pushing method at node point of Bistupur piped W/s Scheme under DWSD, PHE Dte (SL-09) |  |  | ORD/000176/2022-2023 | 1123/DWSD | 22/07/2022 | 16/08/2022 | SK. ALIM | 12.44 | 12.44 | 100 | 0
16 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. | SM/08877 | New | Formal order for the work of 3 Nos road crossing of distribution pipe line under Bistupur distribution main (Part-A) by modern trenchless technology through Jack pushing method at node point1 to 2 & 64 of Bistupur piped W/s Scheme under DWSD, PHE Dte (SL-10) |  |  | ORD/000177/2022-2023 | 1110/DWSD | 19/07/2022 | 13/08/2022 | MACHINO TECHNO | 18.64 | 18.64 | 100 | 0
17 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. | SM/08877 | New | Formal order for the work of 2 Nos road crossing of distribution pipe line under Bistupur distribution main (Part-B) by modern trenchless technology through Jack pushing method at node point-414 to 402 of Bistupur piped W/s Scheme under DWSD, PHE Dte (SL-11) |  |  | ORD/000178/2022-2023 | 1164/DWSD | 01/08/2022 | 26/08/2022 | TARA CONSTRUCTION | 12.43 | 12.43 | 100 | 0
18 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. | SM/08877 | New | Formal order for the work of 1 No road crossing of distribution pipe line under Bistupur distribution main (Part-B) by modern trenchless technology through Jack Pushing method at node point 540 of Bistupur piped W/S Scheme under DWSD,PHE Dte.(SL-01) |  |  | ORD/000170/2022-2023 | 1163/DWSD | 01/08/2022 | 26/08/2022 | TARA CONSTRUCTION | 6.21 | 6.21 | 100 | 0
19 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. | SM/08877 | New | Quotation for Bistupur Pump house no -03 |  |  | VCH/000224/2022-2023 | BP-2022-23-96 | 14/06/2022 | 14/06/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.62 | 0 | 0 | 0
20 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. | SM/08877 | New | Quatation for Bistupur Pump house no -02 |  |  | VCH/000223/2022-2023 | BP-2022-23-95 | 14/06/2022 | 14/06/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 15.76 | 0 | 0 | 0
21 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. | SM/08877 | New | Quotation for Bistupur Pamp House No 1 |  |  | VCH/000761/2021-2022 | BP-2021-22-207 | 15/03/2022 | 15/03/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.76 | 0 | 0 | 0
22 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. | SM/08877 | New | Formal order for the work of Supplying, laying and aligning of UPVC distribution pipe line (Distribution system( Part-B) and allied works including functional house holds tap connection (FHTC) and connection providing to Saraswatiganj (JL No-49) ,Bistupur (JL No-44) Mouzas under command area of Bistupur piped W/s Scheme under DWSD,PHE Dte (SL-03) |  |  | ORD/000355/2021-2022 | 150/DWSD | 07/02/2022 | 09/03/2022 | SK. ALIM | 188.51 | 186.94 | 99.17 | 0
23 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. | SM/08877 | New | Acceptance cum formal order for the work of Additional work for supplying laying and aligning of UPVC distribution pipe line and allied works including FHTC and connecting providing to Saraswatiganj (JL-49) ,Bistupur(JL-44) Mouzas under command area of Bistupur distribution system (Part-B) under Bistupur W/s Scheme (SL-01) |  |  | ORD/000126/2022-2023 | 813/DWSD | 21/05/2022 | 15/06/2022 | SK. ABDUL HALIM | 76.67 | 72.69 | 94.81 | 0
24 | PASCHIM BARDHAMAN | Kanksa | Central Mechanical | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. | SM/08877 | New | Supply , delivery & Installation of Submersible Pumping Machinery , Voltage stabiliser , Chlorinator and Internal House wiring for Tube well No. 2 of Bistupur Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/000003/2022-2023 | 734/CMD | 29/04/2022 | 29/05/2022 | MAHADEV ENTERPRISE | 9.95 | 9.73 | 97.77 | 0
25 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. | SM/08877 | New | Acceptance cum formal order for the work of Construction of boundary wall at Madhabmat H/W site (PH No-2,TW No-2) site under Bistupur piped W/s Scheme under DWSD ,PHE Dte |  |  | ORD/000521/2022-2023 | 336/DWSD | 20/02/2023 | 12/03/2023 | GHOSH & ROY ENTERPRISE | 18.36 | 15.74 | 85.7 | 0
26 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. | SM/08877 | New | Acceptance cum formal order for the work of Construction of boundary wall at Ghatakdanga H/W site (PH No-3,TW No-3) site under Bistupur piped W/s Scheme under DWSD ,PHE Dte |  |  | ORD/000523/2022-2023 | 286/A/DWSD | 16/02/2023 | 18/03/2023 | DARPAN DAS & CO. | 12.08 | 0 | 0 | 0
27 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. | SM/08877 | New | Acceptance cum formal order for the work of rising main & distribution system of Gopalpur Piped W/s Scheme under DWSD, PHE Dte |  |  | ORD/000371/2021-2022 | 66/DWSD | 19/01/2022 | 03/02/2022 | EXECUTIVE ENGINEER , RESOURCES DIVISION, PHE DTE. | 8.89 | 80.89 | 910.19 | 0
28 | PASCHIM BARDHAMAN | Kanksa | Central Mechanical | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. | SM/08877 | New | Supply & Installation of Submersible Pumping Machinery , Voltage stabilizer , Chlorinator and Internal House wiring for Tube well No. 1 of Bistupur Water Supply Scheme under CMD, PHE Dte., Dist.- Paschim Bardhaman. |  |  | ORD/000724/2021-2022 | 478/CMD | 28/03/2022 | 27/04/2022 | C.M. ENTERPRISE | 9.74 | 9.56 | 98.15 | 0
29 | PASCHIM BARDHAMAN | Kanksa | Central Mechanical | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. | SM/08877 | New | Supply & Installation of Submersible Pumping Machinery , Voltage stabiliser , Chlorination Sistem and Internal House wiring for Tube well No. 3 at Bistupur Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/000018/2022-2023 | 913/CMD | 31/05/2022 | 30/06/2022 | ASHUTOSH DAS & CO. | 9.96 | 9.69 | 97.24 | 0
30 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. | SM/08877 | New | Material Requisition To Resource Division |  |  | RTOR000004/2021-2022 | 1816/DWSD | 30/12/2021 | 30/12/2021 | Resource Division | 20.35 | 0 | 0 | 0
31 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. | SM/08877 | New | Material Requisition To Resource Division |  |  | RTOR000006/2021-2022 | 66/DWSD | 19/01/2022 | 19/01/2022 | Resource Division | 80.94 | 0 | 0 | 0
32 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. | SM/08877 | New | Material Requisition To Resource Division |  |  | RTOR000003/2021-2022 | 1752/DWSD | 16/12/2021 | 16/12/2021 | Resource Division | 1.27 | 0 | 0 | 0
33 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. | SM/08877 | New | Formal order for the work of Sinking of 2 Nos (300X200 mm) dia tube well 120 mtr deep by DR rig method using PVC pipe and fiber glass reinforced epoxy resin slotted at tube well No-01 & 02) Molandighi of Bistupur piped W/s Scheme under Durgapur W/s Division, PHE Dte (SL-03) |  |  | ORD/000258/2021-2022 | 1676/DWSD | 30/11/2021 | 04/01/2022 | M/S. D. PALIT & CO. | 18.62 | 11.91 | 63.96 | 100
34 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. | SM/08877 | New | Formal order for the work of Supplying, laying & aligning of UPVC distribution pipe line (Distribution system Part-A) and allied works including functional house holds tap connection (FHTC) and connection providing to Akandara(JL No-47) ,Molandighi(JL No-48),Kandarakona (JL_51),Rakhitpur(JL-42,Chua(JL-43),Bhagaabanpur(JL-45),Hariki(JL No-50) Mouzas under command area of Bistupur piped W/s Scheme under DWSD,PHE Dte (SL-01) |  |  | ORD/000354/2021-2022 | 149/DWSD | 07/02/2022 | 13/04/2022 | MACHINO TECHNO | 377.24 | 232.69 | 61.68 | 100
35 | PASCHIM BARDHAMAN | Kanksa | Durgapur W/S Division | Bistupur Piped Water Supply Scheme under Durgapur W/S Division PHE Dte. | SM/08877 | New | Acceptance cum formal order for the work-Construction of boundary wall at Saraswatiganj H/W site (PH No-2,TW No-2) site under Bistupur piped W/s Scheme under DWSD ,PHE Dte |  |  | ORD/000522/2022-2023 | 337/DWSD | 20/02/2023 | 22/03/2023 | CHATTERJEE CONSTRUCTION | 10.68 | 6.07 | 56.85 | 100
Total | [13 empty] | 1324.54 | 1031.24 | 77.86