## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte | SM/09875 | Augmentation | Formal order for the work of Hire & labour charges for staging and scaffolding bamboo barricading and removal of rubbish for dismantling of RCC elevated 350 M3 OHR of 20 mtr staging height at Gopalpur H/W Site under DWSD ,PHE Dte |  |  | ORD/000304/2021-2022 | 1765/DWSD | 17/12/2021 | 16/01/2022 | TARA CONSTRUCTION | 12.55 | 0 | 0 | 0
2 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte | SM/09875 | Augmentation | Formal order for the work of Laying and aligning of DI K9 rising main pipe line supplying DI Specials valves and allied works under command area of Gopalpur mouza for Augmentation of Gopalpur piped W/s Scheme under DWSD,PHE Dte |  |  | ORD/000303/2021-2022 | 1758/DWSD | 16/12/2021 | 15/01/2022 | RANJIB GHATAK | 15.53 | 0 | 0 | 0
3 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte | SM/09875 | Augmentation | Acceptance cum formal order for the work of Repairing and renovation of pump house with sanitary arrangement at Gopalpur mouza for Augmentation of Gopalpur W/S Scheme under DWSD,PHE Dte.(SL-01) |  |  | ORD/000290/2021-2022 | 1661/DWSD | 25/11/2021 | 20/12/2021 | M/S UNIQUE | 4 | 3.68 | 92.04 | 0
4 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte | SM/09875 | Augmentation | Acceptance cum formal order for the work of Repairing of leakage bursting and chokage cleaning at Gopalpur distribution system & Its all command areas of Augmentation of Gopalpur piped W/s Scheme under DWSD ,PHE Dte (SL-07) |  |  | ORD/000051/2022-2023 | 586/DWSD | 21/04/2022 | 28/04/2022 | QUICK PAL SUPPLIERS | 4.82 | 4.39 | 91 | 0
5 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte | SM/09875 | Augmentation | Acceptance cum formal order for the work of Supplying, laying and aligning of HDPE/DI distribution pipe line and allied works including FHTC and connection providing to ICDS ,Health Centre, Govt Building ,School under command area of Gopalpur Mouza of Augmentation of Gopalpur piped W/S Scheme under DWSD,PHE Dte . (SL-17) |  |  | ORD/000130/2022-2023 | 817/DWSD | 21/05/2022 | 21/11/2022 | MACHINO TECHNO | 77.49 | 51.75 | 66.78 | 0
6 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte | SM/09875 | Augmentation | Formal order for the work of Repairing as well as extension of boundary wall with supply fitting fixing of ornamental Gate at Gopalpur H/W site of Gopalpur Mouza for Augmentation of Gopalpur piped W/s Scheme under DWSD,PHE Dte |  |  | ORD/000301/2021-2022 | 1767/DWSD | 17/12/2021 | 16/01/2022 | D. S. ENTERPRISE | 8.1 | 7.18 | 88.67 | 0
7 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte | SM/09875 | Augmentation | Acceptance cum formal order for the work of rising main & distribution system of Gopalpur Piped W/s Scheme under DWSD, PHE Dte |  |  | ORD/000370/2021-2022 | 65/DWSD | 19/01/2022 | 18/02/2022 | EXECUTIVE ENGINEER , RESOURCES DIVISION, PHE DTE. | 34.25 | 34.28 | 100.09 | 0
8 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte | SM/09875 | Augmentation | Acceptance cum formal order for the work of dismantling of abandoned existing structure at Gopalpur H/W site of Augmentation of Gopalpur W/S Scheme under DWSD,PHE Dte.(SL-02) |  |  | ORD/000289/2021-2022 | 1660/DWSD | 25/11/2021 | 15/12/2021 | QUICK PAL SUPPLIERS | 3.94 | 3.87 | 98.33 | 0
9 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte | SM/09875 | Augmentation | Acceptance cum formal order for the work of Distribution of abandoned existing structure at Gopalpur H/W site and others Pump House site under Augmentation of Gopalpur W/s Scheme of DWSD,PHE Dte (SL-08) |  |  | ORD/000052/2022-2023 | 587/DWSD | 21/04/2022 | 28/04/2022 | CHATTERJEE CONSTRUCTION | 2.16 | 2.07 | 95.77 | 0
10 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte | SM/09875 | Augmentation | Formal order for the work of Dismantling of existing boundary wall and reconstruction of balance portion boundary wall at Gopalpur H/W site (OHR) site of Augmentation of Gopalpur piped W/s Scheme under DWSD ,PHE Dte (SL-09) |  |  | ORD/000104/2022-2023 | 750/DWSD | 10/05/2022 | 20/05/2022 | D. S. ENTERPRISE | 29.41 | 29.22 | 99.34 | 0
11 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte | SM/09875 | Augmentation | Continuation for the work of soil investigation for demining the safe bearing capacity and other relevant parameters of soil for the work of construction of RCC Elevated at Gopalpur Reservoir site of Augmentation of Gopalpur W/s Scheme under DWSD ,PHEDte |  |  | ORD/000468/2021-2022 | 353/DWSD | 21/03/2022 | 15/04/2022 | MABCO CONSULTANT | 1.2 | 1.2 | 100 | 0
12 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte | SM/09875 | Augmentation | Acceptance cum formal order for the work of Construction of temporary approach road at Gopalpur H/W site of Gopalpur piped W/s Scheme under DWSD ,PHE Dte(SL-07) |  |  | ORD/000143/2022-2023 | 975/DWSD | 22/06/2022 | 07/07/2022 | AMAR CONSTRUCTION | 4.11 | 3.97 | 96.74 | 0
13 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte | SM/09875 | Augmentation | Acceptance cum formal order for the work of Land development at Gopalpur H/W site and back filling along the boundary wall of Augmentation of Gopalpur piped W/s Scheme under DWSD ,PHE Dte (SL-12) |  |  | ORD/000147/2022-2023 | 979/DWSD | 22/06/2022 | 07/07/2022 | AMAR CONSTRUCTION | 4.63 | 4.39 | 94.93 | 0
14 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte | SM/09875 | Augmentation | Quotation for Gopalpur Pump house no -02 |  |  | VCH/000221/2022-2023 | BP-2022-23-93 | 14/06/2022 | 14/06/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.48 | 0 | 0 | 0
15 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte | SM/09875 | Augmentation | Quotation for Gopalpur Pamp House No 1 |  |  | VCH/000762/2021-2022 | BP-2021-22-208 | 15/03/2022 | 15/03/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.77 | 0 | 0 | 0
16 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte | SM/09875 | Augmentation | Quotation for Gopalpur Pump house no -03 |  |  | VCH/000222/2022-2023 | BP-2022-23-94 | 14/06/2022 | 14/06/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.81 | 0 | 0 | 0
17 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte | SM/09875 | Augmentation | Formal order for the work of Sinking 3(Three) Nos 300X200 mm dia Tube well 210 mtr deep by DR ring method using PVC pipe and fibber glass reinforced epoxy resin slotted at Gopalpur H/W site under Augmentation of Gopalpur piped W/s Scheme under Durgapur W/S Division, PHE Dte. |  |  | ORD/000286/2021-2022 | 1749/DWSD | 15/12/2021 | 14/01/2022 | M/S. D. PALIT & CO. | 42.11 | 27.75 | 65.9 | 100
18 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte | SM/09875 | Augmentation | Acceptance for the work fabrication and erection of MS structural bridge used to cross 600 mm dia rising main pipe line near Bankura more under surface based W/s Scheme for Panagarh Industrial Park under DWSD,PHE Dte (SL-03) |  |  | ORD/000288/2021-2022 | 1715/DWSD | 09/12/2021 | 18/01/2022 | MACHINO TECHNO | 68.77 | 0 | 0 | 0
19 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte | SM/09875 | Augmentation | Continuation order for the work of Hiring of Luxury diesel Ambassador car including higher model -2012 on wards of diesel Ambassador or equivalent for official use of the Assistant Engineer of EE/DWSD/PHE Dte for the use of the Office of the EE/DWSD/PHE Dte ADDA Adm: Building EPIP Complex ,Banskopa ,Durgapur-713212(w.e.f 01.05.2022 to 30.04.2023) (Vehicle No-WB37D6848) |  |  | ORD/000095/2022-2023 | 687/DWSD | 28/04/2022 | 28/04/2023 | PRAMIT CHATTERJEE | 1.65 | 4.36 | 265 | 0
20 | PASCHIM BARDHAMAN |  | Central Mechanical | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte | SM/09875 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 3 at Augmentation of Gopalpur Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/000158/2022-2023 | 1243/CMD | 12/07/2022 | 11/08/2022 | GOENKA ENTERPRISE | 10.21 | 10.09 | 98.86 | 0
21 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte | SM/09875 | Augmentation | Acceptance cum formal order for the work of Hiring of LUXURY Diesel Ambassador Car including higher model 2012 onwards of Diesel Ambassador or equivalent for official use (Inspection Vehicle for site vigit against JJM related scheme) for the office of the Executive Engineer ,Durgapur Water Supply Division, Public Health Engineering (w.e.f 01.01.2023 to 30.06.2023).(Sl-01) |  |  | ORD/000438/2022-2023 | 1801/DWSD | 30/12/2022 | 30/06/2023 | PRAMIT CHATTERJEE | 0.82 | 1.6 | 194 | 0
22 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte | SM/09875 | Augmentation | Continuation order for the work of Hiring of Luxury diesel Ambassador car including higher model -2012 on wards of diesel Ambassador or equivalent for official use of the Assistant Engineer of EE/DWSD/PHE Dte for the use of the Office of the EE/DWSD/PHE Dte ADDA Adm: Building EPIP Complex ,Banskopa ,Durgapur-713212(w.e.f 01.05.2023 to 31.10.2023) (Vehicle No-WB37D6848) |  |  | ORD/000020/2023-2024 | 654/DWSD | 27/04/2023 | 27/10/2023 | PRAMIT CHATTERJEE | 0.82 | 2.36 | 286.65 | 100
23 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte | SM/09875 | Augmentation | Formal order for the work of Repairing and renovation of PH with sanitary arrangement as well as boundary wall at PH site (T.No-II & III) of crackly nature of soil according to Deptt drawing no GWSS/EC/PHE Dte /DRG-3/7-8 ,Size-5.9X4.10 m out to out) at Gopalpur mouza for Augmentation of Gopalpur piped W/s Scheme under DWSD,PHE Dte |  |  | ORD/000302/2021-2022 | 1737/DWSD | 13/12/2021 | 27/01/2022 | CHANDAN HAZRA | 25.78 | 24.35 | 94.44 | 100
24 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte | SM/09875 | Augmentation | Acceptance cum formal order for the work of Supplying fitting fixing of PCC precast pillar and fencing with barbed wire errection of Govt sign board 03 nos place for protection of vest land at Molandighi of Bistupur W/s Scheme of 03 Nos at Gopalpur of Augmentation of Gopal pur piped W/s Scheme |  |  | ORD/000362/2021-2022 | 84/DWSD | 25/01/2022 | 09/02/2022 | MD JAWED KHAN | 2.33 | 2.33 | 100 | 0
25 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte | SM/09875 | Augmentation | Acceptance cum formal order for the work of Electric wiring and other allied works for modernization of the existing Gopalpur lab for NABL accreditation of Sub-District Water test ing lab at Kanksa of Jamgora-Jagannathpur piped W/s Scheme under DWSD ,PHE Dte |  |  | ORD/000368/2021-2022 | 100/DWSD | 31/01/2022 | 15/02/2022 | BASANTI TRADERS | 1.65 | 1.57 | 95.25 | 0
26 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte | SM/09875 | Augmentation | Acceptance cum formal order for the work of Details route survey, drawing design of distribution network & preparation of estimates and DPR in connection with the JJM (FHTC) of Augmentation of Gopalpur piped W/S Scheme DWSD, PHE Dte.(SL-02) |  |  | ORD/000336/2021-2022 | 1685/DWSD | 02/12/2021 | 01/01/2022 | M/S R.DUTTA AND CO. | 8.48 | 8.48 | 100 | 0
27 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte | SM/09875 | Augmentation | Acceptance cum formal order for the work of Construction of pump house cum chlorine room at Railpar Sarada Pally H/W site pump house No-2 tube well No-02 for Augmentation of Kanksa (Zone-II/D) pipe W/s Scheme under DWSD ,PHE Dte (SL-02) |  |  | ORD/000401/2021-2022 | 241/DWSD | 25/02/2022 | 11/04/2022 | MUKHERJEE ENTERPRISE | 4.89 | 1.01 | 20.59 | 100
28 | PASCHIM BARDHAMAN |  | Central Mechanical | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte | SM/09875 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage stabiliser , Chlorinator and Internal House wiring for Tube well No. 1 of Gopalpur Water Supply Scheme under CMD, PHE Dte., Dist.- Paschim Bardhaman. |  |  | ORD/000725/2021-2022 | 477/CMD | 28/03/2022 | 27/04/2022 | RNS TRADING | 9.64 | 9.48 | 98.35 | 0
29 | PASCHIM BARDHAMAN |  | Central Mechanical | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte | SM/09875 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 2 at Augmentation of Gopalpur Water Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. |  |  | ORD/000016/2022-2023 | 911/CMD | 31/05/2022 | 30/06/2022 | INDIA ENTERPRISE | 9.16 | 8.95 | 97.8 | 0
30 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte | SM/09875 | Augmentation | Acceptance cum formal order for the work of Extension of existing Gopalpur sub district laboratory at Kanksa of Augmentation of Gopalpur piped W/s Scheme under DWD ,PHE Dte (SL-13) |  |  | ORD/000148/2022-2023 | 980/DWSD | 22/06/2022 | 07/07/2022 | BASANTI TRADERS | 4.94 | 3.9 | 78.97 | 100
31 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte | SM/09875 | Augmentation | Hiring of LUXURY Diesel Ambassador Car including higher model 2012 onwards of Diesel Ambassador or equivalent for official use for the Executive Engineer, DWSD,PHE Dte ADDA Administrative building 2nd Floor, EPIP Complex,Banskopa,DGP-12 (w.e.f 18.08.2022 to 17.02.2023). (SL-02) |  |  | ORD/000219/2022-2023 | 1237/DWSD | 17/08/2022 | 17/02/2023 | PRAMIT CHATTERJEE | 0.82 | 2.38 | 288.57 | 0
32 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte | SM/09875 | Augmentation | Hiring of LUXURY Diesel Ambassador Car including higher model 2012 onwards of Diesel Ambassador or equivalent for official use (Inspection Vehicle) of Assistant Engineer for the office of the Executive Engineer ,Durgapur Water Supply Division, Public Health Engineering (w.e.f 01.09.2022 to 28.02.2023). (Sl-01) |  |  | ORD/000218/2022-2023 | 1236/DWSD | 17/08/2022 | 17/02/2023 | BIPLAB BANERJEE | 0.82 | 2.4 | 291.37 | 0
33 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte | SM/09875 | Augmentation | Formal order for the work of Laying of 600 mm dia RCC (NP3) Hume pipe by modern Hydraulic Jack pushing method including laying 150 mm dia MS pipe line at DVC More over Suri road (NH-60) for ROB under Augmentation of RCFA Part-III W/s Scheme (Zone-II) under DWSD, PHE Dte (SL_12) |  |  | ORD/000261/2022-2023 | 872/DWSD | 26/05/2022 | 10/06/2022 | RANJIB GHATAK | 13.63 | 0 | 0.01 | 100
34 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte | SM/09875 | Augmentation | Acceptance cum formal order for the work of Water supply arrangement at Kajladighi ICDS Centre of Bibihar GP having no Electricity power supply to provide solar power connection (For 350 Nos Students), Kanksa Block under Aug: of Gopalpur piped W/s Scheme under DWSD ,PHE Dte |  |  | ORD/000471/2022-2023 | 294/DWSD | 17/02/2023 | 04/03/2023 | RANJIB GHATAK | 6.95 | 6.95 | 100 | 100
35 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte | SM/09875 | Augmentation | Formal order for the work Laying and aligning of distribution pipe line from Bonsol to towards Jhajra Majipara and allied works under Augmentation of Gopalpur piped W/s Scheme under DWSD ,PHE Dte. |  |  | ORD/000440/2022-2023 | 300/DWSD | 20/02/2023 | 07/03/2023 | BABA LOKENATH ENTERPRISE | 6.27 | 6.27 | 100 | 0
36 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte | SM/09875 | Augmentation | Acceptance order for the work of Balance work for construction of boundary wall at Gopalpur H/W site (OHR) site of Augmentation of Gopalpur piped W/s Scheme under DWSD,PHE Dte |  |  | ORD/000448/2022-2023 | 111/DWSD | 24/01/2023 | 08/02/2023 | D. S. ENTERPRISE | 4.36 | 4.34 | 99.54 | 0
37 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte | SM/09875 | Augmentation | Acceptance cum formal order for the work of Concreting of exiting dismantled road of Augmentation of Gopalpur piped W/S Scheme under DWSD,PHE Dte (Part-B) |  |  | ORD/000047/2023-2024 | 771/DWSD. | 22/05/2023 | 01/06/2023 | GHOSH & ROY ENTERPRISE | 4.83 | 4.83 | 100 | 100
38 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte | SM/09875 | Augmentation | Acceptance cum formal order for the work of Concreting of exiting dismantled road of Augmentation of Gopalpur piped W/S Scheme under DWSD,PHE Dte (Part-A) |  |  | ORD/000045/2023-2024 | 768/DWSD | 22/05/2023 | 01/06/2023 | SAIKAT RAY | 4.96 | 4.96 | 99.99 | 100
39 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte | SM/09875 | Augmentation | Acceptance cum formal order for the work of Replacement of existing pipe line at Nachan OHR to Protapur gram for Physical certification of HarGhar Jal in connection with JJM of Augmentation Gopalpur piped W/s Scheme under DWSD ,PHE Dte (SL-03) |  |  | ORD/000026/2023-2024 | 758/DWSD | 19/05/2023 | 08/06/2023 | GHOSH & ROY ENTERPRISE | 9.66 | 9.64 | 99.74 | 100
40 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte | SM/09875 | Augmentation | Acceptance cum formal order for the work of Replacement of existing pipe line and extended the same of total command area of distribution network for physical certification of Har Ghat Jal in connection with JJM of Augmentation of Gopalpur piped W/S Scheme under DWSD ,PHE Dte. |  |  | ORD/000107/2023-2024 | 1135/DWSD | 20/07/2023 | 19/08/2023 | MD AAMIR KHAN | 25.46 | 23.4 | 91.91 | 100
41 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte | SM/09875 | Augmentation | Acceptance cum formal order for the work of Additional concreting of exiting dismantled road after extension of pipe line and retrofitting of existing pipe distribution system of kanksa block under Augmentation of Gopalpur piped W/s Scheme (Part-A, B) |  |  | ORD/000145/2023-2024 | 1275/DWSD | 07/08/2023 | 22/08/2023 | JOY GURU ENTERPRISE | 8.95 | 8.94 | 99.98 | 100
42 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte | SM/09875 | Augmentation | Acceptance cum formal order for the work of Additional concreting of exiting dismantled road after extension of pipe line and retrofitting of existing pipe distribution system of kanksa block under Augmentation of Roopganj piped W/s Scheme (Part-A, B) |  |  | ORD/000146/2023-2024 | 1276/DWSD | 07/08/2023 | 22/08/2023 | JOY GURU ENTERPRISE | 8.95 | 8.95 | 100 | 100
43 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte | SM/09875 | Augmentation | Formal for the work of Construction of 500 M3 capacity ,20 Mtr staging height RCC Elevated Over Head Reservoir at Gopalpur under Augmentation of Gopalpur piped W/s Scheme under DWSD, PHE Dte.(SL-02) |  |  | ORD/000287/2021-2022 | 1745/DWSD | 15/12/2021 | 17/06/2022 | AMAR CONSTRUCTION | 92 | 78.97 | 85.83 | 0
44 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte | SM/09875 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000005/2021-2022 | 1815/DWSD | 30/12/2021 | 30/12/2021 | Resource Division | 19.8 | 0 | 0 | 0
45 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte | SM/09875 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000007/2021-2022 | 65/DWSD | 19/01/2022 | 19/01/2022 | Resource Division | 34.32 | 0 | 0 | 0
46 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte | SM/09875 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000002/2021-2022 | 1751/DWSD | 16/12/2021 | 16/12/2021 | Resource Division | 1.27 | 0 | 0 | 0
47 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte | SM/09875 | Augmentation |  |  |  | BILL/00242/2023-2024 | BP-2023-24-121 | 07/08/2023 | 07/08/2023 | P C FORMS & STATIONERY | 0.19 | 0 | 0 | 0
48 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte | SM/09875 | Augmentation | Continuation order for the work of Hiring of Luxury diesel Ambassador car including higher model -2012 on wards of diesel Ambassador or equivalent for official use of the Assistant Engineer of EE/DWSD/PHE Dte for the use of the Office of the EE/DWSD/PHE Dte ADDA Adm: Building EPIP Complex ,Banskopa ,Durgapur-713212(w.e.f 01.11.2023 to 30.04.2024) (Vehicle No-WB37D6848) |  |  | ORD/000272/2023-2024 | 1702/DWSD | 31/10/2023 | 30/04/2024 | PRAMIT CHATTERJEE | 0.82 | 1.57 | 190.61 | 60
49 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte | SM/09875 | Augmentation | Continuation order for supplying laying and aligning of UPVC distribution pipe line and allied works including FHTC and connection providing to Akandara (JL-47) ,Molandighi (JL-48),Kandarakona (JL-51),Rakhitpur (JL-42) ,Chua(JL-43),Bhagaabanpur (JL-45),Hariki(JL-50) Mouzas under command area of Bistupur distributin system (Part-A) of Augmentation of Gopalpur piped W/s Scheme under DWSD,PHE Dte | Assistant Engineer-II | JUNIOR ENGINEER-2,Junior Engineer_3 | ORD/000691/2022-2023 | 702/DWSD | 29/04/2022 | 24/05/2022 | MACHINO TECHNO | 67.7 | 67.42 | 99.58 | 100
50 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte | SM/09875 | Augmentation | Formal order for the work of Supplying ,laying and aligning of HDPE/DI distribution pipe line and allied works including functinal household tap connection (FHTC) and connection provided to ICDS ,Health Centre ,Govt Bioldings school under the command area of Gopalpur mouza of Augmentation of Gopalpur piped W/s Scheme under Durgapur W/S Division, PHE Dte. |  |  | ORD/000341/2021-2022 | 68/DWSD | 19/01/2022 | 18/07/2022 | MRITYUNJOY MUKHERJEE AND CO | 494.51 | 304.99 | 61.68 | 100
51 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte | SM/09875 | Augmentation | Additional concreting of exiting dismantled road after extension of pipe line and retrofitting of existing pipe distribution system of kanksa block under Augmentation of Gopalpur piped W/s Scheme. |  |  | ORD/000171/2023-2024 | 1302/DWSD | 07/08/2023 | 22/08/2023 | V.C.CONSTRUCTION | 4.75 | 4.71 | 99.06 | 100
52 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte | SM/09875 | Augmentation | Continuation order for the work of Supplying ,laying and aligning of HDPE/DI distribution pipe line and allied works including functinal household tap connection (FHTC) and connection provided to ICDS ,Health Centre ,Govt Bioldings school under the command area of Gopalpur mouza of Augmentation of Gopalpur piped W/s Scheme under Durgapur W/S Division, PHE Dte. | Assistant Engineer-II | JUNIOR ENGINEER-2,Junior Engineer_3 | ORD/000689/2022-2023 | 700/DWSD | 29/04/2022 | 28/07/2022 | MRITYUNJOY MUKHERJEE AND CO | 66.45 | 65.8 | 99.02 | 100
53 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte | SM/09875 | Augmentation | Acceptance cum formal order for the work of Additional work for restoration and repairing of pipe line and construction of Sluice Valve chamber and cement concrete and other allied works for Augmentation of Gopalpur W/S Scheme under DWSD ,PHE Dte . |  |  | ORD/000274/2023-2024 | 1561/DWSD | 20/09/2023 | 05/08/2025 | AMAR CONSTRUCTION | 5.15 | 0 | 0 | 100
54 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte | SM/09875 | Augmentation | Implememntation of Har Ghar Jal for Providing FHTC in connection with JJM for Pratapur, Nachan mouza ,Dhabani mouza (JL-48) under Retrofitting of Jemua piped W/s Scheme, Augmentation of Bistupur water supply scheme, Augmentation of Gopalpur, water supply scheme, Augmentation of Roopganj Water supply scheme of Durgapur-Faridpur Block (SM/16249) |  |  | ORD/000085/2023-2024 | 1074/DWSD | 12/07/2023 | 01/08/2023 | MUKHERJEE ENTERPRISE | 18.4 | 18.19 | 98.86 | 100
55 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Gopalpur (JJM Revision) Piped Water Supply Scheme within Kanksa Block of Paschim Bardhaman District under Durgapur W/S Division PHe Dte | SM/09875 | Augmentation | Acceptance cum formal order for the work of Construction of boundary wall at OHR site approach road ,drain blower room and plantation and other allied works of Jemua W/S Scheme under Augmentation of Gopalpur W/s Scheme of Durgapur-Faridpur Block under DWSD, PHE Dte | Assistant Engineer 3 | Junior Engineer 7 | ORD/001235/2023-2024 | 587/DWSD | 11/04/2023 | 26/05/2023 | GITA CONSTRUCTION | 61.45 | 58.7 | 95.51 | 100
Total | [13 empty] | 1361.98 | 935.63 | 68.7