## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte | SM/10203 | Augmentation | Formal order for the work of Supplying laying and aligning of HDPE distribution pipe line and allied works under command area o Roopganj mouza of Augmentation of Roopganj piped W/s Scheme under DWSD, PHE Dte (SL-07) |  |  | ORD/000173/2022-2023 | 1165/DWSD | 01/08/2022 | 31/08/2022 | M/S BADAL GHOSH | 60.68 | 59.5 | 98.06 | 0
2 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte | SM/10203 | Augmentation | Acceptance cum formal order for the work of Repairing and renovation of pump house with sanitary arrangement at Roopganj near tube well under Augmentation of Roopganj piped W/s Scheme under DWSD, PHE Dte (SL-08) |  |  | ORD/000158/2022-2023 | 1028/DWSD | 04/07/2022 | 11/07/2022 | R.C.ENTERPRISE | 4.01 | 0 | 0 | 0
3 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte | SM/10203 | Augmentation | Acceptance cum formal order for the work of Construction of Pump house cum Chlorine room at ARRAH bazar T.No-III Pump house & tube well no-3 for Augmentation of Roopganj piped W/s Scheme under DWSD,PHE Dte (SL-03) |  |  | ORD/000138/2022-2023 | 954/DWSD | 16/06/2022 | 31/07/2022 | KIRON ENTERPRISE | 4.87 | 2.44 | 50.16 | 0
4 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte | SM/10203 | Augmentation | Formal order for the work of Replacement of damaged AC pipe with 90 mm dia HDPE from Roopganj more to Araichand gram of Augmentation of Roopganj Piped W/s Scheme under DWSD ,PHE Dte(SL-01) |  |  | ORD/000407/2021-2022 | 334/DWSD | 15/03/2022 | 30/03/2022 | M/S KALYANI ENTERPRISE | 10.23 | 10.25 | 100.12 | 0
5 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte | SM/10203 | Augmentation | Acceptance cum formal order for the work of Sinking of 1 No (250 mm X 150 mm dia) 210 mtr depth Direct Rotary method using PVC pipe and fibber glass reinforced epoxy resin slotted at ARRAH BAZAR (T.No-03) under Augmentation of Roopganj piped W/S Scheme under DWSD, PHE Dte.(SL-11) |  |  | ORD/000125/2022-2023 | 812/DWSD | 21/05/2022 | 31/05/2022 | JOY GURU ENTERPRISE | 11.86 | 11 | 92.69 | 0
6 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte | SM/10203 | Augmentation | Acceptance cum formal order for the work of Sinking of 1 No(300X200 mm dia)-Sinking of 1 No (300 mm X 200 mm dia) 210 mtr depth Direct Rotary method using PVC pipe and fibber glass reinforced epoxy resin slotted at ARRAH SIBTALA (T.No-01) under Augmentation of Roopganj piped W/S Scheme under DWSD, PHE Dte (SL-10) |  |  | ORD/000124/2022-2023 | 811/DWSD | 21/05/2022 | 31/05/2022 | JOY GURU ENTERPRISE | 13.78 | 12.81 | 92.94 | 0
7 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte | SM/10203 | Augmentation | Formal order for the work of Supplying laying and aligning of HDPE distribution pipe line and Other allied works under command area of ARRAH Mouza (Part-C) under Augmentation of Roopganj piped W/s Scheme under DWSD,PHE Dte (SL-03) |  |  | ORD/000418/2021-2022 | 402/DWSD | 29/03/2022 | 23/04/2022 | M/S KALYANI ENTERPRISE | 26.32 | 27.01 | 102.64 | 0
8 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte | SM/10203 | Augmentation | Quatation for Roopganj Pump house no -03 |  |  | VCH/000220/2022-2023 | BP-2022-23-92 | 14/06/2022 | 14/06/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.29 | 0 | 0 | 0
9 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte | SM/10203 | Augmentation | Quotation for Roopganj Pump house no -04 |  |  | VCH/000233/2022-2023 | BP-2022-23-104 | 02/07/2022 | 02/07/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.68 | 0 | 0 | 0
10 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte | SM/10203 | Augmentation | Acceptance cum formal order for the work of Construction of 5.40 X3.60 mtr switch room with plinth height (600X 2000 mm) with sanitary and water supply arrangemnt at PH No-3 TW No-3 site of Augmentation of Roopganj piped W/S Scheme under DWSD ,PHE Dte. |  |  | ORD/000512/2022-2023 | 329/DWSD | 20/02/2023 | 22/03/2023 | MAA KHEPIMAYER CHARANE | 6.9 | 0 | 0 | 0
11 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte | SM/10203 | Augmentation | Formal order for the work of Restoration of drain PCC road at Roopganj and Arrah repairing of valve chamber ,construction of masonry community tank with supply of 2000 Ltrs PVC tank at Arrah Samshan supply fitting fixing and installation of sluice valve under DWSD,PHE Dte (SL-01) |  |  | ORD/000200/2021-2022 | 1640/DWSD | 23/11/2021 | 07/01/2022 | M/S KALYANI ENTERPRISE | 12.12 | 10.04 | 82.83 | 0
12 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte | SM/10203 | Augmentation | Formal order for the work of Supplying laying and aligning of HDPE distribution pipe line and Other allied works under command area of ARRAH Mouza (Part-A) under Augmentation of Roopganj piped W/s Scheme under DWSD,PHE Dte (SL-01) |  |  | ORD/000420/2021-2022 | 404/DWSD | 29/03/2022 | 23/04/2022 | DARPAN DAS & CO. | 63.18 | 49.67 | 78.62 | 0
13 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte | SM/10203 | Augmentation | Formal order for the work of Construction of 350 M3 capacity Over Head Reservoir having 20 Mtr staging height of RCC OHR at Roopganj H/W site under Augmentation of Roopganj piped W/s Scheme under DWSD,PHE Dte (SL-05) |  |  | ORD/000419/2021-2022 | 416/A/DWSD | 30/03/2022 | 26/09/2022 | AMARANJALI CONSTRUCTION | 83.6 | 35.9 | 42.95 | 75
14 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte | SM/10203 | Augmentation | Formal order for the work of Supplying laying and aligning of HDPE distribution pipe line and Other allied works under command area of ARRAH Mouza (Part-B) under Augmentation of Roopganj piped W/s Scheme under DWSD,PHE Dte (SL-02) |  |  | ORD/000422/2021-2022 | 401/DWSD | 29/03/2022 | 28/04/2022 | M/S KALYANI ENTERPRISE | 92.48 | 87.5 | 94.61 | 0
15 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte | SM/10203 | Augmentation | Acceptance cum formal order for the work of Construction of pump house cum Chlorine room at Roopganj H/W site near TW-1/2/3 pf Augmentation of Roopganj piped W/S Scheme under DWSD ,PHE Dte (SL-09) |  |  | ORD/000159/2022-2023 | 1029/DWSD | 04/07/2022 | 19/07/2022 | R.C.ENTERPRISE | 4.45 | 3.23 | 72.65 | 0
16 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte | SM/10203 | Augmentation | Acceptance cum formal order for the work of Sinking of 01 Nos 300X200 mm dia Tube well with 210 mtr deapth by DR rig method using UPVC pipe (CD and UPVC deep well screen (RDS) at Roogganj H/W site of Kanksa Block of Augmentation of Roopganj piped W/s Scheme udner DWSD ,PHE Dte |  |  | ORD/000455/2022-2023 | 308/DWSD | 20/02/2023 | 07/03/2023 | M/S BADAL GHOSH | 15.73 | 13.44 | 85.43 | 0
17 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte | SM/10203 | Augmentation | Acceptance cum formal order for the work of Re-connection of exiting FHTC from AC pipe line to newly laid different dia pipe line FHTC and also few new connection with JJM for Roopganj mouza (JL-54) under command area of Augmentation of Roopganj W/s Scheme,Block-Kanksa under DWSD ,PHE Dte. |  |  | ORD/000478/2022-2023 | 317/DWSD | 20/02/2023 | 17/03/2023 | M/S BADAL GHOSH | 57.68 | 50.62 | 87.75 | 0
18 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte | SM/10203 | Augmentation | Acceptance cum formal order for the work of Balance work for laying of HDPE pipe line for providing FHTC in connection with JJM at Arrah mouza (JL-89) part-C under command area of Augmentation of Roopganj piped W/s Scheme under DWSD ,PHE Dte |  |  | ORD/000519/2022-2023 | 319/DWSD | 20/02/2023 | 12/03/2023 | M/S BADAL GHOSH | 97.2 | 73.7 | 75.82 | 100
19 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte | SM/10203 | Augmentation | Emergent work of concreting of exiting dismantalled road at Roopganj under Augmentation of Roopganj piped W/s Scheme (SM/10203) |  |  | ORD/000083/2023-2024 | 1076/DWSD | 12/07/2023 | 06/08/2023 | CHATTERJEE CONSTRUCTION | 4.69 | 0 | 0 | 0
20 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte | SM/10203 | Augmentation | Formal order for the work of Supplying laying and aligning of HDPE distribution pipe line and Other allied works under command area of ARRAH Mouza (Part-D) under Augmentation of Roopganj piped W/s Scheme under DWSD,PHE Dte (SL-04) |  |  | ORD/000421/2021-2022 | 397/DWSD | 28/03/2022 | 27/04/2022 | M/S BADAL GHOSH | 74.2 | 71 | 95.68 | 0
21 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte | SM/10203 | Augmentation | Acceptance cum formal order for the work of Providing functional household tap connection (FHTC) in connection with JAL JEEBAN MISSION(JIM) for Arrah mouza (JL-91) (Pt-A) under command area of Rupganj W/S Scheme at Kanksa Block under Durgapur W/S Division, PHE Dte |  |  | ORD/000372/2020-2021 | 144/DWSD | 28/01/2021 | 14/03/2021 | M/S KALYANI ENTERPRISE | 28.83 | 28.84 | 100.05 | 0
22 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte | SM/10203 | Augmentation | Acceptance cum formal order for the work of 2 Nos trial bore by direct rotary method drilling using rig machine at Roopganj H/W Site ,Tube well No-I &II of Augmentation of Roopganj piped W/s Scheme under DWSD ,PHE Dte(SL-16) |  |  | ORD/000329/2021-2022 | 1803/DWSD | 28/12/2021 | 07/01/2022 | M/S KALYANI ENTERPRISE | 2.32 | 1.16 | 50 | 0
23 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte | SM/10203 | Augmentation | Acceptance cum formal order for the work details route survey, drawing design of distribution network & preparation of estimates and DPR in connection with the JJM (FHTC) of Augmentation of Roopganj Piped W/s Scheme under, DWSD, PHE Dte.(SL-01) |  |  | ORD/000335/2021-2022 | 1684/DWSD | 02/12/2021 | 01/01/2022 | M/S R.DUTTA AND CO. | 6.39 | 6.39 | 100 | 0
24 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte | SM/10203 | Augmentation | Acceptance cum formal order for the work of water supply arrangement at different places to combat water crisis at Kanksa block of Arrah ,Roopganj and Araichand under Roopganj piped W/s Scheme under DWSD ,PHE Dte (SL-11) |  |  | ORD/000324/2021-2022 | 1797/DWSD | 24/12/2021 | 31/12/2021 | M/S KALYANI ENTERPRISE | 4.99 | 4.99 | 100 | 0
25 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte | SM/10203 | Augmentation | Acceptance cum formal order for the work of Repairing of leakage bursting and chokage cleaning at Arrah Distribution main and other allied work for Roopganj piped W/s Scheme all command area of Roopganj W/s Scheme under DWSD, PHE Dte.(SL-05) |  |  | ORD/000441/2021-2022 | 420/DWSD | 30/03/2022 | 14/04/2022 | M/S KALYANI ENTERPRISE | 4.1 | 4.09 | 99.92 | 100
26 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte | SM/10203 | Augmentation | Acceptance cum formal order for the work of Additional FHT work of Arrah mouza and Roopganj mouza part under command area of Augmentation of Roopganj Piped W/S Scheme under DWSD ,PHE Dte(SL-03) |  |  | ORD/000155/2022-2023 | 1023/DWSD | 04/07/2022 | 14/07/2022 | QUICK PAL SUPPLIERS | 4.98 | 4.98 | 100 | 0
27 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte | SM/10203 | Augmentation | Acceptance cum formal order for the work of Sanitary arrangement and plumbing work at Molandighi H/W site pump house no-II tube wno II for Bistupur piped W/S Scheme under DWSD, PHE Dte(SL-04) |  |  | ORD/000140/2022-2023 | 961/DWSD | 17/06/2022 | 27/06/2022 | BABA LOKENATH ENTERPRISE | 4.8 | 3.91 | 81.48 | 100
28 | PASCHIM BARDHAMAN |  | Central Mechanical | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte | SM/10203 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 3 at Rupganj Water Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000159/2022-2023 | 1244/CMD | 12/07/2022 | 11/08/2022 | DEY ENTERPRISE | 9.86 | 9.52 | 96.56 | 80
29 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte | SM/10203 | Augmentation | Formal order for the work of Laying and aligning of distribution pipe line from Hetedoba OHR,DI Specials ,Valves and allied works under Augmentation of Roopganj piped W/s Scheme under DWSD ,PHE Dte. |  |  | ORD/000439/2022-2023 | 299/DWSD | 20/02/2023 | 12/03/2023 | BABA LOKENATH ENTERPRISE | 16.32 | 16.06 | 98.41 | 0
30 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte | SM/10203 | Augmentation | Acceptance cum formal order for the work of Emergent work of Concreting of exiting dismantled road of Augmentation of Roopganj piped W/S Scheme under DWSD,PHE Dte |  |  | ORD/000046/2023-2024 | 769/DWSD | 18/04/2023 | 28/04/2023 | M/S BADAL GHOSH | 4.78 | 4.76 | 99.64 | 100
31 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte | SM/10203 | Augmentation | Acceptance cum formal order for the work of Emergency work of concreting of exiting dismantled road at ARRAH mouza of Augmentation of Roopganj piped W/s Scheme under DWSD,PHE Dte |  |  | ORD/000036/2023-2024 | 742/DWSD | 16/05/2023 | 31/05/2023 | M/S BADAL GHOSH | 4.78 | 4.75 | 99.47 | 100
32 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte | SM/10203 | Augmentation | Repairing of existing concrete road restoration and other allied works under Augmentation of Roopganj piped W/s Scheme under DWSD,PHE Dte (Part-D) |  |  | ORD/000157/2023-2024 | 1288/DWSD | 07/08/2023 | 27/08/2023 | CHANDAN HAZRA | 8.69 | 0 | 0 | 100
33 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte | SM/10203 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000013/2021-2022 | 331/DWSD | 15/03/2022 | 15/03/2022 | Resource Division | 41.84 | 0 | 0 | 0
34 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte | SM/10203 | Augmentation | Electricity service connection rupganj piped W/s Scheme |  |  | BILL/00153/2023-2024 | BP-2023-24-94 | 24/07/2023 | 24/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.95 | 0 | 0 | 0
35 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte | SM/10203 | Augmentation | Acceptance cum formal order for the work of Laying ,aligning of DI K9 rising main pipe and interconnection between 3 TW with OHR and other allied works of Augmentation of Roopganj piped W/S Scheme under DWSD ,PHE Dte |  |  | ORD/000508/2022-2023 | 325/DWSD | 20/02/2023 | 17/03/2023 | M/S KALYANI ENTERPRISE | 24.33 | 0 | 0 | 100
36 | PASCHIM BARDHAMAN |  | Asansol Mechanical | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte | SM/10203 | Augmentation | Supply & installation of Submersible Pumping Machineries, Voltage Stabilizer, Chlorination System and internal House wiring for Rupganj Water Supply Scheme, P/H No-05 under Asansol Mechanical Division, P.H.E Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000633/2023-2024 | 532/AMD | 12/03/2024 | 10/06/2024 | M/S S.G.ENTERPRISE | 11.47 | 0 | 0 | 100
37 | PASCHIM BARDHAMAN |  | Central Mechanical | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte | SM/10203 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 4 at Rupganj Water Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000154/2022-2023 | 1242/CMD | 12/07/2022 | 11/08/2022 | AHALYA ENGINEERING WORKS | 10.2 | 0 | 0 | 100
38 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte | SM/10203 | Augmentation | Replacement of existing pipe line at Nachan OHR to Bansia gram for Physical certification of Har Ghar Jal in connection with JJM of Augmentation Roopganj piped W/s Scheme under DWSD ,PHE Dte |  |  | ORD/000086/2023-2024 | 719/DWSD | 11/05/2023 | 05/06/2023 | CHANDAN HAZRA | 23.76 | 0 | 0 | 100
39 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte | SM/10203 | Augmentation | Construction of 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 2000mm) with Sanitary and water Supply arrangement at kanchanpur of kanksa block under Augmentation of Roopganj Piped W/S Scheme under DWSD PHE Dte. | Assistant Engineer 3 | Junior Engineer 7 | ORD/001227/2023-2024 | 1293/DWSD | 07/08/2023 | 21/09/2023 | MAJI DEVELOPERS | 6.09 | 0 | 0 | 100
40 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte | SM/10203 | Augmentation | Construction of 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 2000mm) with Sanitary and water Supply arrangement at Kanksa Zone II/Part C under Augmentation of Roopganj Piped W/S Scheme. | Assistant Engineer 3 | Junior Engineer 7 | ORD/001234/2023-2024 | 1277_DWSD | 07/08/2023 | 21/09/2023 | PRADIP CHOUDHARY | 5.83 | 0 | 0 | 100
41 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte | SM/10203 | Augmentation | Proposal for diversion of forest land for consytruction of OHR Capacity 350 cum of Augmentation of Roopganj Piped water supply scheme (JJM Work) under Durgapur W/S Division, PHE Directoreate - Demand note for payment of NPV, CA, Boundary demarcation witll pillar fencing etc. :- Cost of Boundary demarcation with pillar |  |  | BILL/00146/2024-2025 | 66/24-25 | 28/05/2024 | 28/05/2024 | DIVISIONAL FOREST OFFICER, BURDWAN DIVISION | 0.3 | 0 | 0 | 0
42 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte | SM/10203 | Augmentation | Proposal for diversion of forest land for consytruction of OHR Capacity 350 cum of Augmentation of Roopganj Piped water supply scheme (JJM Work) under Durgapur W/S Division, PHE Directoreate - Demand note for payment of NPV, CA, Boundary demarcation witll pillar fencing etc. |  |  | BILL/00105/2024-2025 | 53/24-25 | 20/05/2024 | 20/05/2024 | DIVISIONAL FOREST OFFICER, BURDWAN DIVISION | 0.8 | 0 | 0 | 0
43 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte | SM/10203 | Augmentation | Acceptance cum work order for Sinking of 2 nos of 300 x 200 mm dia tube well 210 mtr deep by D.R. Rig method using UPVC pipe (CD) and UPVC deep well screen (RDS) at Bandra village and Roopganj of Augmentation of Roopganj PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 3 | Junior Engineer 6 | ORD/000456/2025-2026 | 2009/RCD-I | 11/07/2025 | 31/07/2025 | M/S KALYANI ENTERPRISE | 27.78 | 0 | 0 | 100
44 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of Roopganj piped Water Supply Scheme of Kanksa Block under Durgapur W/s Division PHE Dte | SM/10203 | Augmentation | Acceptance cum work order for Balance work of Rising Main from Tube Well to OHR at Roopganj Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 3 | Junior Engineer 6 | ORD/000045/2024-2025 | 1646/RCD-I | 04/07/2024 | 03/03/2025 | M/S KALYANI ENTERPRISE | 12.36 | 0 | 0 | 100
Total | [13 empty] | 914.49 | 607.57 | 66.44