## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) | SM/10209 | Augmentation | Quotation for Kanksa Zone-II/Part-C Pump house no -01 |  |  | VCH/000225/2022-2023 | BP-2022-23-97 | 14/06/2022 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.43 | 0 | 0 | 0
2 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) | SM/10209 | Augmentation | Quotation for Kanksa Zone-II/Part-C Pump house no -03 |  |  | VCH/000227/2022-2023 | BP-2022-23-99 | 14/06/2022 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.33 | 0 | 0 | 0
3 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) | SM/10209 | Augmentation | Quotation for Kanksa Zone-II/Part-C Pump house no -02 |  |  | VCH/000226/2022-2023 | BP-2022-23-98 | 14/06/2022 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.33 | 0 | 0 | 0
4 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) | SM/10209 | Augmentation | Acceptance cum formal order for the work of Construction of Guard room cum rest shed at Kanksa Ijjatganj 2nd Pump house site of Augmentation of Kaksa (Zone-II) /Part-C) piped W/S Scheme under DWSD,PHE Dte (SL-09) |  |  | ORD/000123/2022-2023 | 785/DWSD | 18/05/2022 | 02/06/2022 | BASANTI TRADERS | 4.99 | 4.05 | 81.24 | 0
5 | PASCHIM BARDHAMAN |  | Central Mechanical | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) | SM/10209 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-2 at Augmentation of Kanksa [Zone-II / C ] Water Supply Scheme under CMD, PHE Dte., Dist.- Paschim-Bardhaman |  |  | ORD/000015/2022-2023 | 978/CMD | 14/06/2022 | 14/07/2022 | ANANTA ELECTRICAL ENGINEERING CONSTRUCTION | 8.94 | 8.61 | 96.39 | 0
6 | PASCHIM BARDHAMAN |  | Central Mechanical | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) | SM/10209 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 at Augmentation of Kanksa [Zone-II / C ] Water Supply Scheme under CMD, PHE Dte., Dist.- Paschim-Bardhaman |  |  | ORD/000004/2022-2023 | 735/CMD | 29/04/2022 | 29/05/2022 | STANDARD ELECTRICALS | 9.22 | 8.99 | 97.5 | 0
7 | PASCHIM BARDHAMAN |  | Central Mechanical | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) | SM/10209 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-3 at Augmentation of Kanksa [Zone-II / C ] Water Supply Scheme under CMD, PHE Dte., Dist.- Paschim-Bardhaman |  |  | ORD/000014/2022-2023 | 979/CMD | 14/06/2022 | 14/07/2022 | ANANTA ELECTRICAL ENGINEERING CONSTRUCTION | 8.94 | 8.67 | 97.08 | 0
8 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) | SM/10209 | Augmentation | Acceptance cum formal order Additional work for providing FHTC tap connection with JJM at Kanksa mouza-89 and its adjoing are a under command area of Augmentation of Kanksa Zone-II/C W/s Scheme at Kanksa block under DWSD ,PHE Dte (SL-04) |  |  | ORD/000156/2022-2023 | 1024/DWSD | 04/07/2022 | 14/07/2022 | QUICK PAL SUPPLIERS | 4.98 | 4.98 | 100 | 0
9 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) | SM/10209 | Augmentation | Formal-Order for the work of Laying and aligning of distribution network of command area of Kanksa (Zone-II/C) and other allied works under Augmentation of Kanksa (Zone-II/Part-C) piped W/s Scheme |  |  | ORD/000444/2022-2023 | 301/DWSD | 20/02/2023 | 12/03/2023 | BABA LOKENATH ENTERPRISE | 16.09 | 16.09 | 100 | 0
10 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) | SM/10209 | Augmentation | Acceptance cum formal order for the work of Construction of boundary wall at Kanksa (Zone-II & Ph-I W/s Scheme pump house No-II at Ijjatganj under DWSD ,PHE Dte (SL-04) |  |  | ORD/000392/2020-2021 | 186/DWSD | 04/02/2021 | 21/03/2021 | M/S BADAL GHOSH | 4.92 | 4.68 | 95.1 | 0
11 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) | SM/10209 | Augmentation | Formal order for the work of Details route survey, drawing design of distribution network & preparation of estimates and DPR in connection with the JJM (FHTC) of Augmentation of Kanksa (Zone-II) piped W/S Scheme DWSD,PHE Dte.(SL-05) |  |  | ORD/000181/2021-2022 | 1601/DWSD | 12/11/2021 | 12/12/2021 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 19.55 | 19.55 | 100 | 0
12 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) | SM/10209 | Augmentation | Formal order for the work of Additional work for providing FHTC in connection with JJM for Kanksa mouzza (JL-89) under command area of Kanksa (Zone-II) Ph-II W/s Scheme at Kanksa block under DWSD ,PHE Dte (SL-03) |  |  | ORD/000348/2021-2022 | 199/DWSD | 16/02/2022 | 03/03/2022 | GITA CONSTRUCTION | 9.72 | 1.16 | 11.95 | 0
13 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) | SM/10209 | Augmentation | Formal order for the work of Additional FHTC in connection with JJM for Prayagpur (CT) mouza (JL-88) under command area of Kanksa (Zone-II)(Ph-II) W/S Scheme at Kanksa block under DWSD PHE Dte . |  |  | ORD/000312/2021-2022 | 1766/DWSD | 16/12/2021 | 15/01/2022 | B. T. M. CONCERN | 19.37 | 19.61 | 101.19 | 0
14 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) | SM/10209 | Augmentation | Acceptance cum formal order for the work of Providing water supply to Birudiha High school under Kanksa block covered by Kanksa (Zone-II) having electricity but uncovered by PWSS under DWSD, PHE Dte (SL-26) |  |  | ORD/000382/2021-2022 | 120/DWSD | 01/02/2022 | 21/02/2022 | BASANTI TRADERS | 2.11 | 0 | 0 | 0
15 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) | SM/10209 | Augmentation | Continuation order for the work of supplying fitting fixing and installation of Sluice Valve for O & Mtc of Kanksa (Zone-II/II) piped W/s Scheme of command areas of Panaghar ,Prayagpur mouza under DWSD, PHE Dte |  |  | ORD/000117/2022-2023 | 682/DWSD | 27/04/2022 | 12/05/2022 | TARA CONSTRUCTION | 4.94 | 0 | 0 | 0
16 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) | SM/10209 | Augmentation | Acceptance order for the work of Laying and aligning rising main pipe line supplying of DI specials ,valves and allied works at Akandara under command area of Augmentation of Kanksa (Zone-II/C)(Part-B) piped W/s Scheme under DWSD ,PHE Dte. |  |  | ORD/000450/2022-2023 | 298/DWSD | 20/02/2023 | 22/03/2023 | MAK CONSTRUCTION CO. | 92.36 | 91.71 | 99.29 | 0
17 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) | SM/10209 | Augmentation | Acceptance cum formal order for the work of Sinking of 06 Nos 300X200 mm dia Tube well with 210 mtr Depth by DR rig method using UPVC pipe (CD and UPVC deep well screen (RDS) at Kanksa (Zone-II) Part-B,C tube well site of Augmentation of Kanksa Zone-II(Part-B & C) piped W/s Scheme under DWSD ,PHE Dte (SL-02) |  |  | ORD/000454/2022-2023 | 254/DWSD | 15/02/2023 | 16/04/2023 | JOY GURU ENTERPRISE | 94.05 | 0 | 0 | 0
18 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) | SM/10209 | Augmentation | Replacement of damaged PCC pole with allied work. |  |  | BILL/00032/2023-2024 | BP-2023-24-24 | 17/05/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.69 | 0 | 0 | 0
19 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) | SM/10209 | Augmentation | Acceptance cum formal order for the work of Laying and aligning of DI K9 rising main pipe line supplying DI specials ,valves and allied work at Kanchanpur and Kanksa under command area of Augmentation of Kanksa Zone-II/C piped W/s Scheme under DWSD ,PHE Dte |  |  | ORD/000013/2023-2024 | 677/DWSD | 03/05/2023 | 23/05/2023 | JOY GURU ENTERPRISE | 29.76 | 28.62 | 96.16 | 100
20 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) | SM/10209 | Augmentation | Repairing and renovation of pump house with sanitary arrangement as well as boundary wall at H/W site (Ijjatganj OHR) of Augmentation of Kaksa (Zone-II/Pt-C) piped W/s Scheme |  |  | ORD/000124/2023-2024 | 1198/DWSD | 27/07/2023 | 26/08/2023 | MAITO MAA ENTERPRISE | 14.93 | 0 | 0 | 0
21 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) | SM/10209 | Augmentation | Acceptance cum formal order for the work of Repairing of MS structural and supplying hoisting 2000 Liters PVC water storage tank and others allied works at Kanksa of Augmentation of Kanksa (Zone-II/C) W/s Scheme under DWSD,PHE Dte (SL-07) |  |  | ORD/000200/2022-2023 | 1062/DWSD | 08/07/2022 | 02/08/2022 | SWATI CORPORATION | 3.53 | 3.24 | 91.68 | 100
22 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) | SM/10209 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000011/2021-2022 | 328/DWSD | 15/03/2022 |  | Resource Division | 38.73 | 0 | 0 | 0
23 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) | SM/10209 | Augmentation | Acceptance cum work order for Trial run and special Maintenance of Rising main and Distribution system with operating of valve within command area under Augmentation of Kanksa Zone-II (Part-C) PWSS, JJM under RCFA Division-I PHE Dte. 6 (Six) Months. | Assistant Engineer 2,Assistant Engineer 3 | Junior Engineer 7 | ORD/001068/2023-2024 | 687/RCD-I | 29/02/2024 | 27/08/2024 | MALLICK CONSTRUCTION | 1.85 | 0 | 0 | 0
24 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) | SM/10209 | Augmentation | Acceptance cum work order for Trial run and special Maintenance of Rising main and Distribution system with operating of valve within command area under Augmentation of Kanksa Zone-II (Part-D) PWSS, JJM under RCFA Division-I PHE Dte. 6 (Six) Months | Assistant Engineer 3 | Junior Engineer 15 | ORD/001033/2023-2024 | 688/RCD-1 | 29/02/2024 | 27/08/2024 | AMARANJALI CONSTRUCTION | 1.79 | 0 | 0 | 0
25 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) | SM/10209 | Augmentation | Acceptance cum formal order for the work of construction of 5.40 mtr X 3.60 mtr switch room with plinth height (600 to 2000 mm) with sanitary and water supply arrangemnt at Kanksa of Kanksa Block under Augmentation of Kanksa (Zone-II) (Part-C) piped W/S Scheme under DWSD,PHE Dte |  |  | ORD/000147/2023-2024 | 1277/DWSD | 07/08/2023 | 21/09/2023 | PRADIP CHOUDHARY | 5.83 | 0 | 0 | 100
26 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) | SM/10209 | Augmentation | Acceptance cum work order for Trial run and special Maintenance of Distribution system with operating of valve within command area under Augmentation of Kanksa Zone-I PWSS, JJM under RCFA Division-I PHE Dte. 6 (Six) Months | Assistant Engineer 2,Assistant Engineer 3 | Junior Engineer 6 | ORD/001076/2023-2024 | 691/RCD-I | 29/02/2024 | 27/08/2024 | SREE ENTREPRENEUR | 1.63 | 0 | 0 | 0
27 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) | SM/10209 | Augmentation | 1(One) No PWD road crossing SH-34 at Mini bazar more under command area of Kanksa Zone-II/Pt-C distribution main by modern trenches less technology through JACK Pushing method under Augmentation of Kanksa Zone-II/Part-C piped W/s Scheme under DWSD ,PHE Dte |  |  | ORD/000155/2023-2024 | 1286/DWSD | 07/08/2023 | 22/08/2023 | MACHINO TECHNO | 10.92 | 0 | 0 | 100
28 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) | SM/10209 | Augmentation | Acceptance cum formal order for the work of 1(One) No PWD road crossing SH-34 at kanksa underpass under command area of Kanksa Zone-II/Pt-C distribution main by modern trenches less technology through JACK Pushing method under Augmentation of Kanksa Zone-II/Part-C piped W/s Scheme under DWSD ,PHE Dte |  |  | ORD/000143/2023-2024 | 1274/DWSD | 07/08/2023 | 22/08/2023 | MRITYUNJOY MUKHERJEE AND CO | 12.05 | 0 | 0 | 91
29 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) | SM/10209 | Augmentation | Acceptance cum work order for Trial run and special Maintenance of Rising main and Distribution system with operating of valve within command area under Augmentation of Kanksa Zone-II (Part-B) PWSS, JJM under RCFA Division-I PHE Dte. 6 (Six) Months | Assistant Engineer 2,Assistant Engineer 3 | Junior Engineer 7 | ORD/001031/2023-2024 | 686/RCD-1 | 29/02/2024 | 27/08/2024 | MD AAMIR KHAN | 2.51 | 0 | 0 | 0
30 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) | SM/10209 | Augmentation | Construction of 5.40 mtr X 3.60 mtr switch room with plinth height (600 to 2000 mm) with sanitary and water supply arrangement at Kanchanpur of Kanksa Block under Augmentation of Kanksa (Zone-II) (Part-C) piped W/S Scheme under DWSD,PHE Dte |  |  | ORD/000161/2023-2024 | 1293/DWSD | 07/08/2023 | 21/09/2023 | MAJI DEVELOPERS | 6.09 | 0 | 0 | 100
31 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of ground water based piped W/s Scheme for Kanksa (Zone-II/Part-C) to accommodate FHTC ,Block-Kanksa, Dist-Paschim Bardhaman (WB) | SM/10209 | Augmentation | Acceptance cum work order for Separate connection for Ijjatgunj OHR Kanksa Zone-II (Part-C) under RCFA Division - I PHE Dte. | Assistant Engineer 3 |  | ORD/000141/2024-2025 | 2245/RCD-I | 11/09/2024 | 11/10/2024 | COMPUTER MEDIA | 6.62 | 0 | 0 | 0
Total | [13 empty] | 446.2 | 219.96 | 49.3