## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) | SM/10211 | Augmentation | Acceptance cum formal order for the work of Construction of Pump house cum Chlorine room at Madhabmat Pump house No-I tube well no-1 for Augmentation of Kanksa (Zone-II/Part-A) piped W/S Scheme under DWSD, PHE Dte (SL-04) |  |  | ORD/000458/2021-2022 | 379/DWSD | 24/03/2022 | 08/05/2022 | MUKHERJEE ENTERPRISE | 4.89 | 4.7 | 96.15 | 0
2 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) | SM/10211 | Augmentation | Formal order for the work of Supplying and laying of 90/75 mm dia HDPE pipe and 63/50 mm dia UPVC pipe line with necessary allied work at Sundiara and Tilakchnadrapur mouza JL-63/67) under Augmentation of Kanksa (Zone-II/Part-A) piped W/s Schme for providing FHTC under DWSD ,PHE Dte (SL-02) |  |  | ORD/000408/2021-2022 | 312/DWSD | 11/03/2022 | 26/03/2022 | SK. ABDUL HALIM | 9.12 | 9.11 | 99.91 | 0
3 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) | SM/10211 | Augmentation | Formal order for the work of Additional work for providing FHTC tap connection with jjm at Ijjatganj mouza(JL-71) and laying 125 mm dia HDPE and 63/50 mm dia UPVC pipe under command area of Augmentation of Kanksa (Zone-II/Part-A) piped W/s Schme for providing FHTC under DWSD ,PHE Dte |  |  | ORD/000409/2021-2022 | 333/DWSD | 15/03/2022 | 30/03/2022 | RANJIB GHATAK | 29.48 | 29.65 | 100.57 | 0
4 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) | SM/10211 | Augmentation | Formal order for the work of Sinking of 1 No 300X200 mm dia tube well ,210 mtr of depth by Direct Rotary method using PVC Pipe and Fiber Strainer reinforced epoxy slotted at Madhabmat Pump House No-1 under command area of Augmentation of Kanksa (Zone-II/Part-A) piped W/s Scheme under DWSD, PHE Dte.(SL-02) |  | Junior Engineer_3 | ORD/000002/2022-2023 | 660/DWSD | 22/04/2022 | 02/05/2022 | RANJIB GHATAK | 14.01 | 12.95 | 92.45 | 0
5 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) | SM/10211 | Augmentation | Formal order for the work of Sinking of 1 No 300X200 mm dia tube well ,210 mtr of depth by Direct Rotary method using PVC Pipe and Fiber Strainer reinforced epoxy slotted at Madhabmat Pump House No-2 under command area of Augmentation of Kanksa (Zone-II/Part-A) piped W/s Scheme under DWSD, PHE Dte. |  | Junior Engineer_3 | ORD/000003/2022-2023 | 653/DWSD | 22/04/2022 | 02/05/2022 | JOY GURU ENTERPRISE | 14 | 11.75 | 83.89 | 0
6 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) | SM/10211 | Augmentation | Formal order for the work of Sinking of 1 No 300X200 mm dia tube well ,210 mtr of depth by Direct Rotary method using PVC Pipe and Fiber Strainer reinforced epoxy slotted at Madhabmat Pump House No-2 under command area of Augmentation of Kanksa (Zone-II/Part-A) piped W/s Scheme under DWSD, PHE Dte.(SL-04) |  |  | ORD/000004/2022-2023 | 548/DWSD | 08/04/2022 | 18/04/2022 | AHS R INFRA PRIVATE LIMITED | 14.04 | 13.02 | 92.75 | 0
7 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) | SM/10211 | Augmentation | Continuation order for the work of soil investigation for determing the safe bearing capacity and other relevant parameters of soil for the work of construction of RCC elevated at Madhabmath Reservoir site of Augmentation of Kanksa (Zone-II/A) piped W.S Scheme under DWSD ,PHE DTe. |  |  | ORD/000470/2021-2022 | 354/DWSD | 21/03/2022 | 15/04/2022 | MABCO CONSULTANT | 1.2 | 1.2 | 100 | 0
8 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) | SM/10211 | Augmentation | Acceptance cum formal order for the work of Construction of Pump house cum Chlorine room at Madhabmat Pump house No-III tube well no-3 for Augmentation of Kanksa (Zone-II/Part-A) piped W/S Scheme under DWSD, PHE Dte (SL-06) |  |  | ORD/000461/2021-2022 | 385/DWSD | 25/03/2022 | 09/05/2022 | A.K.D. ENTERPRISE | 4.89 | 4.7 | 96.28 | 0
9 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) | SM/10211 | Augmentation | Acceptance cum formal order for the work of Construction of Pump house cum Chlorine room at Madhabmat Pump house No-II tube well no-2 for Augmentation of Kanksa (Zone-II/Part-A) piped W/S Scheme under DWSD, PHE Dte(SL-05) |  |  | ORD/000459/2021-2022 | 583/DWSD | 25/03/2022 | 09/05/2022 | GHOSH & ROY ENTERPRISE | 4.89 | 4.69 | 95.9 | 0
10 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) | SM/10211 | Augmentation | Formal order for the work of Laying and aligning of DI K9 rising main pipe line supplying DI Specials valves and other allied works at Madhabmat under command area of Augmentation of Kanksa (Zone-II/Part-A) piped W/s Scheme under DWSD, PHE Dte.(SL-01) |  | Junior Engineer_3 | ORD/000001/2022-2023 | 659/DWSD | 22/04/2022 | 02/05/2022 | BASANTI TRADERS | 10.58 | 8.45 | 79.84 | 100
11 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) | SM/10211 | Augmentation | Formal order for the work of supplying ,laying of distribution system and providing functional house hold tap connection (FHTC) including reconnection of existing FHTC from AC pipe line to newly laid different dia HDPE pie line for Kanksa (zone-II/A) piped W/s Scheme under DWSD,PHE Dte (Augmentation Scheme) Dist.-Paschim Bardhhaman. |  |  | ORD/000251/2022-2023 | 1361/DWSD | 20/09/2022 | 20/01/2023 | SAIKAT RAY | 236.37 | 239.55 | 101.34 | 0
12 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) | SM/10211 | Augmentation | Acceptance cum formal order for the work of Construction of boundary wall at Madhabmat H/W site (PH No-3,TW No-3) site under Augmentation of Kanksa Zone-II/Part-A piped W/s Scheme under DWSD ,PHE Dte |  |  | ORD/000524/2022-2023 | 297/A/DWSD | 17/02/2023 | 19/03/2023 | A.K.D. ENTERPRISE | 11.08 | 9.88 | 89.2 | 0
13 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) | SM/10211 | Augmentation | Formal order for the work of Construction of 500 M3 capacity, 20 mtr staging height Over Head Reservoir at Madhabmat Tube well No-1 Kanksa (Zone-II/Part-A) piped W/S Scheme under DWSD , PHE Dte (SL-05) |  | Junior Engineer_3 | ORD/000005/2022-2023 | 571/DWSD | 12/04/2022 | 13/10/2022 | SAIKAT RAY | 99.22 | 95.07 | 95.81 | 100
14 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) | SM/10211 | Augmentation | Continuation order for the work of supplying fitting fixing and installation of Sluice Valve for O & Mtc of Kanksa (Zone-II/II) piped W/s Scheme of command areas of Panaghar ,Prayagpur mouza under DWSD, PHE Dte |  |  | ORD/000117/2022-2023 | 682/DWSD | 27/04/2022 | 12/05/2022 | TARA CONSTRUCTION | 4.94 | 0 | 0 | 0
15 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) | SM/10211 | Augmentation | Acceptance cum formal order for the work of Additional work for providing FHTC tap connection with JJN at Debipur mouza -87 and its adjoining area under command area of Augmentation of Kanksa (Zone-II/A ) piped W/s Scheme at Kanksa block under DWSD, PHE Dte (SL-12) |  |  | ORD/000162/2022-2023 | 1032/DWSD | 04/07/2022 | 14/07/2022 | QUICK PAL SUPPLIERS | 4.99 | 4.99 | 100 | 0
16 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) | SM/10211 | Augmentation | Acceptance cum Formal work-Order for the work of ---Sanitary arrangement and plumbing works at Madhabmat Pump house No-1 Tube well No-01(OHR Site) for Augmentation of Kanksa (Zone-II/A) pipe W/S Scheme under DWSD,PHE Dte (SL-02) |  |  | ORD/000195/2022-2023 | 1055/DWSD | 07/07/2022 | 01/08/2022 | MUKHERJEE ENTERPRISE | 4.82 | 4.44 | 92.21 | 100
17 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) | SM/10211 | Augmentation | Acceptance cum Formal work-Order for the work of ---Sanitary arrangement and plumbing works at Madhabmat Pump house No-2 Tube well No-02 for Augmentation of Kanksa (Zone-II/A) pipe W/S Scheme under DWSD,PHE Dte (SL-03) |  |  | ORD/000196/2022-2023 | 1056/DWSD | 07/07/2022 | 01/08/2022 | GHOSH & ROY ENTERPRISE | 4.82 | 4.44 | 92.21 | 100
18 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) | SM/10211 | Augmentation | Acceptance cum formal order for the work of Sanitary arrangement and plumbing works at Madhabmat Pump house No-3 Tube well No-03 for Augmentation of Kanksa (Zone-II/A) pipe W/S Scheme under DWSD,PHE Dte (SL-01) |  |  | ORD/000201/2022-2023 | 1063/DWSD | 08/07/2022 | 02/08/2022 | A.K.D. ENTERPRISE | 4.82 | 4.42 | 91.86 | 100
19 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) | SM/10211 | Augmentation | Formal order for the work of balance work of Augmentation of Kanksa (Zone-II/Part-A) piped W/s Scheme with construction of boundary wall ,approach road,canal crossing ,leftout LDS,FHTC reconnection of FHTC at Kansa(Part),Debipur(Part),Panagarh(Part),Ijjatganj(Part), mouzas of JL-86,88,87,85 of Kanksa block under DWSD ,PHE Dte (SL-03) |  |  | ORD/000451/2022-2023 | 225/DWSD | 06/02/2023 | 07/05/2023 | SAIKAT RAY | 197.71 | 163.93 | 82.91 | 100
20 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) | SM/10211 | Augmentation | Acceptance order for the work of Laying and aligning of distribution pipe line from zero point and allied works under Augmentation of Kanksa Zone-II/Part-A) piped W/s Scheme under DWSD ,PHE Dte. |  |  | ORD/000441/2022-2023 | 104/DWSD | 24/01/2023 | 13/02/2023 | PAYAL CONSTRUCTION | 8.6 | 8.59 | 99.88 | 0
21 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) | SM/10211 | Augmentation | Acceptance cum formal order for the work of Balance work of Augmentation of Kanksa Zone-ii/C piped W/s Scheme with construction of boundary wall renovation of all existing structure repairing of all water retaining structure left out LDS FHTC reconnection of FHTC at Kanksa (Part) ,Debipur (Part), Paragraph (Part), Prayagpur(Part) mouzas of JL-86,88,87 of Kanksa block under DWSD ,PHE Dte |  |  | ORD/000572/2022-2023 | 490/DWSD | 23/03/2023 | 07/05/2023 | BRINDABAN KONAR | 94.94 | 3.85 | 4.05 | 100
22 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) | SM/10211 | Augmentation | Approach road & others necessary allied works at Madhabmat 2nd Pump house to 3rd Pump House ,Kanksa for Kanksa Zone-II/A W/s Scheme under DWSD ,PHE Dte |  |  | ORD/000115/2023-2024 | 1057/DWSD | 20/07/2023 | 19/08/2023 | A.K.D. ENTERPRISE | 25.4 | 25.36 | 99.83 | 100
23 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) | SM/10211 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000009/2021-2022 | 307/DWSD | 15/03/2022 | 15/03/2022 | Resource Division | 45.42 | 0 | 0 | 0
24 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) | SM/10211 | Augmentation | Electricity service connection charges for Kanksa Zone-II Part-A TW-1 |  |  | BILL/00164/2023-2024 | BP-2023-24-104 | 24/07/2023 | 24/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.04 | 0 | 0 | 0
25 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) | SM/10211 | Augmentation | Road restoration at Panagarh Silampur Road (ch 2.5 KM to 3.5 KM) to be executed by Executive Engineer, Asansol Highway Division, PWD Roads directorate for the work of repairing of damaged at Panagarh Silampur |  |  | BILL/00441/2023-2024 | BP-2023-24-221 | 21/09/2023 | 21/09/2023 | EXECUTIVE ENGINEER , ASANSOL HIGHWAY DIVISION, PWD ROADS | 17.96 | 0 | 0 | 0
26 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) | SM/10211 | Augmentation | Quotation money for service connection Kanksa Zone-II Part-A TW-III |  |  | BILL/00166/2023-2024 | BP-2023-24-106 | 24/07/2023 | 24/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.99 | 0 | 0 | 0
27 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) | SM/10211 | Augmentation | Electricity charges for installation of service connection for Kanksa Zone-II Part-A TW-II |  |  | BILL/00165/2023-2024 | BP-2023-24-105 | 25/07/2023 | 25/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.87 | 0 | 0 | 0
28 | PASCHIM BARDHAMAN |  | RCFA Division -I | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) | SM/10211 | Augmentation | Hiring of Maxi Cab (Non Air Conditional ) Bharat Stage-iii/BS-ii purchased on or after 01.05.2008 with Diesel /LPG /CNG Engine for the supervision work of Durgapur W/S Division for office use of Assitant Engineer, RCFA Division-I Public Helth Engineering Directorate, Govt of West Bengal ( w.e.f 01.12.2023. to 31.05.2024) Consumption of Diesel,12 km per litre, Mobil 05 litre per 2500 km. | Assistant Engineer 3 | Junior Engineer 9 | ORD/000727/2023-2024 | 3514/RCD-I | 30/11/2023 | 30/05/2024 | SUBHA TOUR & TRAVELS | 0.89 | 0.8 | 89.34 | 35
29 | PASCHIM BARDHAMAN |  | Central Mechanical | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) | SM/10211 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1, 2 & 3 at Augmentation of Kanksa Zone - II/A Water Scheme under CMD, PHE Dte., Dist.- Paschim-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000072/2023-2024 | 2571/CMD | 06/06/2023 | 06/01/2025 | M/S. SWAPAN BANERJEE | 29.92 | 9.58 | 32.01 | 31
30 | PASCHIM BARDHAMAN |  | Durgapur W/S Division | Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC ,Block-Kanksa,Dist-Paschim Barddhaman(WB) | SM/10211 | Augmentation | Acceptance cum formal order for the work of 1(One) No PWD road crossing SH-34 at Railpar Sarada Pally near DVC Canal under command area of Kanksa Zone-II/Pt-A distribution main by modern trenches less technology through JACK Pushing method under Augmentation of RCFA part III Zone I piped W/s Scheme under DWSD ,PHE Dte |  |  | ORD/000142/2023-2024 | 1272/DWSD | 07/08/2023 | 18/04/2025 | SAIKAT RAY | 8.56 | 0 | 0 | 100
Total | [13 empty] | 923.43 | 675.1 | 73.11